## Sheet1
A customer project team member said that we haven't been told about the complexity of STAR. It's not our fault. But Miriam (Charles predecessor) just didn't understand the complexity of STAR - and that (complexity) wasn't communicated to Microsoft.
AW not testing before UAT
Customer definition of complete may be different from MS definition of complete
- Existence of changes in the applications after starting the SQL migration process
- FF project with limited risk reserve à in the WBS extra hours are added into the plan – it still is the first time we are delivering this
La réplica de Reglas de negocio en HDI para consulta requiere la funcionalidad liberada de la solución "(PPMC 84967) Explotación de Datos de la Factura Electrónica en su Fase 3".
LBG unable to schedule IT sessions
MCS Resources will need to offboard in the late September/October timeframe and reboard in January 2018
still open three SRs of RESCO mobile solution
– Windows To Go USB Stick not in scope
Delay in R1 -LLD for Analysis environment Sign off may impact R2 Timelines
Finalization of Mobile App UI ‘Look and Feel’
In the 1a design: 1.The Registration Service (RS) in the Cloud Gateway (CG) checks to see if the IMEI of the device attempting to send telemetry to it is one that is registered in Advance. 2. It gets this from a process where RAC notify the RS each time an IMEI has been added to Advance. 3. There is no process in Advance that 'removes' an IMEI from the system. 4. This means that a device that has been de-installed/de-commissioned will still be able to send messages through the CG. It's only once the message reaches the socket service that it will get 'dumped'.
Lack of a set of check lists for all areas that is visible to ensure all areas are ready for go live
Remediation and enablement activities, including migration of end users may not be completed by Feb end timeline.
Scope - There is delta between Microsoft's scope in SOW and CIBCs understanding of Microsoft's scope. This may cause scope gaps in the overall project and could potentially lead to missed milestones and ultimately project completion.
There are three bugs with severity 1. If the fix of these bugs are prioritized before the PBI for SID, there are a risk for delay of the UAT for Release 1 of SID.
​R2.2 DDR (phase 1) testing may not be completed in time to meet the planned Stage Deployment date.
​SDN Vehicle Decoder​ New Vehicle Decoder received on 09/26 that will need to be integrated into NG SDN and tested.
"Entrega de servidores de desarrollo definitivos y de produccion
"Pause" and "Cancel" features are fundamental for the customer operation and SCCM does not have this originally
(Closed) Adoption and Change Management is not staffed at BP
(Closed) Availability of stable CTP environment may affect schedule
(CLOSED) There are numerous Accelerate Dev tasks, Inactive Mailboxes, Skype VVC changes, Rooms and Shared Mailboxes, New Hire Feed. Those tasks are blocked by KP delivery right now
(Scope) There was a request for DR to be included in the Design. Network resiliency between Bisho and DR is unknown
[CDSA] {BOT] Accenture team support
[DIP[BOT][CDSA] HCF activities have slipped further
[DIP] DIP Budget at risk
[DIP] RBAC Rules not tested
[HCF] [DIP] Bring your own key for Blob Storage
>60% of GCR projects delivery activity is on customer site. Internet access connectivity control or performance issue on customer site. Sometime China great firewall impacted Azure access performance
• Complex project with multiple stakeholders, governance requires to be reinforced.
• Only 30K€ Invoiced have been received by thalys until now rather than 200K have been delivered. Risk to loose the budget if regularization don’t come quickly
1) The customer’s expectation for “rules” seem to greatly exceed our defined scope 2) Without a sufficient number of “rules” implemented, we cannot sunset the legacy system, CS Tracking, and continue down the path to “hard” launch at the end of Dev4/PfH 3) Additionally, the evaluation of some “rules” will require data in Titan that does not appear to be in-scope (SOW) or in the current design (FDD/TDD/SID)
1,400 rules to be specified, which exceeds internal Azure load balancer capacity.
1. APP CR for worklight development is under processing. 2. There're new stakeholders join this project in Feb 2017, these new ones want to make changes of scope. Still negotiating with customer.
1. Difficulties with implementation MAP toolkit
1. Decision from customer on Where environment will be hosted
1. Lack of SQL ownership (on both architectures and operational levels).
1.Subcontractor implementation and implementation effort: there are some components in the design document approved by the customer that were not clearly defined in the Subcon contract (Info Corp).
10-week timeline to CRMOL Go-Live is aggressive
1st Pilot dealer may not meet Performance KPIs
2 Departments at Daimler will have to restructure themselves
3 P1 Portal bugs are reopened 10/5 without Adoxio resources to fix, support
30% of LBE IT FT staff to be reduced by end of 2016. To reduce overhead. IT Director job also at risk.
3rd Party encryption software for In-Place upgrade
3rd party project dependency
3rd paties are not finished for integration to Modernization
6 ACM activites are requiring leadership in taking the completed draft plans into "make it real" execution for ADB
6 large out of scope items identified
600 office clients are less that Office 2013
88 request to add one more ESAE UAT ENV due to the LAB ENV is different with 88 current production ENV. Our Cybersecurity team assumed we need about 240 hours to cover the new UAT ENV, but 88 reject the CR, they want to deploy the UAT themselves, if having any technical they also want to get support from local team and cybersecurity team.
A key use-case or scenario at Scotiabank is that there are users which frequently move between branches which may drive end-user CSAT. 2 Key examples -1) Users who were migrated to O365 and them move to another branch which has not been migrated; 2) Users who have not been migrated to O365 but move to a branch which has been migrated. There are many variants to these examples
A long time approval of developed documents
A lot of our design team are on annual leave during the engagement.
A new SPO customer program management team has been announced and restructuring the SharePoint workstreams
A number of issues has been detected with PFW tool, including the problems with data imports : - CP report is not accurate - Inclusion of Rejected Time in the actuals - Lack of Tool's perfomance - Poec caculation is not aligned with ROC tools PFW and ROC Tools aligned, PFW should contain WP1+WP2 budget
A requirements document for the FDC private cloud environment (Dev/Test/Prod) has been created
A support case had been filed and escalated to a Support Escalation Engineer
ABB business requirements may oftentimes be difficult to meet with the existing Skype PSTN Calling Solution.
ABB may not be able to provision the required 3rd party CCE appliance in time
ABB not ready in producing documentation to go on with requirements gathering and fine tuning of Configurator Helper
ABB Operations may not have sufficient bandwidth to provision, remediate & operate the required infrastructure
ABB's velocity in setting up the required backend designs & processes may delay expected enablement velocity.
ABC AD environment has user-accounts that have multiple source mailboxes within ABC domain
Ability for ASG to resume project with required resources for required time % allocation
Ability of Development team/Cognizant/PepsiCo partner to transition design into development offshore
Ability to complete Fit/Gap review sessions in the next 3+ weeks.
Ability to deliver CIHS across multiple lines of business in light of changes to releases being required every three months due to new VA VIP process. If the multiple stakeholders’ needs are not properly coordinated and planned in a timely fashion, then the planned system may not provide the full capabilities for business and users’ needs.
Ability to turn in the first deliverable (Operational model) by 12-Nov as per WO
Ability to understand Astra's Financials and integrate the ideation based on facts (data points)
ABSA Board approval for migration
Absence of a Dev Lead experienced in BOT framework beyond Sprint 2 (Shireesha has quit Microsoft) might affect quality of deliverables in future sprints.
Absence of focus on speed and overall value may slow innovation possible with advanced public cloud features/services.
Accenture expects (due to agile approach) continuous changes till last week which is not in line as per Microsoft (Surestep) approach
Access management not available for go-live
Access policy needs to be defined, how will conditional access be implemented
Access to BUPA CRM is not issued in a timely fashion
Access to Client
Access to Development Environment
Access to necessary customer systems
Access to STORM SharePoint Externally with Azure. Currently this system is only accessible via internally. Need to grant access externally so that we can query the database documents related to a case.
Accessibility Testing not in scope of MS
Accor FOLS business case
According to the last estimation for the T&M component, there is a big risk of completion of the total amount of planned hours for this component. This could impact the total revenue for this year.
Account could go into non-compliance for delay in payment of invoice raised on 28-Apr.
Accuracy of Data Mapping The current data mapping is prepared on best effort by Microsoft and Biz IT. Update (27/4): Initial testing on daily synchronization from CSB is done in SIT environment. However, due to the nature of masked data, it is very difficult to verify the mapping correctness.
Achieve stakeholder buy-in for PoC initiative: Aligning PoC deliverables to business vision and secure buy-in from influential stakeholders can be a challenge
Achieving Minimum Viable Product within CEWA timeframes - Working agile with requirements developed JIT and iteratively, there is currently no schedule with a critical path to reliably demonstrate that MVP will be achieved by Dec 17 11/8 - Following a meeting with CEWA on 10/8, it is evident that MVP scope within the CP is not yet clear and delivery within the current CEWA timeframes not possible.
ACM is not in scope because of budget issues at DB Systel
ACM quality of identified gaps and actions to resolve them
ACM team did not have access to systems or O365
Active Directory synchronization in Azure
Activity of support for the definition and implementation of a SSO system by the customer: this activity depends on the customer's verification of the impact of a change in the SSO identification on the Systems in use.
Actual provisioning tool (Service desk) must be adjusted to support Office 365
Actualmente el equipo de proyecto tiene total dependencia de Marcos Moore para la incorporación de credenciales y gestión de accesos a los equipos con los cuales se está trabajando y se presentan retrasos en los avances al no estar Marcos presente o disponible para ingresar las credenciales.
AD and Tenant migration could impact in project go live or business impact depending on AD project plan
AD Identity IDM server upgrade may not be completed by the AD migration date
AD physical design not finished impacts the rest of projects
AD resource required for critical path items
AD Update: Dependency-Applications
Additional resource roles needed for Azure to support the need to "Move Faster"
Additional activities by new stakeholders that require a better understanding of the scope and work done in the project
Additional assistance for free to resolve WP ESAE completion
Additional efforts in remediation integrations with base line of Poliedro code.
additional fund
Additional merges have been asked before the delivery of the V1.
Additional requirement changes may not be approved by CPSM and/or other stakeholders, or have sufficient budget causing delays
Additional requirements need to be defined and addressed and aligned with other projects requesting services
Additional support from Sport Team to reinforce the positioning of our solution with the customer especially in the areas of digital marketing and video platform / OTT
Additional working session requested by CIBC not currently in scope of Envision and Planning work planned.
Additionnal Slippage of Fols Cloud v1.0 UAT
Additonal shifting of the planning that would require change request to maintain team.
Add-on compatibility – Telemetry not yet run, without may have higher level of compatibility issues Business has not been engaged; no work done on Office ProPlus compatibility
ADGM requested on 5 Sept. to replace the current portal’s yellow UI with the previous fuchsia and black one (the changes will impact the colors and some design items).
Adjustments that require additional work by using mockups of services during the first sprints
ADMS - Consolidation of the five orgs in One org
ADMS schedule reflects an extended timeline of approximately 3 months, due tothe addition of two pilots and the associated LOB application remediation activities
Adoxio team resources - changes, not dedicated full-time
Advise from finance requested, no other mitigation than to include 5% cost uplift which is done in Compass directly.
AECOM Migration Readiness in terms of Migration Schedule readiness, helpdesk readiness , Admin Readiness and Post-Migration Process "War Room" to handle Migrations incident management
Aflac QA process misaligned with Aflac IT deployment process
After a strong review (still ongoing) of code, configurations and infrastructure (made with the product group) there are some actions which will be taken and which consist in risks for the project (because they will be implemented directly in the Production Environment)
After an analysis of our findings following the workshops with the business teams, we have discovered some gaps and limitations in EMAAR infrastructure that may limit the business value as an outcome of phase-1.
After analysis, determined scope in refactoring backlog is much more than anticipated, therefore, the total effort in backlog may exceed current refactoring project budget.
Aggressive implementation timeline
Aggressive implementation timelines and MS reputation at stake
Aggressive Schedule
Aggressive Time with high amount of client dependency
Aggressive Timeline
Aggressive timelines
Agile impact on overall project outcomes • Requirements provided in iterations and not detailed in advance may result in rework impacting the extent of functionality delivered within the fixed timeframe
Agreeing Phase 1 SOW may take more time than february
Agreement for Syncing/processing/strorage of data in the cloud is in place by Fiducia&GAD?
AH is unable to provide the 7.10 version of FOLS on-prem in June.
AH wants to open the first pilot on the 21st of November but no PVs
AIG Datacenter Staff Participation in HCF Project Workshops: AIG is not providing the requisite staff to participate in HCF Workshops. The Solution Alignment Report (Deliverable #1) can not be completed unless AIG provides design decisions.
AIP Client Deployment
AIP may be Under-resourced
AirWatch license issue if project is delayed
Aligning expectations of ZIC executive sponsor, O365 program manager, and ODfB project manager
Alignment of Dev & Support Release Schedules
Alignment of Microsoft Resources to customer expectations, thoughts and culture
Alignment of UPN, SMTP and SIP addresses
Alinear Kickoff con el Dominio, ya que 10 diaz despues de la aceptación del proyecto no está alineado a los procesos internos de MCS.
All key resources to attend the workshops as per schedule
All LaPoste resources are involved in the crisis. LaPoste vision is that we focus also on task force instead of focussing on SCORE V1.1
all licenses won't be available until Feb 2018, and FTC only migrates the amount they say the see in the tenant which is 6600 licenses there fore 3'3TB, when Repsol needs to migrate 10'6TB.
All Shared Mailboxes should be licensed.
All team members are travelling to conference between 17-21st July
All technical tasks needs to obtain a change approval, before being implemented
Allegion may insist on customizations because 'they've always done it that way', even when there is not a business competitive advantage to the customization. This may be shown by insisting that the new AX system work exactly like the old Oracle system.
Allegro Deployment plan sign off
ALNG Operations team needs training to support the new platform when in production
Although MS Team is performing per T&M contract, the business relationship/partnership may be impacted if Ford fails on their agile journey and ability to support VSDN solution.
Although the project started on 02-May-2017 the milestones in SOW only reflect dates assuming project contract would be signed on 03-April. There is expectation from customer to complete the project based on old schedule
Ambiguity upon the Sponsor and the expectations
Amendments need to be made to Milestones to ensure timely payment
An Active Directory topology diagram, Network diagrams. A list of known issues with the current AD DS and Exchange environments (if applicable) will be available by End of envision phase
An IDG project manager is not included in the standard ENMO package
An impact on the deadlines of the contracted milestones by december 31st due to the dependency of the completion of these tasks on work sessions with the client
An impact on the work being done on the infrastructure area because the Azure environments are not ready due to the fact that, at process level, it is not possible to activate the amount through a corporate card.
An update to Dynamics 365 is planned on the CRM instance on April 29th, 2017
Anomalies between BMO production-QA-Dev are potentially causing new issues BMO production environment has differences with QA & Dev. The solution tested successfully in QA environment and stabilized with UAT signoff. However, some of the scenarios are not working in production environment and causing new issues.
ANSA to review and signoff Infotech Submitted deliverables within 3d of submission Infotech to review and signoff Microsoft submitted deliverables within 5d of submission. Additionally, deliverables need to be approved by 6th May to avoid a late start of the Development Phase
Any new requirements or new features which arise during UAT phase are not defects but enhancements that the user may have realized the need for when testing.
Any parallel development in production branch may cause delay in schedule or additional effort to merge code.
Any requests to increase the network bandwidth will impact TRTA migration timelines
AP Pay Refund Design taking longer than expected
APAC Migrations - If mailbox replication is not optimized to complete data replication prior to migration, can lead to migration delay or cancellation
API Logging
App integration complexity
App integration strategy
Application install media and install instructions not available.
Application mitigation may take longer than planned
Application owners scheduled for creating UAT plan and executing UAT testing As the migration schedules are defined, the application owners need to be commnicated with to create their test plan and scheduled to conduct UAT This will cause a delay in the migration schedule
Application Packaging stream may not take off
Application Planning and Assessment Resources
Application Rationalization & Source Files
Application Rationalization is not complete.
Application Remediation
Applications shared by ESB for deployment into Win 10 env, if are not compatible then those cannot be included for processing on the current engagement
Approach to cloud and operations is immature as per our technical team
Approval for enabling ODB licences during YEC is not signed till Jan 9th
Approval of design phase deliverables requiring significant time impacting closing design and start of development for impacted FDD deliverables.
Approval of Purchase committee for required Contract amendment needed to cover any new Change Request
Apps build and release
AppZero scenario not applicable
April release FDD dates are not available.
APS 2016 upgrade is scheduled for 7/25
APS to be abandonned
Architect Availability Leading To Sub Quality Delivery
Architect has hours but is not formally/periodically assigned to the project.
Architect moving from Offshore to Onshore
Architect was assigned only 40 hours in the deal, but needed 80 hours. The assignment has been done and the hours have been utilised.
Arrangement on the new Customer PjM
As a result of Active Directory consolidation activities, there will be organisational changes to the Operations and/or teams.
As a result of Bottomline completing their tasks late, some aspects of the solution may not be sufficiently tested and \ or time to remediate issues will be limited.
As a result of delayed documentation for the FDD and customer signature, Build Phase start date will be impacted and may cause a schedule and financial impact to the project
As a result of the wide range of individual desktop configurations/user changes, SCCM testing may not be representative of live desktop deployment
As of 4/14 there is $214,161 left in the TM budget and $244,289 left in the BIF budget. We are burning ~50k in TM and ~11k per week in BIF. We only have ~27k left in the expense budget
As part of the initial planning activities, Microsoft and AT have identified some key gaps in the Microsoft SOW for this project. These include the application migration scope, Azure configuration and new support model implementation. There’s a risk AT will not have the capability to address the gaps in scope resulting in delivery issues and project delays
As per COMPASSONE (https://compassone.cloudapp.net/Deal/30048/Customer/33542) the costs on the project should be a maximum of 256K (+ 27K of Risk Reserve). Actually, we're expecting a total of 272K (259K consulting costs + 13K expenses) which means we're going over-budget
As per initial discussion with client, they need to have additional documentation, apart from what's mentiond in SoW, for their internal compliance. Further meeting with client is planned to understand & customized required documentation
As per the product group, Site to SIte ASR public release has been pushed back again. The new target date is early Q2 2017 but exact date has not been determined. There is a high probablity that this engagement would need to be extended to align with these dates. Budget allocated for this work stream remains unused.
As removing Hypercare period from the amendment is under discussion, support process must be defined for the period after MS team disengages.
As Simulation Testing isn't normally done as part of Sure Step Evolved methodology, there is no template to follow in terms of scripting the execution of this phase.
As the budget cycle for GPG ends on 31st of March, the invoices must be sent before the end of February which is not possible.
As the project deals with Azure PaaS, we need to have dev skills also in the project. If we don’t have an OC with dev skills, it will hamper our monitoring capability.
ASE API
ASG does not have a well stablished IT department. There are very few people available with limited technical knowledge. Agency has a strong dependency on vendors to provide IT support. Potentially AX and portal ownership concerns long term.
As-Is and To-Be Impacted Processess
AS-IS business process unavailability triggers gap being identified in UAT
Asking questions or for information not detailed in the SOW.
Assessment part of VF miniproject process
Assessment Phase not paid
Astra has indicated that they will not be able to share credit scores with MS
Astra ID generation has the following gaps that needs to be addressed: 1. Astra is not going to map Astra ID to all transactions. Transactions will continue to have existing Customer ID. Microsoft will have assign Astra ID to each transaction based on a mapping table provided by Astra 2. There is possibility that the same customer id can be duplicated in different business units for different customers. This could potentially introduce referential integrity problems
AT and its partners (e.g. Fujitsu) are currently running a large number of initiatives which is overloading the BAU teams (BT and Business) with project related activities. There’s a risk that clashes between this project, BAU activities and other projects will impact AT capacity to deliver to the proposed timeline, resulting in project delays and increase in overhead costs
AT Design approvals delays
AT DRB may not approve the design on Monday 4th December.
AT Pgm Mgr signalled that start of IDM P3 Stage 2 development may be delayed
AT TEST environment may not be ready by due date
At the current rate of burn, it is highly unlikely this engagement hours will get consumed before Sept, in time for annual renewal.
ATO for PPMS Application may not meet July Rollout
ATO must be in place by 10/1/17 in order for migrations to begin in the remediate phase otherwise the schedule for completion by 5/31 cannot be achieved.
August local summer vacations, potentially could move Release 1A Go-Live date, if not achieved in July
August month critical for vacations; Mediolanum plan is to start integration test on August 16th
Autodiscover recommendation implementation will be performed after end of MSC engagement.
Availability of ANSA SME to complete aggressive Analysis phase schedule
Availability of CJF team to collaborate in the project due to production incidents
Availability of Claro's team during the month of December for the pilot testing, change management and training activities
Availability of EPS management for defining SCSM processes (Incident, Problem and Change management) is very limited.
Availability of Express Route may take longer than expected (6-8 weeks)
Availability of GM Resources
Availability of High Quality Data from Astra.
Availability of ISV resources - setup of PoC
Availability of key resources on AXA Side impact review/acceptance schedule
Availability of key Starbucks resources - Starbucks ownership
Availability of Metalogix tool for migration
Availability of MS SA
Availability of native PSTN Calling capabilities in important countries (Switzerland, Sweden, ....) may be delayed and impact the enablement planning.
Availability of Samuel from 24-Apr to 5-May
Availability of technical team during workshops in India
Availability of the Dynamics 365 Product for setup, use by MCS resources
Availability of Users for Testing
Availability to schedule mettings on the client's end
Awaiting a Part time consultant from IGD
AX Retail functionality not meeting BESTSELLER Requirements, there is a risk that BESTSELLER may exclude AX retail from the scope.
Azure account is not activated yet which will impact our development plan
Azure AD Connect AIP Licencing cost
Azure Cost Management
Azure enrolment for customer in Singapore is required.
Azure Licenses
Azure readiness
Azure subscription
Azure VPN Connection from EU to Americas
BA not available in the project from KPMG until May 1, no BA built into the deal for MSFT
BA’s finding errors in data migration transformation which may take longer to correct
BAB Team Availability
Back to Back signing of CRs with Partner
Backend Reports from DyP Team - Service Unavailable
Backlog of hours
Bad pricing model for ASA on Edge
Baja productividad en los desarrolladores por las restricciones en los ambientes de desarrollo
Bandwidth not being sufficient at the sites.
Bandwidth Requirement/Express route: Customer is preferrign to go with VPN route whereas our recomendation is to use express route
Bangalore "one off" request extended
Bank considering not testing Audio traffic with EF QoS tagging
Banking entity velocity migration start date (planned in Feb 18) at Risk due to prerequisit not available
Barclays key project resources have been reduced per early August: Matt Lyddon-Jones is off the project as of July 31, Bob Cunningham is off per August 7.
Barclays Preproduction environment not ready for the new Barclays planned dates and Barclays do not have the skillset to achieve the build activities in time
Barclays Preproduction is out of date and will require significant effort and budget to upgrade
Barclays team does not have enough resources & focus to meet the planned dependencies on their side.
Based on architecture decisions Entergy went with the Delly tool for sync rather than MIM. This puts a work effort on already overloaded resources.
Based on ThermoFisher current migration rate (576 per week aprox), it won´t be possible to complete the 65K+4K on the re-planned date of 10/31. Customer forecast is to end migration by February, 2017 but budget will last only till November-December, 2017. Situation has been escalated to project sponsor.
BAU Azure support for production environment
Baxter is acquiring another company and will be want these emails to be part of the migration . Baxter indicates that they will handle the migrations. This will be less than 1000 accounts. This needs to be done by Sept 2017
BBL is in process of submitting Memo to get approval on purchasing Network equipment, Additional Sitecore non-production License, and Azure Subscription
BBL is responsible to develop some financial calculators, Forms, and Back End service to replicate form data from Azure to On Premise DB. It might not be able to finish within SIT phase
BCI tiene una aplicación desarrollada que depende de la presencia del Lync 2010 y se está validando la compatibilidad entre Lync 2010 y AD 2016 previo a la ejecución de acciones sobre el AD.
BDO's Denial of work done by MAS
Because of scope management process a Sprint can be modified by a critical requirement from customer
Because of the requirement to engage a significant number of 3rd parties there is a threat that the upgrade to supported platforms may take longer than the proposed project duration.
Because of the tight timelines as a result of the Need 4 Speed, it will not be possible to apply the train the trainer approach to the project. The project implementation team will perform the training instead. Because of this, it will happen that the project training resource does not speak the local language of the people being trained. If the local people do not speak sufficient English and there are no people available to provide an on the fly translation, then the training will not be successful.
Because the actual number of sites (680) is much lower than the contracted number (1253) Barclays claims that the contract budget can be negotiated down.
Because the solution requested in the TDR has not been evaluated with the needs of the new business model of CPE through OSE, it could present incomplete or incorrect requirements of the solution delivered, whose impact would be the infeasibility of putting the solution into production
Because the TDR does not specify some response times, SUNAT could present dissatisfaction with the expected times, whose impact would be customer dissatisfaction
Because v1.3 deployment was delayed due to post-production issues, we have a one week delay and will commence QA activities on Sept 18
Below risks due to SIT being run in Parallel instead of running in sequence as earlier planned: Redundant defects can cause addition effort or impact timelines. Integration testing on unstable code might give inaccurate results. Additional regression due to SIT related defects. Delay in test execution due to multiple Build deployments.
BENZ disabled TLS1.0 for all servers. But SharePoint workflow engine must based on TLS1.0 to work properly and our product team can not update it in a short time. So we need create a new customized workflow engine to replace it.
BES12 initiative timelines may have project interdependencies affecting timeline and offline print capabilities
BESELLER implementation approach is changing to be multiple streams, finance, logistics, retail etc. and time lines extended.
BESTSELLER resourcing for BUYING/PRODUCTDEV streams strained
BHP is having difficulty (contractual and technical) dealing with OBS to setup the ExpressRoute. The target date has been moved several times and there is no revised timeline - it's a day-by-day delay.
BHP project team is under scrutiny with project management approach
BI Team velocity below planned
BIF Extension to H2
BIF funding dealys
BIF is about to expire on June.
BIF of $177,103 may not be consumed by 31-Dec-17
Big gap between Project scope and Project estimation
Binaries and installations guides cant be provided by business system owner at a large scale.
Binaries are required in order for the factory to run the assessments in the cloud.
Binding generation between Xamarin and SDK - We use a CECA Bank SDK for payments with NFC technology - The SDK is built in native coding for Android (Java language) - The SDK has two versions: debug (for developing) and release (production) - We have been working with the development SDK and having the problems mentioned above (slow integration pace) - Last week we did a test in production and we found the we can’t generate the connect with the production SDK because is encrypted for security reasons
BMO business is planning to introduce a few functional changes including CASL tags
BNC does not want to provide full access requested to MSfC team.
Brett Coddington will be moving off project
Budget is almost consumed due to project delays. Contract amendment is required to continue support customer with MCS
Budget Overrun in engagement
Budget overrun was reduced from 205k to 113k, due to resource usage optimization and CR budget added. Remaining overrun needs to be covered, with additional optimization, or the risk reserve and / or margin will be affected.
Budget revisions drove a reduction in consultant hours
Build Kick off -in flux-
Build, Development & Test completed in PROD environment
Building information and asseet operation hours are required by ICONICS to configure fault rules.
Burn rate extremely low from May 16th to May 27th. Ability to complete all deliverables on time need to be re-assessed.
Business and Mission Critical Solution This risk now
Business benefits are not recognised by the Rexel Business community
Business can not to accept the solution, as the IT accepted only a subset of the CR detected without sharing it with Business user and setting up their expectations accordingly
Business Confidence In Cloud Enablement Team
Business Env - Failure: Internet banking failure could be impactful in terms of revenues.
Business Impact
Business Interrupts due to UPN/SMTP Switch during YEC
Business milestone
Business Rules for Sumarizado Nomina 1.2 are more than expected.
BYOK tenant is expected but not yet licensed. Hardware already ordered but needs to be sorted out with Microsoft.
Bypassing the proxy servers
C# dev consultant from MA domain cannot be onsite before March 18th . 2 subcon can only work remotely
CAE’s AD main user identity domain NetBIOS name contains a dot. A formal non-supportability statement was obtained from CSS specifically around AAD Connect. The MCS team is currently assessing all options in order not to interrupt the ongoing remediation phase. 2 options consisting of AD redesign, and 1 recommendation will be presented to CAE on Nov-15
Caer en retraso en cronograma debido a que no se cuenta con las dependencias superadas
Call center and services stores indifferent countries connect to OL side with bad latency and bandwidth, especially in India, South Africa, Mexico.
Capgemini has not assigned a Technical Architect full time on the Project. D&G has many different Store Configurations (different version of the OS, Hardware; Peripherals) which require Cap to design different store Topologies.
CASL Application Servers Competing for Virtualization Environment Resource Allocation; 10,000+ VMs in Production – Perf Environment Running near 80% Utilization
CB testers new to project and will have limited training and process knowledge. Postponed workshops and bringing forward go live date reduces testing window.
CBL UAT will be conducted on TEST environment (it wont be specifically tested during tests on UAT) wich may result in lack of stability after deployment on PROD
CC Engineering have stated that the expectations placed upon them from Spectirs are more than they undertake for their other customers, hence setting up a Help Desk and operational management team will be challenging
CDS Product Issue
Certain Business Systems may need to be migrated to the production subscription
CEWA Program Budget
CFO and FC have limited time availability to attend solution playback sessions.
CGI has declared a work stoppage of 4 weeks (Apr 24 – May 19), is needed to allow CGI to produce and approve internal documentation and to secure hardware to right size their target deployment environment.
Change control may not be approved during Olympics
Change Freeze dates
Change Impact Assessment (CIA) not completed per plan
Change in Customer Organizational Structure
Change in the Local TEAM (ADE and Services axecutive). Actually Chile's DMM is acting like ADE and Chile's Service Lead is supporting the service executive rol. The engagement doesn’t have EM/ADE and SE, PjM is supporting this activities, with the risk of the loose the realtionship with the customer, new opportunities and quality of the delivery.
Change of political structure at COJ from ANC government to DA has brought about changes to stakeholders who were aligned to this project's success
Change of Subcon
Change Request
Change requested by customer infrastructure team is against best practices
Change requests continue to come in from the business.
Change Requests have not been accepted by the customer
Change the resource assigned on 01/02/2017 in two weeks
Change, Release and Configuration Management
Changes made in the last month on the version of Financiador Project.
Changes or new definitions not included in the design by the organizational and process restructuring project carried out during the TFS implementation phase
Changing detailed requirements and delays in lock down decisions until sprint 4 impacted/delayed development work (backlog). This may lead to possible delay in development work
Changing in sponsor. Next activities must be coordinated with new area in Claro
Chester Coronel will not be available on Oct. 25, 2017 to deliver the basic training in Pakistan. He is being retained onsite to provide continuouse support to the VIP for possible mail migration issues
China contract (21Vianet) not yet signed
Chistmas and New Year holidays of Customer staff not incorporated in the project plan. Holidays might impact the project timeline
Circuit upgrade from 2 GB to 10 GB
CKHH requested to rebuild the SharePoint hybrid search in UAT environment after the readiness of the servers in HIT
Clarity of Scope and Approach
Clarity on scope of EDA - MS Architect has proposed that in the scope of current project, we would include DA Jumpstart offering
Clarity on the number of personas and level of details for each personas.
Claro customer has limited experience with the Agile methodology of development and may not be aligned with this delivery approach.
Clean Refresh of Master Environment is incomplete The project has not successfully executed a clean cutover simulating go live and there are no additional scheduled tasks to attempt again. Without a successful test of this cutover, there is a risk that the Master environment may not be in sync with all of the Norbord-required configurations and customizations and may affect how the cutover to Production environment is conducted for Go Live.
Client expectation of SAA scope of service is different from SOW signed
Client go-live readiness
Client has done no change management activities with target group of users for post deployment rollout
Client has introduced a dependecny on the completion of a DomainController configuration in DSC so that this can be used to rollout new 2012 DomainControllers in the QH Domain
Client is asking new CR
Client is slow moving and very process driven and may not be able to keep up with the speeds of the project
Client is unable to provide ALFRESCO development server, for completing the 2 interfaces
Client may be resistive to Cloud technologies and disruption to standard patterns
Client not focused on detail and seems to change his mind every time we meet him. Extremely hard to pin down and struggling to agree on requirements for MVP
Client Security Policy doesn’t allow direct traffic to the Internet from Tier0.
Close the project without consuming the backlog
CLOSED - Assessment conversations may lead to design conversations, which is out of scope for this engagement.
Closed - Customer Environment and History
Closed - Fee arrangement
CLOSED - O365 IP Lockdown by KP to not access outside of KP network
closed - Resourcing gap in upcoming 2 weeks (GD)
CLOSED - The out of band internet connection is not yet available in the data center. We are waiting on the customer to configure the hardware (IBM contracting) and configure the firewalls.
CLOSED - UPN completion by customer
CLOSED: EU Training units were depleted and customer needed to renew or all end user training would turn off.
Closing the project before finishing the integration between Clarity and 123 if it is decided it should be done
Closure date may be pushed to January
Closure deadline set unrealistically by customer's management
Cloud hosting has not yet decided to allow the project to use Service Fabrics
Cloud PBX project has not started yet and the project depends on some functionalities that will be implemented from this project.
CMS (End customer) needs to develop Business plan for Azure.
COCS (Propriétary Microsoft Tool) seems not to correspond entirely to the ACCOR-FOLS specfifcities.
COE could be delayed due to 3er parties delay in delivering code
Cognitive Services and Chatbot technology is not GA.
CoJ Intranet testing users not available for UAT 8 hours a day. UAT reduced to 4 hours owing to COJ resource constraints.
Collaboration challenges are still affecting the performances of the project and impacting the frustration level of both teams even after the partnership review meeting
COM: The analisys the Data of the traces could change the previous estimation informed to the customer April 11th: Customer says the is possible that the project will be cancelled. Impact in the remaining hours in the project.
Commencement of UI Dev stream.
Communication from Customer to Partners is poor
Communication risks due to constant changes in stakeholders
Communication strategy validated by the Project Committee is to only communicate on Online Services and web application usage. In reality, subsidiaries are showing the willingness to have rich client experience by keeping their current office versions.
Communication Structure
Community Care Network (CCN) Providers contract award is scheduled for Nov 1st, and key dependencies leverage that date. No sample data is available till CCN's are onboard.
Compatibility of Applications with proposed Directory Services
Compensar's project manager expressed his concerned on 1/Sept 9:40 pm in a email, about the work that will not fit within the remaining hours contracted. He asks for help to find a way for Microsoft to finish the work. He escalated his request to EPG.
Competing with parrallel projects
Competition Risk
Complete data not available for FDD technique 1.
Completeness of requirements
Completing Remediation Items ID03 and ID14 for ASR from the Remediation Checklist. ID03: Ensure that all AD attribute mappings have been identified for AD synchronization, ObjectGUID disassociation, AltID attribute population, Exchange as well as ASR ID03 Ensure that all AD attribute mappings have been identified for AD synchronization, ObjectGUID disassociation, AltID attribute population, Exchange as well as ASR ID14 Submit Change Requests to the Office 365 Dedicated to establish trust and MMSSPP integration with the Greenfield AD for ASR"
Completion date is unsure.
Completion of bugs/defects by end of Testing Period, 8/19/16
Completion of Customer Testing for R10 may not meet the planned Aug. 18th deadline.
Completion of UAT on time due to two round from client. one internal testing and then actual UAT
Complex Feature LiveTicker cannot be stabilized and tested by B04 till 3rd of March
Complex integration of evolutives in Poliedro, that will be in execution in parallel way.
Complex or in-process procedures from other areas in the deployment to production generating delays, defaults or delays in response times
Complexity & Feasibility to develop the intended Solution as-is in time for the POS POC Demo: 9/29
Complexity customer environment
Complexity of Cecabank integration - Integration with Cecabank backend is the main technical risk and it's in the critical path of the app development.
Complicated Project Financials because of Amendment 1 Sign-Off Date
Compromised deadlines due to dependencies
Concurns related to the suggested resource loading and possible impact to the budget: • Amit will need to log hours on the T+M deal very soon, and we still need to discuss this with Manoj. He knows this but has not commented it yet • Chris will not be available for the project starting August if he does not get addition hours. This is a huge risk for the project as Chris is the solid support we have on all the escalations we have had so far. • The admin work and the reset changes due to Rahmani´s long leave plans leaved us with a gap Amit A. will likely fill. Again this impact the need for additional tester resource to assist Amit while he takes on the addition admin task • The workload on the developer resources are very high, and they cannot continue to work like this for much longer. Additional resources will be needed if the team are expected to keep up the same pace of work • It seems HPI is planning to extend the MS engagement until 1st to 2nd week of September, but even t
Conditional Access feature in private preview only allows for "best effort" support
Conditional Access in Private Preview could generate additional changes
Confidential
Configuration Manager in customer environment in non-recommended way
Configuration of NAC in certain areas of the Sky network prevent deployment using SCCM in these locations
Configurations of the RDS hosts
Confirmation of the Architecture Document
CONFIRMATION PROCESS Tied Baseline
Conflict of priority because same resources are required for HeiCloud workshops
Connecting Dynamics 365 to pop3/smtp server using Server side synchronization. This is a blocker for the upgrade and needs TAM's & CBRE attention
Connectivity between Ibercaja environment and CECA environment
Connectivity issues: we are experiencing several connectivity problems (that mut be handled by Inditex).
Connectivity loss due to CPF environment
Consider the definition of scope, approach and project methodology.
Consider whether the customer expectations are clearly defined and understood.
Considerable increase in the complexity and quantity of work for the implementation of framework change (Technological Renewal)
Constructive Deliverables Feedback
Consultant language limitation to increase the learning curve
Consultant skills mismatch
Consulting expectations
Consumption of all project hours by end of August 2017.
Contacted hours - increase
Continous extension of Project end date and no visibility of project status
Continually getting changes to processes. No complete alignment from Dell Business side on some FDDs
Continuation phase planning and project scope definition
Contract amendment must be extended beyond June 30 2017 for Microsoft to continue work
Contract states the majority of work will be onsite. Assumption is Veripark will do all development offsite
Contract Termination due to Performance Issues.
Contract to be cancelled if Microsoft doesn't implement the KPI's requested by Vale
Contrat considered by the client as fixed fee.
Coordination of each project workstream
Corda Does not support 443 connections
Corporate policy for RMB data to be stored on personal devices
Correct identification of involved servers that will be migrated in technological migration process.
Costs and effort may change depending on the additional volume uncovered.
CP account creation for resource is pending
CR delays
CR04/Daily operation will continue under working mandat to estimate all sizing in one Active Directory Domain
Creating a Komatsu Global plan
Creation of package manager by IT department is being delayed
Credentials for FTC pending + Migration strategy & plan still not yet established in terms of start and end dates and user list for each batch for velocity phase
Critical changes requiered for improve quality of the solution found by QA team
Critical requirements are surfaced up at late stage of the project life-cycle, for example, • SMM printouts (resolved) • One package has multiple billing methods • Flexi-entitlement in early bird packages (Pearl) • MLD OPD (Output Deal) allows bill by delivery • Advanced Approval Rules (SK) • Data accessibility / security / sensitivities Subject to business criticality, late requirements or business scenarios that are recently raised to or known by Microsoft during UAT may not be able to transact in NGCSB Step 1.1
CRM Attachement in Azure : New product to admin and support in SCORE architecture
CRM Licenses
CRM licenses not configured in the AT&T Azure environment.
CRM SDK (6.0.0.515) used on DP is not supported by current CRM version (8.1.0.538)
CRs awaiting approval
CSAT Impact as a result of e-service applications design change
CTS – CICD pipeline development schedule is at risk due to resource constraints.
CTX: Citrix UAT (CEC-RI-004)
Current cost forecast shows a delta of 19% against the baseline
Current pilot will assume that all users who are using Win 10 are only using Win 10
Current PjM (Scott) is transitioning off the project as client PjM. Due to known AT resourcing there could be delays in assigning a client PJM which could negatively impact project progress.
Current resources will be unavailable during the months of July and August.
Current security policies at SAT does not permit to enable communications flows from FQDNs.
Current security software (NetBackup, Deep Security & Entrust Client) will be a high risk on this project – information received was the software has not been certified on Windows Server 2016.
Current system stability issues can jeopardize the project timeline
Current version of EMS may not provide all the capabilities required to conform to TD MDM and MAM requirements
Currently – SCCM information on 3 day delay as sent to data warehouse. While a report is available to show successfully deployments day after, this is by individual deployment, manually run, and not easily manageable for velocity deployments. This would indicate a high level of data inaccuracy.
Currently changes in Port-out services could affect the recommendation analysis of architecture and activities remediation/services migration.
Currently not clear how processes in operations will look like
Currently not clear which are functional criteria for monitoring of services
Currently seeing incomplete data in SCCM about users machines, combined with published RAM schedule that does not appear to align with Bulk Schedule for initial deployments; velocity numbers may not be at level needed to start.
Currently some subsidiaries are not fully integrated to SPIE Group infrastructure (Exchange, Active Directory..)
Currently there is no overall support model and SLA defined for all these topics Only ES DevOps services provided SLA for Incident/Defect, Change and new services provided 5*8 support Refer to ES DevOps Operation Guide Page 6 Service Catalogue, some service request need escalate or forward to MSIT or partner support which has no specific SLA Service Request like request for information or request for document, troubleshooting
Currently we don't have full details on the entire activities that need to be completed this year. Only one SOW has been developed and other in progress. We still need to have customer commitment for the program and all details around it. So we need to formalize and get customer onboard on complete strategy and all tracks that need to be completed on each year.
Currenty not clear how will take over operations of the solution
Currenty not clear who will take over operations of the solution
Custom code in pipeline
Custom images from customer will not be available in time for completion of SOW.
Custom requires a product in production with real data for September 18th, so that funding for Community Care Program continues
Custom solution risks timelines
Customer not Signing Sprint 2-6
Customer approach to milestones & remediation is delaying the project
Customer approach with Microsoft is always negative and complaining. This seems to be a standard behavior with external vendors.
Customer asked to anticipate MMT implementation
Customer cancelled project in current format
Customer changes mind on delivery
Customer Configuration Manager environment is outdated. It neither 1) supports the deployment op tempo that will be required to fulfill the requirements of the contract nor 2) will it be supported by Microsoft.
Customer continues to have limited support for VSO and no steadily available MS VSO resource for assistance.
Customer continues to identify out of scope changes as issues and now that UAT has been conducted it is expected that alot of the issues identified will be changes.
Customer controlling access to BU project teams and project stakeholders. May impact project task assignments. Monitoring closely.
Customer dependencies delay
Customer dependencies may not be provided in time for project completion
Customer Detail Requirements confirm
Customer didn't provided any specific requirements in terms of warranty and penalties. However, customer might still ask for such terms during the negotiation phase as those type of terms are quite common in Russia
Customer does not agree to fund additional days to deliver the numerous change requests
Customer does not fully understand what is requried for them to do in a WS, what are preparations that Need to be done, what will be discussed, and what are follow.up activities that Need to be done.
Customer does not have any experience in some of the fronts
Customer doesn't have the mailbox on prem
Customer don't want the user to have 2 jumps, to onprem and then to O365
Customer EPS hasn't paid 2 invoices without valid reason.
Customer expectation is so high that we might not define our scope of works.
Customer expectations
Customer expectations for solution may exceed what is possible in the available time frame
Customer expectations of having CRMOL could not be met
Customer expectations that applications will be packaged for App-V in the “Assess” phase of the engagement
Customer focus & delays on inputs for Assessent Phase
Customer generated User Stories and requirements may not be complete or accurate.
Customer has concerns around the operational process for user support during and post deployment.
Customer has decided to deploy Ad FS rather than SiteMinder for identity federation
Customer has expressed unhappiness towards closure of deliverables and if MCS does not close on the XOM deliverables in the remaining budget, there would be CSAT issues
Customer has limited experience and knowledge of Dynamics365, particularly from an administrative standpoint, also from a developer standpoint
Customer has no budget for CR006
Customer has not any requirements.
Customer has not indicated a date by when they will decide on a 'go forward' approach and sign the contract.
Customer has not received yet important definition information from final user for Comercio Exterior Services.
Customer has not the project owner, so the project acceptance process didn't be confirm with them till now.
Customer has poor processes and workflows
Customer has raised a concern on the delayed deliverables and has suggested extreme steps in case the go-public event on 15-Nov is impacted.
Customer has raised lots of CRs during pilot UAT wave, more CRs may raised during pilot wave
Customer has released new project roadmap, which introduces changes on scope and timelines.
Customer has resisted having an Exec Steering Comm with the MSFT Team
Customer has restared UAT only on March 1st after 2 months of stop
Customer has stated Intune support will not be needed from MCS
Customer has thousands of applications (Enterprise and Clinical) most of which are old versions likely not supported on Windows 10. They have stated that applications owners need to be consulted for any version change.
Customer has to clarify definitions that are not as the partener expected.
Customer insatisfaction because they have identified diferences in the way they operate that require configuration changes, which represent Change Controls to us
Customer insist on animation dashboard to be delivered with VD project together. Background: in February when discussing requirement with the customer , the delivery team found that SOS is vague and ZPMC insist on animation dashboard to be included in VD delivery scope and after several times of discussion the customer agreed that animation dashboard can be covered in another contact leading by MA domain. MA domain followed this case but in June the customer expressed their dissatisfaction with MA's delivery. this task return to DI and DI/AAD promissed to deliver it with the customer together. animation dashboard is very complex and it's the critical precondition for VD project acceptance
Customer is about to hire new project manager for engagement
Customer is analyzing the possibility to add 2 new functionalities to the Office Banking site at the same time of the pass to production of this project.
Customer is asking for on-site personnel to conduct the operations workshops instead of the originally planned remote execution
Customer is falling behind on milestones
Customer is going through a deep internal re-organization. CIO has left the company. We have been reassured by the Innovation Unit Manager nothing will change on the project.
Customer is insisting that Backup and Restore should be included in project scope without increasing project costs
Customer is insisting that DR should be included in project scope without increasing project costs
Customer is insisting that Monitoring should be included in project scope without increasing project costs
Customer is insisting that Workstations and Enterprise WAN should be included in project scope without increasing project costs
Customer is looking at changing the way the Users are provisioned. Instead of files from SuccessFactory, they looking to provision through MIM
Customer is not able to complete all their tasks at the end of the project
Customer is not aggressive in the approach, leading to delay in overall progress of the project.
Customer is not clear about how much their Azure cost will increase with the introduction of this product
Customer is not happy that Warranty is nearly finished and may refuse to pay final milestone if we do not continue work at their request
Customer is not migrating Groups
Customer is not prepared for the pilot, release and support of LEAP v1.x. The application is large and complex. The Customer has a minimal staff and only involved at the Business level and except staffing by a third party (SPR) for the DEVOPS area. GTIL has not defined their support plan and methodology entry is behind.
Customer is not willing to start phase 1 before end January 2018
Customer is planning to migrate only Dev environment with Microsoft, this will lead to erosion in migration scope for total the number of servers in scope.
Customer is pursuing an alternate design approach where the development will be handled by their in-house team and MS involvement may not be required. Project to be converted to a 'staff augmentation' mode
Customer is pushing on deadlines matches, asking to close the Project within the end of the calendar year
Customer is requesting few CR's to be implemented for the system to Go live
Customer is requesting for this demo to ONE Management to impress on the success of the Project
Customer is requiring GO Live date for December, 31st 2017 to start the new fiscal year in D365.
Customer is scheduling most of the discovery calls. Current schedule velocity is very low.
Customer is so demanding and expectations are very high
Customer is taking longer than planned to complete remediation tasks
Customer is taking too long to provide information required by the project.
Customer is thinking to stop the engagement
Customer is upset about the non-availability of Service now (ticketing tool). They expect Microsoft to internally resolve the roadblocks for ticket creation.
Customer IT capability to achieve their developements could impact the critical path, and project finances
Customer may reject profile of the Control Panel support engineer put forward therefore the support engineer may not be able to start on agreed date of 1 Nov
Customer might not approve entire hours charged for App Proxy/MFA projects
Customer might not continue the delivery of the remaining engagement due to dissatisfaction of the value of the incident response report.
Customer might not start the project
Customer might want secure his servers that doesn't have any PKI role in them
Customer migration to open source products
Customer new requiriment to have a golive every 4 moths could increase time
Customer not able to identify 250 servers for migration
Customer not making backups as requested by project
Customer not providing the right resources for 1:1 meetings
Customer not ready in time with pre-requisites
Customer not satisfied due to the fact that project team does not act/execute as a Microsoft Product Team.
Customer Operational Team not ready to take over (GSS IT) - Handover from project
Customer PJM not assigned
Customer PM having techincal discussions
Customer POC Rajnish is transitioning out this project and will be replaced with a new person: Seetharam and new POC need to provide signoff for Deliverables.
Customer Pre-requisites cannot be delivered due to lack of capacity
Customer process to secure vpn access has taken one month with no results for the recent request for vpn access.
Customer project management is incomplete
Customer project manager is not managing the project
Customer relationship is strained and escalation and steering committee relationships have not been identified.
Customer requested at project launch to add a new service (Travel Warning) in iteration 2
Customer requested changes to the Action Plan with new functionality may impact schedule
Customer requested, at project launch, a Go-Live after every iteration, which is not in scope
Customer requests schedule extension without compensation
Customer requirements more complexed that there is no clear definition in the scope of the project that make project scope is too difficult to control and the budget will be over.
Customer requirements reflect an expectation of a very high number of customization (approximately 80%)
Customer requires continuous support from Microsoft on tasks that are out of project scope (support on architecture definition, Azure services comparison, etc). It's unclear how to support the customer on these activities.
Customer requires too much time to test the migrated servers. There are a lot of observation to be checked with our team.
Customer resource committments
Customer resource constraints and priorities may prevent Bottomline from completing their critical path technical tasks on schedule
Customer Responsibility to provide ASR Hardware at each location contributing towards Lift and Shift migrations
Customer Responsiveness
Customer responsiveness to requests for information/general availability is low.
Customer Satisfaction Meeting not organized before Program Closure meeting
Customer SMEs may not be able to articulate the complete and accurate requirements.
Customer SMEs may not be available to attend the workshops
Customer SOP Risk
Customer Sponsor Change
Customer staffing needs to be maintained during the test phase of the project
Customer Stakeholders are not engaged enough to steer and help solve the issues the initiative is facing.
Customer takes long to overcome dependencies on the project
Customer technical requirements and environment are increasingly correct. Risk that revised technical environment may not support current and future requirements
Customer time to validate FRD could take more than planned
Customer uncertainty surrounding the merge and acquisition of a new name will impact work streams (ODB and EXO MT)
Customer very likely to CR
Customer want to stop the training till he understands what they have bought to Telefonica, to see if it is needed to include that part in our scope with a cahnge request, or not. But doesn't want to cover this part until then.
Customer wants Mayself and Ada to follow up Avanade
Customer wants the project to be implemented in november since SHA1 is deprecated on Jan 1st 2017 and they need to apply changes on their certificates because of this.
Customer would like to utilize Nutanix platform (software) with Lenovo hardware to host the solution. We have some major issues of supportability and suitability that we need to research; i.e. Windows Server 2016 is not yet officially supported on Nutanix .
Customer’s project manager o Continually requesting our attendance at meetings (ad-hoc, not critical to meeting target Go Live/internal to the City/unclear meeting objectives). o Introducing scope creep which is “termed” issues but are actually enhancements being requested by their business clients o Unable to get commitment to meet bi-weekly to synch up on project activities/status
Customers acceptance on the revised commercials
Customer's PO is not quality and also hasn't Scrum experience so the requirements is not clear that impact project delivery schedule and quality.
Customer's Project Manager is going to get replaced
Customers TS2007 server farm is on Windows 2003 server that has 4GB RAM. There is a risk that our jobs might not be able to run with limited RAM
Cutting over Ontario.ca, largest domain first
CV has not published a formal design document with MS team. The workflow development by CV is based on a series of conversations and feedback shared on the workflow. This could lead to issues being identified during the system testing leading to Schedule impact as the product matures iteratively.
D365 is the latest release of CRM. Our required ISV are not up to that code level.
Daimler has not yet given any specific performance requirements for production system
Daimler wants to add scope to address NTG5.5 CY17 and NTG6
Dashboards design – ICONCIS out-of-the-box design not to Ascendas expectation.
Data Connectivity to Gemini BMS not ready by end Month 2 of project
Data entries into ChangePoint / Chronos are irregular and don't correspond to the Partners' RAMS.
Data Integrity/Data Loss in migration
Data Integrity/Metadata field descriptions
Data Mapping and Requirements are pending
Data Migration
Data Migration - Database is 7 TB in size. Not the typical migration size candidate. Migrating data may take longer than estimated
Data Migration - REOPENED
Data Migration is taking longer time then planned.
Data Migration issues
Data Migration may not be completed within 8hrs migration window for 2nd Pilot Dealer
Data Migration track is behind schedule
Data Modeler Resource: Risk to Quality of Database Design and Data Migration
Data preparation by Sinara for data Migration Release 1A
Data Quality & Cleansing Effort unknown at this point
Data Quality of the two hypotheses currently analyzed seems to be not suffiient
Data source for performance evaluation hierarchy is inaccurate or incomplete; requires extensive updating
Data Structure Impacts/De-normalized in ICM
Database migration was not done because SAT issues and we need it to upload database to Azure
Database Migrations are not excluded in the SOW, and the fees are not included in Project Estimate - per Factory Review of Estimation Model, and this could cause a significant increase in cost of project (~10% or 50 to 60K)
Datacom has assigned only one resource (Chris Bannan) to review all HLDs and Detailed Designs and he is running behind with reviews.
Datapower is ECI's IDP and it is not supported by Premier
Dataset need cleansing
Date set MAY/)/2017 for initial communication testing. Customer has not confirmed.
Dates for Vulnerability Test
Dati di test per sviluppo SSIS
David Z the subject matter expert has key dependencies on all requirements shared with the Tech Lead.
DBSW program scope and success factors are not finally aligned /agreed with steering board and key stakeholder.
Deal team has explained that the customer has unique requirement to support users from various retail outlets. An example that has been shared by project team for this scenario is like if a customer walks into a retail outlet to purchase a TV and needs to apply for loan. A user at retail outlet must be able to submit a request for loan, track the status of request and submit the required documentation of customer to the bank. Bank HQ resource then must be able to process the incoming request, must be able to uniquely identify the users submitting the request and then update the status of request. There are over 30,000 users who would be using application from various retail outlets across Russia
Decision Governance There is a risk that existing Prudential IS OM is not fit for purpose for the adoption of Azure Cloud services. Owners of decisions needs to be clarified with PGDS and business units
Decision has been made to include McAfee in the current build. This has not been designed for.
Decision on Domain Controller (Hyper-V or VMware) delayed by customer.
Decisions on Emerging Requirements impacts the overall schedule
Decommissoning Schedule
Dedicated resources (both IT and users) are crucial in the data conversion activities. Both TVB IT and business users play an instrumental role in the data mapping (including transformation rules) and verification process. Subject to the data quality and data cleansing requirements, the time window for migration could be under stress relative to the baseline planning.
Defects raised from sprint 8 onwards
Defence Infrastructure Readiness - If there isn't sufficient capacity for deploying SQL server platform within the existing Defence environment, then additional infrastructure (Physical/Virtual) will be required.
Defined plan SE is targeted at finishing migration by end of March 2017. Currently submitted numbers are lower than planned and therefore force an extended timeline.
Definición no detallada y clara de los requisitos iniciales generando diferencias frente al alcance establecido al inicio del proyecto
Definition of User Migration Calendar
Definition phase may not be able to complete in 16 weeks due to slow start of the project and holiday season
Delay activities due to micro management meetings and emails that make our consultant to use his time unproductively
Delay could lead to big bang scenario when end date is not allowed to move or delay of the whole project
Delay due client does not deliver the prerequisites for migration within the time required.
Delay due to changes in deadlines for the implementation of related projects carried out at PERN.
Delay in access to the Infrastructure
Delay in Application Priority List and Pilot
Delay in approvals of FDDs may result in delay in deployment into testing and Production environments.
Delay in approving the Amended WO by county to address the following issues will bring the project to complete stoppage and is preventing all 1. Their PO contained additional T&C’s that conflict with our MSA and Work Order 2. The amendment contained the over-allocation of expenses versus have the PjM hoursinvoicing till date. 3. The Period of Performance is prematurely set to Nov 11, 2016.
Delay in Business Case signoff
Delay in closure due to customer readiness for device enrollment dependencies likely to be ready only by August end
Delay in configuration of Audiocodes device will delay configuration of LBR
Delay in CRMOL Test/PreProd Environment setup with Integration endpoints configured
Delay in decision making
Delay in delivering information and solving questions on Claro's side during the internal testing process
Delay in Delivery
Delay in Functional Spec sign-off for each sprint
Delay in getting access and endpoint details to connect to Genpact LOB Systems.
Delay in getting Azure Subscription access
Delay in Infra for Pune DC
Delay in infrastructure procurement by TetraPak may delay the start of stabilize phase
Delay in Iteration2 design closure will impact the overall project schedule. This could impact the FF cost with Hitachi (subcontactor in India).
Delay in Migration track 1. Delay in availability of 1 TB data from Genpact - Earlier there was a delay of 6 weeks, and there would be an additional dellay looking at the pace of developments 2. Delay in Azure VM availability 3. Delay in S2S connectivity
Delay in Partner WO
Delay in Phase 1 : RAMP UP. This phase will contain discussions with customer on planning and delivery of key deliverables by customer including ramp up of their resources. It is possible that customer will not be able to align with the pace dictated by our FF offer
Delay in Phase 2 : Set up ADMS This phase will contain the set up of ADMS and creation of all support documentation deliverables by Msft team. Close colaboration with customer teams is necessary to complete our deliverables, as they provide key imput. It is possible that customer will not be able to align with the pace dictated by our FF offer resulting in delays of delivery of key input.
Delay in providing direction for work to MS resources by BOA Project Manager
Delay in providing the required DNS records for SfB Internal Components: Mediation, SQL and Reporting Services
Delay in R2 (1st iteration)planning may impact R2 timelines
Delay in receiving Census Data
Delay in re-instancing the SQL servers and redeploying CRM may cause further slippage
Delay in requirement definition by the customer which may impact in the team having no work to do for PD2 and PD3 after completing the work for PD1
Delay in scope alignment for POC directly impacts the start of activities from MSFT to deliver according to timeline
Delay in securing resources may impact delivery.
Delay in SharePoint Feature Pack 2. The SharePoint Feature Pack 2 for SP2016 includes the new UI features that are necessary for implementing the UI upgrade for DMS.
Delay in signing off of the CR for the application scope change from On-Premise to CRM Online 2016
Delay in start of Enablement for EMS and Skype
Delay In submitting the first draft. Review now needs to be done by the customer in max one week. Failing which can result in schedule overrun.
Delay in testing and development activities due to errors in the QA version of Poliedro Enterprise
Delay in the decision about the tool to be used in marketing / campaigns.
Delay in the decision of the migration environment
Delay in the Project as a Whole due to the customer delay to gather the stakeholders team end Homolog enviroment
Delay in the start of this project is preventing revenue recognition. From a PjM perspective, I am driving as hard as I can to get this project kicked off.
Delay in Ticket Closure
Delay in Transition to PMA team and no oppurtunity for shadow supporting. KT to PMA team on CRM Online 2016 is completed on 26th Jan and PMA support was expected to kick off starting 29th Jan.
Delay of getting a CR completed . Services Connect and Pursuit Lead need to be assigned for scope changes/CR
Delay of PoC environment for SharePoint Upgrade
Delay on "Financiador" project that could affect the "Modernización" project base line.
Delay on delivering all user stories related to technical product backlog
Delay on delivery to Microsoft team a second application to use for DevOps PoC
Delay the alpha pilot date if DOW did not provide the required items
Delay to delivery of MIM server guidance document to KBC. Peter Geelen (sub con) was requested for 2 days to work on a guidance document for MIM server. Due to his lack of avaialability (expectation was set with Tom & Dirk - sponsors at KBC), and the fact that 2 additional days were needed from KBC - the document hasn't been done. A due date of 11-Aug was finally committed, however, Peter Geelen had a personal emergency situation due to which he is now away until 31-Aug. As a result there is no clear ETA. KBC has been informed of the situation, however, it is not plesant.
Delayed Customer sign off on CR004 for 166 to 180 Active Archive groups
Delayed feedback to deliverables
Delays from Bechtel
Delays in achieving Design Approval
Delays in analysis phase from Mediolanum and other vendors while providing technical references to Microsoft team on Genesys integration
Delays in developing SAP interfacing scripts
Delays in getting the Certificates
Delays in getting Visa’s for the identified onsite resources
Delays in installation and configuration of SBA device by MTN Cameroon is delaying schedule and project closure
Delays in project schedule due to resource constraints and unavailability (competing priorities)at AB Energy
Delays in project timelines due to dependencies on 1706 installation
Delays in provide integration interfaces from customer side
Delays in providing the right information and migration batches, will cause both Lighting and Lumileds not to be completely finished with their migrations by September 1st
Delays in providing: - Information about current infrastructure and company procedures\politics. - Information about application. - Documentation
Delays in SME Functionality review may impact schedule and budget
Delays in staffing Security Consultant leaves one unstaffed role per the SOW
Delays in the delivery of required information, documentation, environments, licenses, etc. for technical activities
Delays in the issuance of certificates for ADFS. Kroton suggested the re-use of existing certificates, however as the URL of the ADFS 3.0 can change is necessary to evaluate the possibility of re-use of SSL certificates.
Delays in the review of deliverables by Claro
Delays is identification of servers may impact schedule
Delays or lack of coordination for the implementation of remote activities with Microsoft factory team
Delays to ITSM elements may lead to project delays
Delays to LLD phase completion
Deliverables Acceptance Criteria
Delivery of solution is a highly complex process
Delivery team planning
Dell has not finalized Operations approach for 1,000 (now approx. 700) POC users. Help Desk and Operations team say they will not be involved. Dell says they can manage it within the team
Dell reports a 3 month delay in the setup of the Dell migration synchronization tool required to synchronize identity objects for JCI SOA project due to a SCCM rebuild time of 3 months.
Deltatre is facing some difficulties on delivering the functionalities and therefore it could lead to delays.
Demand visibility
Dependancy on Operations DB Interface Views
Dependence on other projects and policies to Poliedro, which affect the scope or they could generate change controls.
Dependence with other team (Oracle), and affected the times.
Dependencia con terceros (fábricas y proveedores de Claro) para la ejecución de actividades, entrega de requisitos, resolución de dudas, etc.
Dependencia de un experto en Claro para los requerimientos y definición del proyecto
Dependencies
Dependencies among services and infrastructures
Dependencies from teams other than Customer (IBM)
Dependencies from teams other than Customer (outsourcing team)
Dependencies on 3rd parties: Integration with the MOI
Dependencies on other LoB systems and lack of knowledge around LOB systems
Dependencies on other services and infrastructure (networks, security, storage), have not been resolved at the time of deployment in production, producing problems in the deployment
Dependencies with different teams to advance in the migration of environments activities
Dependencies with other components of the solution (F64 and F33)
Dependencies with technical leader in Claro that change the role in the company
Dependency on Arcworx Code- Status Unknown -ArcWorx needs to update their code to allow integration with new platform. Status of work unknown
Dependency on CDW infrastructure on staged data. Due to network bandwidth constraints, database size, and the frequency of data being updated, additional applications may not be able to be added to the current environment.
Dependency to start UAT for a communication flow.
Dependency with changes made on Poliedro Enterprise (services) by other projects in Claro
Dependency with the migration of components (applications) on another area of Claro that should be synchronized to be executed along side the migration of application within the scope of the project.
Dependent on Clusters to have them remediate/investigate their applications that are dependent on UPN - Negative user experience if applications break that we did not anticipate.
Dependent Project delays: IDM P2 Online Card Sales NTMAS AT Park
Deployment of a feature that is in Preview
Deployment timelines for china might be tight
Description of B2B/"Serie" services not complete and not detailed enough to build user stories according to management expectation
Design 2b is expected to need additional resources to optimally cover FDD creation. Critical will be to bring on appropriate Manufacturing consultants with lean experience.
Design dependency on NSSAB design
Desktops remediation update previous mailbox migration. customer plan to migrate each desktop just before the migration take place
Detection of post go-live product and other bugs delaying pilot store and roll-out into 500 stores after go-live
DEV and QA environment delayed with several technical issues and forecast to complete by Mid-February.
Dev team has submitted CR for various delay and changed in development methodology asked by client. There are several discussion but same is not yet sign off by customer.
Dev team is still waiting for details regarding Abbott Data format.
Development activities are advance with a communication flow from polybase to a Storage Account, enabled towards the network segments of azure. This is not an operatational best practice but for now helps to move forward.
Development ensurance management when merge will be executed with other developments and adjustments by Claro and its fabs.
Development environment / DUPLICATED
Development environment is not available
Development team depends on Skype connection to access Dev/Test environment
Development team does not have any experience in HealthVault product, which is core of the solution.
Development team must maintain a high velocity to meet the customer's expectations and to deliver the expect scope on schedule.
Deviation from original approach to non-prod buildout The original approach for the non-prod build out was more of a Starbucks participating with Microsoft and then for Production, Starbucks driving with consultation from Microsoft
Device Analysis – To install Office Pro Plus. a. We need to get a timeline and estimate on what this analysis will take and when it can be done. If we have a number of devices to be upgraded, we need to what the effort will be as this could delay a number of individuals from upgrading to Office Pro Plus and thus affecting the O365 Migration
DI Lead Consultant replacement
DIAD - Lack of physical and logical infrastructure of the target forest/domain.
Difference in business goals and drivers behind the project between ING Poland and ING Netherlands. One of the goals for ING Global migration project is to reduce IT staff costs.
Differences/Arguments with customer because SLAs have not been established for QA and production
Different environment between production and quality in Claro
Different logic being used for different company codes will lead to breaking the LOM application. Having to address this 1 company code at a time during design will have a significant impact on schedule, budget and overall progress of the project.
Different SIP and primary SMTP
Different Telstra embargos will impact and slow down migrations.28/06 EOFY embargo has impacted migration schedule and active archive groups pushed out to early July.
Difficulties obtaining Xamarin specialized consultants
Difficulties related to monitoring of third-party vendor hardware
Digital Architect: No available resources to start the project.
Dilemma in making decisionn
Disapproval of the proposed process for optimization by all stakeholders
Disconnect between business and IT concerning comprehensive testing plan
Disconnect between customer's adherence to the integrated project plan including waterfall (functional design-technical design-build-QA-UAT) processes for large groups of scope.
Discussion of cross-functional links between the documents of the FDDs may affect the timing of completion of the Design phase.
Discussion whether It is possible that on different servers the same user name exists for different users. Maybe a problem for migration.Microsoft must provide us a procedure to address it.
Disruptions on migration day due to deployment of Office ProPlus on same day as migration (T-0).
Diverging Requirements (Raymond/TMHU)
Do not have easy access to Tesoro Data and SharePoint site
Do not yet have Data Insights Consultant identified for workshop week of 9/18.
Document Review
Documents to be updated to align with development and testing
Does ADMS fit the requirements of the Customer
DoITT currently considering using AX7 rather than currently in-scope AX 2012 R3
DoITT stated that the Total cost of ownership of this solution due to License and Support costs (not delivery) is more than they have appetite for at this time
Domain Controller Communication Update
Domain controller needs to be setup in VMs for development team to start the work. VPN is required to connect to the Domain controller in the production environment
Domain has no appropriate resources to deliver this project. Currently assigned resources have to few time and/or have not the required skillset
Domain verfication delay would impact the build phase dates
Domino Remediation for Room&Resources not done for pilot. Still not done – Boston R&R last to remediate but in progress
Domino Remediation issue for first migration
Dopravo UX design go beyond May 1
DRP - Implementation of Pass DRP not on shelf element. Full implementation to defined & supported by the projet
DRP could be necessary and this could involve an OnPrem implementation
Due actions on the customer site
Due customer has not updated sight of the utilization of the contract they may comply about the consumption of it and try to renegotiate the time of support
Due Dilligence and Remediation
Due the implementation of OSE will be mandatory from June 2018, there could be delays for the estimated output in May, whose impact is postponement of Azure's maintenance, support and platform activities
Due the resources rates has increased since FY18 start
Due there are some steakeholders against the project, there could be blockages in the progress or disapproval of deliverables, whose impact would be the application of fines for non-compliance or very high number of observations generating overload in this activity in the project team
Due there is a limited credit in Azure for the development stage, a higher consumption could be presented to the granted credit, whose impact would be greater investment required by Microsoft.
Due to Christmas holidays not all resources may be available during end of December/beginning of January.
Due to customer internal security event (auditor found the existing 2 years PT points were not fixed yet), currently CIO has started the mitigation project (from Apr. to Sep.) as priority first with whole TSMC IT which includes network, infra and AP department. So customer has request to postpone project schedule to October.
Due to customer internal security event, the original AP development plan was changed. After negotiated with customer, the 8th application will be provided at July but the resource will be shift to internal mitigation project immediately (from Apr. to Sep.). So customer has request to postpone project schedule to Oct. 1. There are 4 applications are still not decided by TSMC. 2. Due to TSMC internal application development schedule is not confirmed yet, the project schedule will be extended based on TSMC's schedule. 3. Has discussed with TSMC owner and push them to confirm the schedule and speed up the progress.
Due to customer request the burn rate will be lower than estimated in December for the first three month.
Due to delays caused by ALNG team, MS may present CR with respective costs
Due to delays in activating the Azure subscription in time for delivery on December 15, there could be a breach of the deliverable E1 whose impact is the application of a contractual fine
Due to extended scope, extensive parallelization is required to meet the Feb-28th timeline
Due to festival season in the month of Jun & Jul with limited participation of resources for workshops, the timeline may get extended
Due to lack of resources time delay in implementation
Due to lack of specification of some non-functional requirements in the TDR, there could be disagreements in the form of measurement, whose impact would generate delays or disapproval in the validation of compliance of the established non-functional requirements and generating cost overruns for fines
Due to non-fulfillment of expectations of the areas responsible for the review and approval, it could generate dissatisfaction in the approval of the E1 deliverable, whose impact is delayed in the beginning of the phases of development and breach in the delivery period
Due to non-local resources being assigned to the project, we have the risk of not having on site support when it is required by the client
Due to regulations that impact the CPE process and that must be implemented mandatorily, changes could be generated in the scope of the solution for the start in production.
Due to replacing the Architect with another one, the project end date might delay from 30 Nov 2017
Due to requirement readiness and complexity, there is a tendency for reschedule of FS towards later batches. In summary, there are 15 FS to be released in last 2 batches (as opposed to 9 in the baseline schedule). The chances to conclude 15 FS within 3-4 weeks are at risk.
Due to resource constraints on the customer side, they have asked for Microsoft to take on the Performance, Functional, and Integration testing task. The customer will still be responsible for the final User Acceptance Testing
Due to restrictions of scope, there could be retsrictions for project team to accompany Claro during its whole deployment process.
Due to sensitivity of customer data (police officer records of performance, etc.) we are only allowed a randomized, obscured subset of the data, which can lead to misinterpretation of the data.
Due to SSRS native mode not being available, prior to any LOBs accessing CIHS data, the security implementation needs to be reviewed / refined based upon CDW architecture.
Due to SUNAT does not have updated documentation about the current solution of CPE can generate differences with the functionalities developed for the solution in the cloud
Due to the Annual Result Announcement, CKHH would like to prefer to data collection after 22-Mar
Due to the August holiday period, availability of the right resources to attend workshops may mean gaps in knowledge
Due to the big data of system, high concurrency and high risk of SQL Server performance tuning after project online. So resource reservation is needed.
Due to the big data of system, high concurrency and high risk of SQL Server performance tuning after project online. So resource reservation is needed.
Due to the complexity of SMM and its interdependencies with other modules in Stage 1, the development progress has slowed down significantly. The technical design of SMM is also taken longer than expected.
Due to the dependence of a single expert resource (Victor Mendieta) for the capture of information in SUNAT, there could be a bottleneck in the capture of information, whose impact is delayed in resolving doubts and reviewing requirements that affect delivery dates.
Due to the dependence of the CPE process with the current solution of other SUNAT applications and solutions, it could be generated that the CPE solution can not be put into production in the cloud, whose impact is delayed in the full SUNAT CPE project and start of support and maintenance
Due to the difficulties to identify the changes on the Informix database and the synchronization time restrictions, there could be modifications or new functionalities required in the On-Premise environment to achieve an optimal data synchronization mechanism, whose impact would generate additional work by the SUNAT team or change controls to the project
Due to the fact that the TDR does not have associated requirements to any specific deliverable, it could present inaccuracy in the scope expected by SUNAT and in the delivery dates, whose impact would be conflicts in the approval phases generating delays in the closing dates of the project
Due to the issue of quality found during the testing of SVC, its needed an exhaustive review of the deliverables and to ensure special dedication of the Technical Lead to this last deliverable of the project.
Due to the lack of detail about the replication of data in the TDR, could be an increase in the scope of data replication needed for the solution of the CPE additional to those established in the TDR whose impact would generate delays or disapproval in the validation of compliance with non-functional requirements, and generating cost overruns for fines
Due to the lack of experience of the SUNAT in cloud solutions and Microsoft technologies, there could be disagreements in the design and technical decisions, whose impact would be disapproval or customer dissatisfaction of the deliverables, as well as additional scaling activities
Due to the lack of knowledge of SUNAT in the implementation of solutions in the cloud, it could generate lack of understanding of the architecture and solution delivered, whose impact is additional explanatory activities or delay in the approval of deliverables
Due to the lack of understanding of the proposed solution, there could be delays or disagreements that take more time than estimated in the review and approval of deliverables or documents, whose impact is delayed in production.
Due to the lack of understanding of the SUNAT in the security mechanisms that will be implemented in the solution for the protection of accesses and information, it could generate disapproval of some components or deliverables, whose impact is delayed in the delivery activities and breach in the established deadlines
Due to the specification of the Azure payment in the TDR for processed voucher, there could be problems in the Azure billing, whose impact would generate problems in the support and maintenance phase
Due to the technical complexity and dependencies of implementing MPLS connectivity, it could be unfeasible for the configuration of ExpressRoute in SUNAT, whose impact would be breach of connectivity through this technology
Due to the unavaibility of the project environment until last week , the partner was not able to start the developement durint the sprint 1 and 2 .
due to the way the documents are arranged in the folders: a lot of clips, staples, and laces that take a long time while disassembling the folder (and later re-assembling it), also a lot of small papers (post-it note types) that need to be separately scanned, and pages with a photograph of the health professional that requires the scanner to be set at a different capture configuration from the rest of the pages in the document. This is all taking a toll in the overall time it takes to scan
Due to time constraint, the team has opted not to use certain common patterns and code analysis tools, these will be entered in the backlog/technical debts for future consideration. The scoped items to • Do gated check in for TFS will not be possible because it requires the use of the code analysis tools. • Utilize a TDD approach may not completely fulfil without the use of these common patterns.
Due to unexpected changes, the Technical Lead currently assigned to the project will change. A plan has to be defined to find a replacement and complete the knowledge transfer.
DuPont resources working on multiple workstreams, and availability for many workshops that may overlap may not be able to adhere to the tight timeline for completion. For O365, one of the Pioneer resources has the responsibility for three tasks that has high visibility, (AAD Connect, ADFS and set up of Hybrid server). Another resource has the responsibilty for the edge server which impacts Skype and O365, this action has been outstanding for two weeks).
Durante la ejecución del programa el Banco seguirá ejecutando sus proyectos e iniciativas, las cuales tienen pases a producción. Existe la posibilidad de que se requiera priorizar los proyectos para poder realizar los pases a producción.
During a meeting with the Program Managers the Expo2020 team confirmed that the Aconex production environment cannot support the production of smoke testing data to confirm that the CRM and Black boxes deployment has been completed successfully.
During discovery it was identified that Sky do not implement or whish to implement a number of native security controls in Windows 10, including the Windows 10 Firewall & Defender. Sky also make use of a 'Grant Admin' functionality allowing users to have local administrator privilege on their devices.
During migration from vCurrent to vNext TD needs to give default inbound internet access to O365-D. This will expose their EDOS endpoint on the Internet, thereby making it susceptible to ‘Password guessing attack at scale’. This would only be for duration of the migration.
During the BU CEO meeting, it was indicated that we should plan waves of implementations for every 3 months in production. They also indicated that they wanted the working models to be production ready and not be in prototype mode. This could mean that we might have to change the current Rapid Prototype based model.
During the session on 2017.07.24, the IP department requested more time to provide the business processes regarding the processes. - The IP team confirmed that the existing Payment process presented is not finalized and will need two more weeks to finalize and provide it to MS. - The IP team confirmed that they will provide process detail for following services: a. Enabling Work Permits b. Soil Investigation c. Building Permit d. Plot Possession These processes will be a part of Pre-Construction Stage. - The IP team will confirm the following enhancements to the existing CRM Implementation a. Need to add date column to SVP notes b. The Sub Theme selected in the participation journey should be shown in the country overview report.
DXC has stated that Day 270 (December 2017) represents a milestone where they desire the same funcationality in DXC as is currently in HPE. This means Skype experience, Exchange and Sharepoint. Delays in staffing are putting completion timelines at risk.
Dynamics OPS mit CRM Anbindung
E- firma development pending
E2E Testing Visibility and Progress
EAMER Configuration Backlog
Early adopters to the Cloud
Early production expectation of customer
ECI has mailboxes with more than 2Gb which is the license they will assign to some mailboxes.
ECI will freeze their production systems in mid November
ecisions about the final to-be configuration need to be taken by iGoVTT. Otherwise, the project will be late
Effort to develop sign-in/sign-up through telephone is not included in current ETC.
Efforts and technical integration architecture for the solution with different services (OS Plus) may be underestimated.
El Banco maneja varios Tenant de Azure y se requiere identificar cuál será el que se utilizará para el Proyecto AIP.
El Desarrollo de la aplicación de biométricos podría no empatar con el plan maestro de implementación de la implementación Dynamics CRM
El desarrollo de Timbre Fiscal 1.1 tiene atraso en Anexo 20 parte 2
El desdoble de la información actual aún no termina de procesarse. Actualmente se están procesando el histórico
EMS requirement before Velocity
End date of last stage can be moved due to license providing delaying
End User Knowledge is suffering due to lack of communication (Offerings for Training etc.)
End User Satisfaction/Advanced Finds
Engagement does not reflect the SOW, customer is beyond a foundational engagement and is looking for validation of significant plans.
Engagement has been oversold and not all MCS hours may be consumed by 30 June 17
Engineering to execute the goLocal V1 process to move US tenant to CAD. There are limitations and risks with this process.
English content might take longer approval time due to BBG team has other project to finish with higher priority
Enhancement requests continue to be made which may put at risk the delayed completion date
ENMO Customer discovery activity is likely to drive change to SoW to support some transformation activity
Enterprise Site Discovery was approved on 6/22 but not turned on
Entrega de servidores de desarrollo definitivos
Environment Access to MS Dev resources
Environment Build and Migrations dependent on 3rd party- Infosys owns & operates datacenters; Environment Build and Migrations dependent on 3rd party scheduling & coordination
Environment readiness can delay the project as we have tight deadlines.
Environment unavailability for testing
Environments not available
Environments: With 3 env - dev, test, prod- the customer Azure budget will run out in June 2018
Envisioining Workshop to be done Remotely
ER Configuration for O365 to meet TIC requirements
ERP implementations impacting business processes usually see big resistance in the business
Errors and additional stabilization time due to the high complexity of the process of integrating the modern version with Poliedro Enterprise v4.6
ESAE and PAW are red due to end date slippage into May, due to resource and change constraints imposed by AIG.
Estandarización de data en Oracle y homologación de data AD pueda tardar más del tiempo contemplado antes de pruebas con QA
ESUN Project stakeholder change
EV volume is much larger than what is reported in reports provided by OPS.
EVS contract has been signed off and Real Madrid wants it to start as son as posible. This impacts directly on current roadmap, since although we may have new developers, QA and realeses roadmap will be affected
Exchange Encryption Services Workstream
Exchange resource required for EXO MT-MT workstream
Execution of processes in the production environments that require planning and prior approval of the customer
Execution of Simulation has uncovered issues that should have been identified during prior test phases - this may affect successful transition to Production.
Exemptions in Proxy/Firewall
Existe un manejo dinámico de contraseñas de Admin Local, sin embargo no existe un procedimiento que indique cómo se manejan o quienes son los custodios. Se requiere identificarlos antes de las ventanas de pase a producción.
Existen diferentes aplicativos en el Banco instalados en diferentes servidores y no están catalogados. Es posible que se presenten problemas en la operación con el cambio de dominio de los usuarios/servidores que hacen uso de los aplicativos por desconocerse su origen y dependencias.
Existing logic will be re-used for Mesh Decimation workflow, so the validation of the decimation can only be determined by checking entries in database.
Existing solution code may not be production ready. Code developed in different POCs was packaged into a production solution.
Existing test cases may be not covering all the scenarios
EXO MT_MT schedule realignment
Expectation from the Customer, to ensure a Agile approach, based on a ongoing identification of Journeys and Features from the Business
Expectations and understanding of Agile project execution with Sonova stakeholders
Expectations do not align between signed WO and PWC consultants acting for customer
Expectations on SSO configuration
Express Route Circuit for all Regions
Express Route- USDA need to implement an Express Route Solution by 10/1/17 in order for the migrations phase to start and complete by 5/31/18.
ExpressRoute Availability - RemoteApp has some dependency on ExpressRoute – should this not be ready in time for build will need to revaluate next steps
ExpressRoute implementation delays
ExpressRoute Setup
Extend Second FC - Don Tavani to support project activities Our Second FC - Don Tavani is supposed to roll-off on Dec 30th. DA alone will not be able to support the project activities due to the aggressive nature of the project, slow pace of county, the on-going discussions related to emerging requirements and most importantly the re-planning efforts to go-live early with Dynamics AX and Sympro
Extension to Project Closure date
External sharing of crop sites, and AD group mapping for the Crop sites will need to be addressed prior to migrations
External System Dependency - CSS/R If the external CCS system is not ready in time for Stabilization testing in MSQA, then all testing will be performed with Stubs. Final integration testing will need to be performed in as part or future Drop stabilization or even future Release. In addition, PSL testing will not be able to provide will not be able to provide actual end to end times for the application.
External System Dependency - RTT If the external RTT system is not ready in time for Stabilization testing in MSQA, then all testing will be performed with Stubs. Final integration testing will need to be performed in as part of future Drop stabilization or even future Release. In addition, PSL testing will not be able to provide will not be able to provide actual end to end times for the application.​
External System Dependency - WIG if the external WIG system changes are not ready in time for Stabilization testing in MSQA, then all testing will be performed with Stubs. Final integration testing will need to be performed in as part or future Drop stabilization or even future Release. In addition, PSL testing will not be able to provide will not be able to provide actual end to end times for the application.​​
EY is in the process of outsourcing to a third party company. The current expecation is the automation testing currently being done by our team in India will be asked to perform knowledge transfer to the 3rd party company.
Failed Delta and Bulk Load activities
Failure to comply with customer expectations regarding the reports generated by TFS based on current reports, especially in the demand management process
Failure to provide timely resources to Microsoft SMEs, e.g. SCM/AGPM infrastructure, BP1 domain accounts with appropriate permisssions to work on GPOs etc.
Failure to provide timely responses to technical questions from SMEs in one to one meetings
Falta de conocimiento y familiaridad con las aplicaciones a modificar por parte del equipo de desarrollo y pruebas
Falta de definición de Fuentes de datos para los reportes.
Falta de firma de contrato nuevo que permita realizar finalización la fase de soporte para estabilizar la herramienta en ambiente productivo
Falta de tiempo o recursos para la finalización de las pruebas de UAT impactando la fecha de finalización del proyecto y utilización de recursos mayor tiempo al planeado
Fast Track Team
FDIC Corporate Communications will not release the 'global' email announcing the project to the organization, allowing the project schedule to be finalized
Feaure Release may require AT reinstall
Federation solution - undetermined whether AD FS S3.0, Okta, PingFederate, etc.
Feenstra resource availabilty
FF arrangement for all project stages
Fiducia&GAD lacks information on AD at the moment.
FINANCE: D365 Usability issues
Financial loss due to extra costs of the model required to get customer satisfaction up to 280 K€ to fund
Financial Risks
Financials will be impacted because the customer does not want to pay for the CR
First invoce that is being raised is not yet approved by shell this may result into cost increase.
First Release going live on 19/12/2016 but not post golive or AM existing
FIVB availability and capacity for fast decision making, intensive operative work and handling 3rd party vendors
Fixed Fee Subcon cannot add into VSTS as no Microsoft alias, security policy changed as security reason recently
Fluctuating totals of Process Test scripts in VSO.
FNB skillset for Hyper-V - Hyper-V is a new Microsoft product that is now introduced to the FNB operational landscape.
Following ADGM's escalation in February, the subsidiary promised to involve Court and Legal SMEs on the project (which didn’t happen in the end) and to increase the time of the Business Analyst (subcontractor). We estimated a need of 30 additional days of the BA to cover the related tasks until the end of the project. These 30 additional days require $70K additional funding that the domain is expecting the subsidary to fund (and was communcated since February). Since no decision has been taken yet on the origin of the funding, we didn't issue the Work Order and we are hitting a critical path where the BA is needed and already conmsumed his original hours.
For administrative issues, delay the start date of the project and go through the date of exit to PROD that is being requested by Business [Oct 2017].
For China deployment of Mailboxes and SfB and for NAM+EUR SfB new local datacenters are to be provided by customer and his partners. Being not available can negatively impact the overall deployment schedule.
For FY18 Starbucks is decentralizing funding such that each application team will secure funding for their application to move to cloud. App teams are looking at many avenues to reduce cost including interviewing other vendors, and analyzing every single financial aspects at their disposal. Starbucks also shared concern over Microsoft resources/sub-con resources high expenses.
For Iteration1 the UI was delayed due to which the team got little time to complete integration of UI with backend development. During this integration starting W5 of Itr1 we found many changes had to be done to align with UI. In Iterations2&3 some Design items changed or not been fully explicited before getting into development and it's getting finalized as we proceed in the development for the iteration. Due to this it's challenging to plan tasks cleanly and also test cannot plan detailed testing activities.
For lack of a Product owner role, requirements is not available for the team to work on, resulting in wasted team hours
For Liechenstein Delay in obtaining FMA approval for the migration to O365
For this project we have not yet had contact with the client nor do we know the progress.
Ford Enterprise solution, use of Informatica with Dynamics CRM
Ford has onboarded over 90 people of which 85% are actual contract to hires. Ford expects that at least 50% of these people will leave within the next 6 months.
Ford is undergoing alot of change; change in IT organization; change in IT management, change in team structure; change in development approach. All of this change is underway without a clear program plan (and OCM).
Ford's approval on project team's travel for upcoming workshops.
Formalize requirement changes from SOW
Foundations Rollout plan
Freeze
From QADC
FTC has had issues coordinating and responding to customer needs.
FTC won't migrate custom permissions and states that any site with custom permissions won't be migrated. 90% of Repsol content has custom permissions, so it is critical that FTC migrates them. FTC changed the scope of what they migrate and affects directly in the project.
Fujitsu do not provide a remediated VDI to align with project schedule
Full contract funding is not secured
Full Migration Schedule
functional documents version
Functional resources are managed as a bucket of effort and not assigned at task level
Funding additional PjM Hours. PjM hours continue to exceed the expected part-time hours week by week. Also, PjM started early than expected and analysis phase was extended by a week. As of 9/2 - PjM hours exceeded by 105 hours over the budgeted hours even after recouping 40 hours with vacation.
Funds required to cover key resources between CR approval cycles
Further delays in resolving connectivity issues with ASE due to Manulife's Express Route configuration is preventing the team from being able to deploy the solution using ASE.
Further descoping due to the budgetc constraint
Further extension to Step 2.0 UAT from end-Nov to end-Dec 2016
Future releases of CRM might obsolete SetValue Method which needs to be replaced in future if this issue is not addressed at this point during this upgrade.
Future work start date is not aligned yet.
FY18 Cost Rates impacting project -ve margin
Galsync V2 will sync non-users objects – mandatory before restarting velocity – risk to not be ready on time
GAP in solution and what the IP can actually offer. #1 - No cancellation email sent to patient after cancelling meeting by practitioner (no email notification to patient when meeting is cancelled) #2 Book multiple appointments at same time for the same person #3 rejoin experience for patient after connection issue in UCWA - Patient joins call gets disconnected re-joins, 2 patients are now visible in the call, both are disconnected after 120 seconds – Meetings participants are not removed if the patient disconnects - also not possible to re-join #4 Followed a link to a cancelled appointment and received: 'Server Error in '/' Application' when the App was starting #5 Android devices in landscape orientation is presented in the wrong orientation in the Web Portal - we are not going to develop the application work in portrait mode landscape vs portrait orientation in app - video stream in landscape
GD has no prior experience of working with Cybage. Their deliverable Quality is a area of concern.
GD resource (DI Developer) not identified/assigned
GD resources onboarded for SPO enablement
GD Resources to be allocated to the project
General web content needs to be signed off which is pending with HEC DG IT Anwar sb since 18th July
German Version of 'Scope and Vision Document' not ready in time
Get collaboration from ADS for phase 2.2
Girish's Phase 2 estimate assumes that we will leverage/reuse Ryan's Phase 1 work Charles' believes that Phase 1 work was a proof-of-concept (only partially reusable)
Given the delays incurred to date and the extended Pilot duration, a key risk to the project is the completion of velocity migration within the agreed timelines from the original SOW.
Globally dispersed team with multiple stakeholders and very high visibility
Goverment Security Identitys are afecting to the final identity solution.
Governance Issue - no clear direction from executive committee that results of not feeling of urgency among the technical team
Governance nominations and set-up (based on recommendations) pending completion.
GOVERNANCE: BESTSELLER delayed test for Finance Vila and Logistics CMW will lead to peaks (e.g. bug fixing) before go-live
GOVERNANCE: Use of D365O standard as much as possible in Finance, Logistics and Wholesale.
GP dev capacity is fully booked for existing GP releases and will not be able to accommodate changes for PBC
GPO - Modern Auth GPO must be fully applied to client machines
GPO for seamless SSO
GPO for workplace join readiness
GSD Support Readiness
GTIL Restructuring of LEAP leadership has Microsoft in the middle of a power struggle between IT and Business leaders.
Guidelines introduced by the SA, PgSA, are not well understood and followed.
Hardware Availability
Hardware certification is delayed for 6 weeks
Hardware compatibility
Hardware delivery timelines
Hardware is not yet ready and may potentially require up to 10 weeks to process before being ready onsite. We may lose the current Microsoft consultant resource if delays result in long idle project time
Hardware not available in time
Hardware not ready for software installation by 12/15
Hardware Readiness
HCA: Build cannot happen until TDA have approved the AZRA
HCA: Paul Grimley is taking a new role and his last day on this is Friday 13th Oct (now less than two weeks). There is insufficient time to get a replacement in and on-boarded to effect a smooth handover.
HCA: SQL Resource Routine - CEC-RI-009
Healthirl Migration User Engagement (UE)
Heavy dependncy on Publicis design completion
HEC has delayed the release 2 content sign off
HEC to signoff SP/HTML designs within 5 days of sharing
Help Repsol on applications testing
Hi TM estimation
High amount of additional customization and reporting requirements
High complexity of applications to be migrated by technologies used, dependencies with other applications and web services.
High impact of ING headquarters on scope, schedule and resources allocation.
High Number of Defects in UAT
High number of external systems & interfaces might increase scope.
High risk of customer not accepting our deliverables due to misaligned expectations, and customer not having confidence in our ability to deliver
High technical complexity in development for all platforms
High technical complexity in Poliedro changes, specially in decoupling and implementation of new frontend, then team has to move a lot of code to services.
HIM handover could not be performed by the Build team.
Historically, communication about the project never flowed down from the Desjardins executives down to the floor ressources.
Honeywell India team seems to be wanting Microsoft to suggest an approach which has conflict with what Microsoft team in the US (Alarmnet) has suggested couple of years back. Alarmnet and Valuenet are having their own approach, which impacts Microsoft to provide a single recommendations - situations are different.
How to match the McAfee Legacy objects to the Intel mailboxes for migration purposes.
HP Business and HP IT are not aligned on the governance model and planning process. There is a larger risk that this will delay the requirement gathering and project panning in general
HP is currently reporting the UAT status as Red and that it is only 61% complete as opposed to expected 100%. Inability to complete UAT on time can impact the key deliverable of UAT sign off, followed by Phase-1 Go live followed by Phase-2 milestones.
HP is currently using ALM vesus VSTS for UAT. Due to this, MS does not have visibility into the bugs that are filed by HP team.
HP will not implement Hybrid until December
HPE needs to decide on the direction of the project, whether Release 2 will go live on 2012 or D365.
HPE, our partner, is expected to deliver backup software with delays
Hrs. Consumed by consultants before Aug-21 cannot be recovered
HSM hardware delivery delays. Long lasting PERN internal procedures (also related to lawyers acceptance for purchase application) may affect delays in PKI and Bitlocker streams of work.
HTML readiness for integration
Huge delay from customer
Huge number of CR with high impact on current schedule for R1
Humana Open Enrollment Freeze
Humana Resource availability
Humana slow to make decisions and determine timelines for remediation tasks
HW/VM not available for SCOM Build.
Hybrid configuration
Hybrid situation with shared mailboxes doesn't work
Hyderabad data center setup has not started yet. This will lead to delay in the completion of the project.
I dati clienti devono essere mascherati
Iberdrola team availability
IBM have a standard process to Harden servers after they have been cutover, so that they can be brought into support.
IBM Project Governance. IBM appears to be in no position to handle the complexity of Etihad's processes and the different stakeholders and vendors involved (Okta, SkyHigh, Symantec).
ICONICS offered 5 copies of its mobile solution in the RFP clarification of 20 Jun 2016.
ICONICS site assessment has revealed inconsistent and badly configured data in the BMS of Galaxis.
Identified more messages getting rehydrated than planned
Identified that a custom policy is needed for IAM PKI. This is a new requirement and will be tracked as CR. We are highlighting it as it is realized that custom code may not work. The product from market was also explored but it is not suitable to customer needs. The option is to check with customer if they can alter the applications (around 6) to accept the standard certificate but it is too costly and may not be accepted. The workaround is also not accepted as it will increase security risk. Hence we are running out of all options and this is a risk. The risk is that we need some solution without which few applications may not work and hence it is highlighted as Amber.
Identifying and engaging business stakeholders for feedback and sign-offs for Telephone Operator
Identity column datatype needs to be updated – This will impact the current timeline and integration testing
Identity Lake
IDM G2C Sprint 1 development extending beyond duration planned due to lacking documentation from the Azure AD B2C Product Team; project team having to review and implement fallback option.
IDM testing
IEC Dev env. Not ready on time
IEC InfoSec does not approve the dev architecture on time
If ‘real world” messages from ITRON are not received by 08 Mar, then it will impact quality and increase the risk of rework
If a delay is faced in completing UAE Exchange tasks in the the Remediation, phase, the assigned consultant shall start working in a new project and we shall need to request a new consultant. This shall also require additional time for shadowing and handover.
If a delay is faced in sending the UAE Exchange team's their schedule to the Remediation plan more overrun time shall be consumed from the consultant and the PjM in discussions related to the Remediation checklist and design that were already delivered and explained. This shall also require additional time .
If a review process isn't in place and active as soon as we send out documentation
If all the required use cases do not pass during testing after PROD implementation on August 30, users will be impacted globally
If any delays with the provisioning of the Infrastructure, Media for SP and SQL and licenses occur, there will be delays in build activities start
IF BOC Business Stakeholder Stakeholders are not getting enough time for the project
IF BOC IT Stakeholders are not getting enough free time
If CAB success criteria is not outlined at the beginning of the project
If CR is not accepted it could increase the duration of the project
If CR003 is not approved by end of Release 2, Release 3 will commence, which includes Data Migration, increasing the effort of addition of new requirements
If CR003 is not approved by January 2nd project will not have an agreed direction and cannot continue; CR003 is to be created during a period with many key resources taking leave which may impact ability to create and approve.
If CRs are required due to solution gap, this may impact the project schedule and budget
IF Customer is not accepting Analysis Schedule
If domain name is not confirmed by 10 Oct, Office365 enablement phase will be further delayed.
If Go-Green plan is not executed in a timely manner, customer may be more dissatisfied and quality may spin out of control
If Hacienda decides to deploy AX7, this will affect the HCM/Payroll workstream as this module is not yet available for this version
If Hacienda decides to deploy AX7, this will affect the Tyler workstream as Tyler is not yet available for this version
If high number of defects are encountered during SIT/UST of SPrint 2b then it may not be possible to complete early planning for Edge cloud scenarios which may lead to less than optimum productivity for the team once we hit the next sprint.
If HP is not able to setup an OU for Microsoft, search online is not able to create clustering for the servers for the on-premises hybrid SSA.
If JCI bypasses the CTM architecture/design to perform administrative functions, the benefits of CTM may be reduced
If JCI experiences challenges in getting servers provisioned in the regional data centers (Frankfurt, Shanghai, Singapore, PDC2), project schedule/cost may be impacted
If JCI experiences challenges in getting servers shipped/racked/cabled in the MDC/PDC1 data centers, project schedule/cost may be impacted
If MGD does not have sufficiently developed User Stories in a groomed Product Backlog, then MCS/MGD will experience difficulty starting the project
IF new P1/P2 risks come up from latest tests THEN fixing takes additional time and ressourses
If no data cleansing activities are not undertaken as part of the programme, then there will be a dilution of the expected benefits of the business case
If prerequisites & arrangements on environments and execution of scripts are not timely available, the timeline will be impacted
IF Rabobank wants to end the Delivery from MSFT
If regulatory approval for Hong Kong MIL and Malaysia MIB is not obtained by mid-October, migrations will not complete as per original schedule
if releases are not deployed on schedule and quality assurance is not undertaken as planned (according to the plan that will be shared by Partner) it is likely that release deadline will be compromised
If some of the test systems are still not available during CSIT, then defects will be found at a very late stage in the programme
If the access to Azure Subscription is not given to Deepak Sharma, he cannot perform his build activities.
If the communication flow of Landing Zone and APS to internet ont work with the Workaround, there will be necessary that Hp re configure the internal network of APS appliance
IF the Mobile App will not run in the German Cloud beginning of April because of dependencies and technical issues THEN likely the customer will escalate this
IF the new SoW is not accepted timely internally and by the customer THEN schedule is endangered
If the PBX Configuration is not ready in the time required, we could not set up the Integration between SfB and PBX/PSTN Infrastructure. Will generate delays in the date of completion of the project.
If the performance of CRM and all the integrations is not tested by TVPHC in a timely manner, then defects will be found at a very late stage in the programme
If the productive environment for Contabilidad and Retenciones is not delivered to us on the required date it will impact the scheduled activities
If the project deliverables do not pass 508 compliance testing procedures, then the Telephone Operator solution will not be allowed to deploy to Production.
If the project extends from the planned 8 week duration to a 21 week duration
If the project in on hold for approximately a month or more, pending completion of dependencies by GOVTT-Contractor Alliance, Microsoft resources may be released from the project. The same resource may not be available once the project resumes which can come at an additional cost to the project due to the on boarding time for the new resources.
If the project team does not have clear guidance on where to focus their time (i.e., prioritized features and user stories), the project may not produce a viable product or may miss high-value features/functions.
If the project timeline "uncompresses", the project duration may increase by up to 24 weeks and project costs may increase up to an additional $1.7M
If the quality of the Phase 1 & Phase 2 CIHS requirements mirror those provided by the Business for the Pilot phase (low quality), then the project team risks having to spend additional effort to obtain requirements with clear acceptance criteria.
If the SMEs Leads are not available to be dedicated 100% of the time to the project, there could be impact to the project schedule
If the standard support implementation in different products do not overlap, the favored solution “Standardization” might not be viable
If the Telephone Operator solution does not meet VA accessibility needs for the pilot release, then the solution may not be allowed to proceed for full roll-out.
If the transition of the OMS portal to the Azure portal breaks or modifies any existing queries, then Nick and Shay will need to review each pattern and adjust for the new user interface
If the VISA processing is delaying the onboarding of AX offshore functional consultants to be working in the onsite team to work with Clas Ohlson stakeholders face-2-face, the AX planned progress may be delayed.
If the WBS and schedule is not formally agreed upon, it may delay the project execution.
If there are any changes to the design decisions or they do not get approved
If this project experiences resource contention due to competing projects/initiatives (e.g., acquisitions, divestitures), project schedule/cost may be impacted
If TN DIDD Titan resource turnover remains high, the customer may have difficulty making planned finish dates for Dev3
If TVPHC runs out of budget, due to ongoing delays, and cannot complete the programme, then the significant investment made in CMP (£33M+) could go to waste, and Microsoft could be publicly blamed for wasting public sector money. Same applies if the system goes live, without properly being tested
If we do not find a technical CRM architect with knowledge about Genesys interfaces the customer will escalate the project and may be step back.
If we start Project close out activities, the customer may get confused about Deal Renewal
IGD assignment
IGD Integration - Language Barrier - coordination with FI
IGD Integration - Language Barrier - technical Analyze of Migration Logs
IGD Resource to be swapped every three months to comply with business guidelines
Immaturity of customer’s long term support organization
Impact on timelines because of new tenant approach, hardware to be provisioned, and mailbox backlog to be migrated
Impacto en el avance de las actividades de desarrollo por dependencias técnicas y funcionales entre PBIs
Impacto en el avance de las actividades del proyecto por salida o vacaciones del equipo de DNP debido a la época de fin de año
Impacto en la continuidad de actividades entre Sprint debido al tiempo extendido de pruebas por parte de DNP
Impacto en la continuidad del proyecto debido a decisiones técnicas y funcionales que complejicen o modifiquen el desarrollo y avance de los requerimientos inicialmente establecidos
Impactos en la gestión de recursos del proyecto por retrasos de facturacion por parte de Microsoft
Implementation of all B2B "Serie" services until end CY17 at risk at Daimler
Implementation of ASE in Azure could increase the Consumption. We need to implement ASE to be compliant with PCI DSS to : - Avoid using TLS 1.0 - Isolate SQL Azure.
Imposibilidad de pase de los reportes a certificacion y/o produccion, debido al uso de fuentes de datos temporales (txt)
Imposibilidad de realizar el dimensionamiento de los ambientes y capacity plan, por falta de la definición de las fuentes de datos finales.
Imran's availability to complete the project from onsite ( dependency on his visa extension)
In case of role model change and its consequences may have impact on projct governance. Cutomer require only Hungarian speaking PjM
In case the WAN links between Soyo and Luanda have no capacity, it can impact the services that depends on synchronization between both sites
In case there is no hardware to support SQL stream, that stream will be put on-hold and when resumed the resources may not be the same
In order to re-assign to other team members the process takes 5 days as per WF. If this is not strictly implemented, there will be delays in the progress.
In our steering committee meeting on 15th of May, MoTC project managers (Hossam Fouad, Ahmed Bekhit) stated their expectations on having a brief reporting structure where they would see the coverage and the adoption of the bot. Currently, it is not in our scope that we shared for Iteration-1. They confirm that it is also a misunderstanding on their side, but insisted to have this in the scope of Iteration-1. If we add a reporting functionality to Iteration-1, we may go over budget and behind schedule.
In Phase 1 of the project, access to various customer ressources was very difficult. The risk is that we encounter the same problem in this new phase.
In preparation for Process Testing, the timetable for completing Norbord-led activities (finalize list of processes and associated scripts) needs to be aggressive and its progress monitored closely.
In team 2 (Azure Components) the delivery is 3 weeks behind schedule. Development is ready but testing is not finished yet. Officially there is only 1 week left for testing and bugfixing. As the test scenarios are quite complex there is the risk that not all test scenarios will be executed succesfully.
In the file servers in the migration scope, there is the presence of folders used not by users but by applications and or FTP clients. The problem is that the customer technicians do not have a clear list of which applications are using these services.
Inability to deliver project in remaining time
Inability to secure an on-site support engineer in the time frame required to support the build phase.
Inability to secure appropriate Premier Field Engineers within the required time frame.
Inadequate test data in non-production which could result in defects not being identified until deployed to production.
Inclusion and Alignment with C2020 Project & Configurator remains to be the highest risks to the project delivery. An action plan has been put in place to address the ISV selection and code merge issues, and will be monitored so that it will not have a negative impact on the project's timeline. Risk related to the C2020 Project has been raised and is considered a show-stopper due to the implications on the assumptions / requirements being captured as part of Project One. Weekly meetings will take place to ensure communications lines are in place, monitoring status, and providing for awareness into planned configurator decision.
Inclusion of Franchise operations
Inclusion of the Jobs AX Instance could have a project schedule impact for the Re-optimization project
Incomplete Customer Solution Gap List
Incorrect expectations on the date of deployment to production taking into account the impact of migration times on all stakeholders
Increasing delay on Stakeholder nomination for DPCD Portals
Increasing the team (mitigation action of risk 8) can cause a budget issue, since new internal/external resources will be added not originally forecasted
India & HK design decision - - Option A: multi-tenant with single AD forest - Option B: Multi-tenant & multi-forest (split the India AD out from HK) - Option C: Single tenant with single forest
Indications of weak Program/ Project Management from client side
Inexperienced customer project manager
Información disponible en el modelo Relacional en formato OCRs
Information exchange between the extended project team members must become more efficient.
Information provided on the questionnaires by the selected MDAs may not be reflective of the entire GoJ organization.
Infosec review both of code and infra has not been conducted after sweeping changes have happened in phase 2, This might bring up issues which can have cascading impact on the overall solution
Infotech has challenges with tracking project progress.
Infotech PjMs not properly tracking open issues/risks/actions/dependencies
Infra Structure activates efforts are not budgeted
Infrastructural Connecivity of Daimler LOB Systems impacts availability of test data
Infrastructural Connecivity of Daimler LOB Systems is complicated and takes long time
Infrastructure Consultant availability
Infrastructure Requirements for Security Capabilities are not deployed in time
Infrastructure security issues are blocking the team to go ahead with environment setup. Impact document has been shared with TetraPak.
Infrastructure Setup Delay
Infrastructure Stability and Access
Initial assessment of requirements for security roles mapping in AX has identified a high percentage of customized roles being needed.
Initial meetings and SAW workshops revealed discrepancy between Trizetto executive sponsorship and working-level on the level of "lift and shift" that this effort would provide.
Initially Starbucks had agreed to provide incremental approvals. Since approvals have been slow to come. They have indicated that at the end of the work-shopping exercise, they would require 5 days for Sr management approval
Initiative planned for two weeks of requirements and three weeks of development and testing (inclusive). If scope extends beyond this timeframe, the work would need to be deferred.
Inna leaving on Aug. 15
Insentra are very conscious of re-ingestion risk and will suspend migrations by end of October if Telstra do not accept data integrity of migrated data.
Insentra is very concerned that they may be required to re-ingest the archives (and journals if we get that far) if Telstra eventually gets to sign off stage on the ingested data. At the moment, Telstra Dave won’t accept Insentra’s certification reports, because he cannot independently validate the accuracy of these reports via our O365 eDiscovery tool.
Instability of services in QA environment in integration and production.
Installation and running of the Bluestripe tool In parallel with the application owner communication, the onsite Msft team needs to install the Bluestripe tool to gain additional server information This tool needs to be installed and run for at least a week to gather the information needed
Installation of Connectors change request
Installation process takes longer due to BWI internal problems
Instead of the MAP Scan finding 1,000 servers to remediate, the new baseline is ~550 and is still a moving target. The reduction is number does not directly correlate to a reduction in scope or schedule, as those remaining we find are the most complex and will require the most effort.
Insufficient / late testing Lack of negative testing scenarii The rate of Code coverage test is very low.
Insufficient effort for Win10 resource to cater for additional 4 weeks in the schedule- Additional effort required to support extended Alpha pilot including application testing
Insufficient PjM capacity / seniority
Insufficient time has been allocated to the MCS technical consultant to complete the rework remaining
Integrating the Solution with different Services
Integration BAT Testing is not yet started . Again this might impact the Go Live.
Integration complexity
Integration dependency with Digital Bank Mobile APP (RGA)
Integration with IVR would not be implemented
Integration with the new Identification tool of IEC (Okta) which is in procurement phase will cause the solution to change/ be delayed.
Integrations
Intel is actively piloting their migration to Office 365. If Intel plans to perform migrations on or before 4/3 there is potential to impact McAfee mail migrations
Interfaces readiness (structures, samples, effective feed) to react to development pre-requisites from Veripark in order to respect the planning
Interfaces readiness will delay the project timelines do to Back End build delay.
Interfaces with SAP have not yet been finalized, thru initial assessment, more than 60 interfaces to be integrated with SAP.
Intermountain's requirement of bulk protection of files that exist within SharePoint libraries
Internal Issue with Customer
INTERNAL: SCCM 1610 Build Out of Support with MSFT
Internet Connectivity solution is yet available. There is a risk of not having solution by 02/06.
Interview Schedule Delay
Intranet
Introduction of new process modelling tool may introduce delays / additional costs due to ramp-up of knowledge of migration of current MS artifacts and expectation of Sonova.
In-Tune standalone mode, or linked to SCCM: Must have discussion regarding implications of each approach
Investigation of the pilot users determined eight new Exchange organizations should be brought into scope to ensure no negative end user experience post-migration.
IoT Investigation: connectivity at farms is limited which may impact the results during stabilization
IP Subnets to be opened include locations outside of Canadian DCs.
-Issue found with AS after the first migration
Issue: Deployment of SailPoint is dependent of the availability for paid licenses in the TEST tenant first. TEST licenses are targeted to be available on 2/17
Issues with connection between Resource forest of Bank VTB and AD forests of brach companies: VTB24, VTB Capital
Issues with SCCM packages being delivered to lab machines that are supposed to be excluded, i.e. Symantec DLP
ISV solution provider, To-Increase. Partner contract is not yet signed for work on TDW project. Required to be in place for ISV to provide TDW with a PoC.
IT Customer Area not ready for preliminary testing for communications CRM - Fraud Prevention Customer's Area
It department has no intention and ability to take the ownership and we need to keep tight communication with many business departments and get recognition from these departments respectively.
It has been announced that BMN will be merged with another Spanish bank (Bankia).
It is currently not clear (to Microsoft) how integration testing with the environment is planned
It is not clear that Azure CDN will be upgraded to Premium versión
It is not clear who/how the data received by the devices would be interpreted. The Connectivity Team has limited knowledge on the data
It is posible that the considered duration of AVL for the project, wont be enough.
It is possible that the budget is not enough for T&E (Architect assigned is located in Mexico)
It is probable that the deputy general director (Narciso Lucero Zuñiga a kind of CDO) will be replaced of the position.
It is unclear how much of historical and ongoing transactional data for FIF, ACC, AAB and M88 will be transferred to ADP Customer Universe. Astra also indicated they will not transfer credit scores for existing customers
IT Lock down for Annual Meeting
It takes a long time to interview the LoB app owners
Iteration 2 Design discussion and sign-off delay due to unavailability of Business users and HPIT team before Christmas shutdown.
It's a T&M but has no work plan nor schdeule dates for interventions.
Its probable a Change Control at "Reportes" module the customer want around 30 reports, at the SOW is not clear how many reports we have to build.
James Glading role is critical on in the MS team, and we do not have replacement for him. The same situation is with Anna-Lee in the MCM team.
JCI is in discussions with BE regarding go.johnsoncontrols.com. The outcome of which will determine whether JCI needs to rebuild the green field domain.
JCS to provide team with Azure subscription for duration of project.
JH/Manulife has requested for timeframe when MS can address their concerns regarding ASE - to provide a specific IP range that they can open firewall for or an alternate solution that complies with Manulife security standards.
Jian Sun on leave from 11 Dec - 9 Jan 17.
JMR depends on multiple outsourcer resources to tasks implementation
K3 co-development details as yet unknown and may not satisfy 100% of BESTSELLER requirements.
Kaiser Permanente acquisition approved and will likely move forward. Some risk to this engagement given KP is moving to O365 as well. Will need to assess as the deal matures.
Katalyst migration needs to be finishd before end of KPMG FY
KB quest (MCS vendor) is working along with Kodak for the project . KB quest is taking care of the Sharepoint solution with KIAS ( Kodak Info Activate Solution ) while Kodak works on the scanning part of the solution. The vendor from Kodak might have a business trip in the near future and might not be able to travel onsite to customer premise and this may cause a delay to the schedule.
Keep financial elements under control if go live of the project will move from Dec 2016 to Jan 2017 plus costs associated to some gaps in scope plus business re-engineering activities (architect solution) not budgetted initially.
Kerrie Stevenson is forecasted to underspend 106 hours at 30 June 2017.
Key customer resources not available for project tasks
Key MCS resource leaving.
Key resources engagement - Some key resources are working on the project since almost a year and may ask to leave the project
Key SME resource involvement in developing the PoC: Based on the business scenario for PoC, significant time commitment might be required from ENB SMEs.
Key stakeholder/influencer demanding that modern app mimic design decisions of old app - will have impact on configure vs customize
Key users availability on time for analysis sessions which might impact the time and cost
Key users availability on time for FRD orientation sessions
Keyman Risk
Kickoff and sales-to-delivery handover meeting showed that there might be quite different understandings of the project scope (BMW expecation vs. EDAG expecation vs. PreSales Architect vs. SoW content).
Knowledge transfer minimal
Knowledge Transfer to Help Desk pending
Known Exchange 2007 bug may recur in the future causing a store crash bringing all databases down.
Komatsu(Quarica) may not prepare user data for inputting MIM construction.
KPI required by the customer are not relevant enough for Azure configuration. In the performance KPI delivered by the customer there are number of active users however not concurrent users. This Risk is related to Azure Consumption problem
La actualización del flujo de cancelaciones y estados intermedios requiere la funcionalidad definida por solución a construir en un "Adecuación Cancelaciones CFDI 2017".
La solicitud de nuevos requerimientos, durante la ejecución del contrato podría impactar el desarrollo de los entregables programados.
LAB / QA Environment Dependency
lack of aligmenet between the BS brands means that a significant OCM effort is required.
Lack of alignment with approach for moving applications to the cloud - misalignment between: Starbucks and Microsoft Internal Starbucks Internal Microsoft
Lack of availabilities from key AXA stakeholders (applications owners)
Lack of availability of bank resources and access to relevant 3rd party resources. The bank has assigned key points of contacts for the core delivery functions at Governance and Programme Levels. This is part of the program/project delivery processes - i.e. highly agile and iterative planning, organizational structure and RACI. For DWP Design Complete, we have successfully mitigated this. Moving forward in the engagement, we will actively mitigate. We continue to proactively planning at the right level of detail in each workstream so as to manage critical path. Our next to-do here will be to investigate if these will change after 'design complete'. Check-In 19th September: mitigation plan is still accurate.
Lack of Azure deployment, maintenance and support processes to the Claro team
Lack of business led requirements and decisions
Lack of clarity and alignment on customer priorities within the bank will mean that DWP stops after 'Design Complete' - 'flying under the radar' and 'need to sell the DWP implementation in order to get it funded using a credible light-touch plan'. We now understand that a major business change programme (a Temenos implementation) is the key IT and business priority in the bank. This will consume banks resources and take priority over most of the new initiatives. The DWP governance committee has given direct feedback that 'DWP will likely not exist as a programme post Design Complete due to competing forces' and that we should seek 'existing initiatives to tag onto or join'. Therefore, there is still a risk with DWP that it stops after 'design complete' as there is no appetite/budget to implement. We are actively mitigating. We have (a) produced a business case/benefits plan to help 'sell the adoption and value realisation'.
Lack of clarity on Product Backlog for n+3 Sprints
Lack of Clarity on Scope for RRM IAM-Lack of clarity on Scope and amount of work being planned. The dates are published, however capacity need vs amount of work is yet to be assessed.
Lack of clear vision of SymPro definition of done
Lack of competenties for AAM Ops resources
Lack of comprehensive testing on the Banks part.
Lack of CR for Scope Changes in Anlaysis/Design Phase
lack of delivery hours
Lack of direction from FIFA
Lack of engagement from Exec sponsor will result in the project not continuing
Lack of ENMAX resources to validate the design
Lack of integration between Program and Project Manager
Lack of knowledge of Azure in different departments of the customer (infrastructure, operations, GCRM, etc.)
Lack of knowledge of process-building activities and structure carried out by other areas and suppliers of Claro
Lack of operational guide for scale out plan.
Lack of participation of all stakeholders in Claro in the adoption of the tool
Lack of processes knowledge by the users or lack of participation of all the areas to define transversal processes
Lack of resources to properly deliver production migration and production failover testing
Lack of rollback procedures
Lack of sales governance and acitivity on the Account
Lack of services for consumption of neccesary data for the view of unique client profile.
Lack of stress testing pre-production
Lack of technical resources from Dynamics Domain could impact delivery as we move forward.
Lack of time to lead the reach of Technological Renewal by the technical leader
Lack of understanding the day to day business on the sales floor, will result in business critical processes breaking during/after migration
Lack or limitation in the participation of America Movil (Claro) applications teams owners to the process of gathering information and testing
Lack or limitation on the participation of teams owners of Interbank applications in the information gathering process and Testing
Language barrier that the person from business department cannot speak english well. This is in the period that the resource Germany is in vacation. He will come back on 9th September, 2017.
Language Customizations- feature in public preview
Language: Since the customer's primary language is Italian, all documents are required to be maintained in both English as well as Italian languages. This will require extra effort and time.
Las consultas Detalladas que tiene el usuario no existen en este momento en el servicio de Explotación
Late arrival of subcontractors. 2 new subco were planned to join the project by Jan 16th Due to delay in the signature of the amendment, the partners could not join te project on time
Late Change Requests could cause some regression bugs
Late delivery penalty, capped at 5% overall.
Late signoff on FRD
Latency associated with authN
layer 7 - unable to have this available in dev which could lead to rework on product
LBE Business Impact - LBE intends to move all of their IT service delivery to Azure and off premise. LBE are also in the process of removing their existing outsource provider and putting in place agreements for new suppliers. This is a significant change in LBE approach to IT service delivery. This project is a key component of that overall programme.
Le Creuset delivery responsibility is not clear and will not be met
Lead Arcitect moved to another domain and country - no formal announcement was made internally or to the customer and a new Architect has not been appointed.
Lead Consultant Rolling Off Project, No Replacement Identified
Lead resource for Tulsa Hub improvements workstream released from MSFT.
Learned on 9/1 that the Onshore Coordinator will be sent home to India on 11/24 (as communicated verbally by GD PM this is directed by Max Long), advised that we have no recourse or say in the decision.
Legacy applications that will be ported to new environment not determined
Legacy browser based applications/Intranet sits may require remediation to work with IE 11
Legacy Data Migration
Legacy Ektron versions Compatibillity with Supported Azure OS Versions
Legal close of merger may impact Day 1
Leidos needs to develop service plan to support and provision resources.
Leidos resource and their commercial engagement - If the Leidos resources will be a constraint for Microsoft and our project activities due to their delayed Defence Commercial engagement (and its approval), then this will hinder our schedule, implementation and migration (which are activities for Phase-2, next year)
Lengthy approval cycles especially from the Security Department might delay progress
Less face to face time with all resources could result in less time and lower effectiveness, for MCS and customer, in building relationships and resolving conflicts.
Level of defined work may exceed 30 June deadline
Level of Project priority accross organization
LGI Testing
Liability Negotiations
License is not yet determined for Staging. Mori-san is working on it
Licenses and Binaries - access to MVLS site for Customer
Licensing agreements not closed in time for build phase
Limitation on ServiceNow application will only accept single policy. Solution requires multiple advanced policies
Limitations of technical options to accomplish the AWS build-out is impacting schedule
Limited ability to provide awareness communications to end users
Limited Access to Network Engineer
Limited availability of Gemeente Den Haag resources
Limited availability of the PERN team.
Limited Azure consumption
Limited internal QA test time for first sprint
Limited number of Club Bruges resources dedicated to the project. Limited bandwidth. Also very junior team
Limited number of resources on the customer side work on the project. Also, they need to be involved all the project activities
Limited time for BBL to prepare Content and Photo shooting by 25 Oct; 9 Nov, and 23 Nov
Lindsay Legler, SSB project sponsor, is seeking funds to extend contract to Jan 31, 2018. This may take longer than current contract expiration date.
Line of command not clear
List of Interviewee Names
LLD of Analysis Environment – MSFT team recommended not to have the Domain Controllers multi-homed as it may give raise to name resolution, GPO processing and replication error…etc
Load on the system will dramatically increase after go-live. We don’t have a good indication of what the performance will be when all users are on boarded.
Logistic: a room assigned to the team will be dismissed next week, not enough space for all in the other room. If we have to work remotely, due to VPN slowness and the demanding integration with the customer and ACN/CDM teams, that will become even tougher remotely, this change could heavily impact the current delivery plan and our ability to match the current delivery milestones.
LOGISTICS: Additional requirements for CMW and Regional Roll-Out (not in scope for current SOW) may impact regional roll-out.
LOGISTICS: BESTSELLER may not fullfill their contractual obligation to execute 6 weeks of E2E and 2 weeks of UA testing
LOGISTICS: Bugs in production due to limited testing by BESTSELLER impacting acceptancece by business negatively.
LOGISTICS: Delay of technical and business go-live due to critical requirements being identified, limited E2E / UAT testing
LOGISTICS: Delays due to too agressive planning assumptions behind time plan for CMW
LOGISTICS: Extending logistics capacity and implementation of new BI2 functionality.
LOGISTICS: Limited training and in general limited knowledge of D365 in the Logistics business may lead to high level dissatisfaction with the solution
Long timelines for decision making across the OPS could hinder current schedule. Need consensus from the business before making drastic changes
Los cambios en la organizacion del Proyecto (Presidente Ejecutivo, Director de IT, Jefe de Sistemas, Jefe de Estretegia y PjM del cliente) y la nueva administracion por parte de Christian San German (Jefe de Operaciones y Sistemas) ha obligado a generar cambios en el Proyecto de Dynamcis CRM con el Posible Riesgo de CONCLUSION DEL PROYECTO
Los procesos de carga estan utilizando el 100% de la capacidad del SSIS debido al volume alto de records transferidos en las cargas,
Losing resources allocated to the project due to delayed start date
Loss of IGD Factory Revenue
Loss of Portal support from Adoxio by 9/16.
Lots of AXA stakeholders to interact with.
Low interaction with the Business Users
Low migration throughput
Low performance of the modern version in production due to high response times of the Poliedro Enterprise services
Low quality of the development indeed the solution has been deployed in PRO with little or no testing is causing lots of bugs that we need to solve as part of the assumed operations
Luanda datacenter may be moved to other location
Luis does not fully support the simplified Chinese
LV's attempt to constantly change scope.
Lync 2013 platform without an administrator actually with issues
Lync Client 2013/SfB 2016 deployment
Machine learning result is the major concern of the customer. 1) at the begning from the hundreds of alarms we choosed 4 kinds of alarm for ML modeling. planed UT is 37 days. 2) now delivery team aware of it's hard to do the ML modeling, choosed contact alarm for delivery. ML UT already run out. 3) meanwhile the customer is expecting more prediction such as life forecast, dignosis prediction etc 4) delivery team is looking into whether life forecast can be implemented
Mail file replication has a low throughput over Internet. Might have an impact on the T-Minus Plan and velocity needed in velocity migration
Mailbox count in original SoW equals 6,200 mailboxes when there are approximately 10,000 in all in scope organizations will affect the original schedule to complete migrations by October 2016.
Main Office Pro Plus team member on Baxter team to go on vacation next week (Aug 14th) during the initial roll out of OPP to the main Pilot users.
Maintenance contract and hyper care support during first days after go live is not yet agreed and contracted.
Major subcon is T&M where project is FF; any extensions that cannot be passed on to client will have to come from MS RR
Malos entendidos por ambas partes / Misunderstanding on both sides
Managed Services can't insure the SLA resolution level required by the contract. They take engagement to treat only Minor customer Enhancements, which 80 hours/month.
Managed Services onboarding may not be completed on time for the first release in production.
Many dependent features are currently in private preview and not available to customers. Particularly SAML and advanced policies which are running the app we were hired for
Many stakeholders with different interests and objectives
Mapfre wants infrastructure information to be included in assessment which is out of the scope which may impact Schedule and Budget.
Marcos Moore está asignado como líder técnico para todos los proyectos que componen el programa y se pueden presentar posibles retrasos en la toma de decisiones, gestión de información, definiciones y reuniones debido a su asignación y disponibilidad. Vale mencionar que tiene otras asignaciones en su haber en BCI con las cuales también debe cumplir.
Mario start date pushed to 7/5
Mark Kenyon is transferring off the TLT engagement to EPG supporting Walmart's data initiatives. The target transfer date is 4/15/16.
Market release for Lynk&Co is delayed, it might impact on project final acceptance and support efforts
Marko is unable to spend time and we are unable to find his replacement. We will not be able to consume the contract value.
Mayor esfuerzo para adaptar las fuentes de datos a partir de la LZ una vez disponible
MBAM Deployment Dependencies of SCCM Deployment can delay MBAM Deployment
MBAM Infra Deployment Delay
MBS team indicated that pilot users migration must be done immediately after Enable.
McKinsey are engaged with BESTSELLER, scope unsure but understood to be process re-engineering.
MCS effort and costs increase whilst waiting for eDiscovery and other Telstra techical issues to be resolved.
MCS involvement limited by CSC
MCS is resource who is authorized to access to customer's staging and production environment is allocated only 8 hours or less per week
MCS resource (consultant) unavailability
MCS resources are only secured until Nov 7 on the project but with the revised project completion date will be 4-6 weeks after.
MCS Spain Testing Readiness
MCTO Operational and Technical IT Readiness
MCTO Requests to extend go-live date to end of Feb'18
MCVP product group does not post any plans about which features will be covered in upcoming releases, resulting in a risk of - not meeting customer expectorations/project timeline - developing custom features which will be in the MCVP platform at a later point (wasted effort)
MDM and Development Strategy
MDM Open PBI Remaining & Scope Creep.
MDM product deprecation. Project completion date and scope not known and clear.
Mediacom may not have enough time to load all data for launch
Merrill Security stance is restrictive. During the review of the Health Check results, Merrill's security lead (Bryan Koch) stressed the need to prevent access outside their normal security policy.
Microsoft Bot Framework vNext Designer (In Preview)- Not Available
Microsoft can not influence Go-Live date of Priva Canada
Microsoft is the prime contractor but responsible for less than 30% of the total planned work effort.
Microsoft is working on the WBS and SOW for Change Request
Microsoft may make a number of recommendations for the Windows 10 build that require technical implementation. There is a limited time period within the project for implementation of these items.
Microsoft resources are scarce. Time is needed to allocate resources for POC and detailed design.
Microsoft Saudi behavior around Premier in KSA putting at risk Regional support framework
Microsoft Solution may not deliver the functional requirements ABB requires for a production rollout
Microsoft team has turned over the CASL solution final build at the end of August and conducted several knowledge transition meetings with BMO development team QA-UAT phase. The plan was for the BMO development team to start owning, enhancing and supporting the solution from September. However, this has not happened and BMO development team has not demonstrated their willingness to own/sustain the solution yet.
Mid Point Workshop not as expected, Client not satisfied.
Mid-Office Architecture FCTG is currently progressing with the D365 and Mid-Office deployments as part of P1. During this project Mid and Back Office cross-over workshops, the project team identified a number of issues and concerns with the current Mid-Office implementation. There’s a risk the proposed architecture is not following D365 best practices which could undermine FCTG ability to achieve the P1 objectives (e.g. single code base, global template, timeline, etc.)
Migration both pre & post Issues exceeding the projected 20% estimated issues
Migration DAS (Legados) -- Pending
Migration's complexity and components remediations of established services.
Migrations in scope list of servers and therefore the final schedule is not locked. Apps that are targeted for migrations are falling off the list and LV/ENMAX are trying to find replacements.
Migrations of On Prem VM to Azure will be not happen
Miki and Luca from FIFA Digital Team are leaving. No person has yet been identified to replace them.
MIM end to end solution in place in time for migrations
Minimizing integration requirements to keep the attack surface as small as possible.
Misalignment between customer expectations on the business side and solution capabilities / release plan
Mis-alignment on project success criteria between project sponsor and project manager at ENMAX
Mismatch in the number of rows when files loaded into the DW compared with the workbook provided by Santi
Missed management expectation on B2B/"Serie" services
Missing binaries/installer/install instruction may lead to more number of In-Place upgrade(7 as per SOW).
Missing capacity in Operations team
Missing customer project manager
Missing information about application compability
Missing Stakeholder Commitment from Celcom
MMAD Schedule is very tight and runs until 30-Oct. MMAD could be delayed on their activities
Mobile app is limited to 10 custom entities. Design may require more. Limit is blocked by licensing and technical lock
Mobile Application compatibility
Mobile Application Readiness from BU
Mobile devices not delivered in time
Mobile interface developed by IGD partner - we can’t get access to that GD partnerà IGD should have resource to deal with this
Mobile policies are not clear
Modern Apps assessment work may not take off.
Modifica all'architettura di integrazione SSIS (trasmissione file)
Modifications in design can extend the timeline of the project if not pushed back or changed in time.
MoJ expectation around pilot vs roll-out
MoJ needs confirmation on MS Products adhering to WCAG 2.0 standards and whether the product has been tested with disabled people
More hours are required to complete the tasks of the engagement
More hours Worked
More integrations are necessary, and many of these are with Hacienda's financial system/bolt-ons
More involvement of MSFT technical team members to support the new ALTEN technical lead (4th)
Most components are well understood but some integration efforts have been time boxed as exact integration requirements are not yet known (e.g. external POS integration)
Most of the process owners express difficulty in comprehending the Functional Spec document, given the magnitude and complexity of information being covered.
Most of the servers are not managed by IT bujt by business areas without IT governance
MOTA Interface Documentation. ​Documentation for this dependency (D391) has not been provided by Ford. ​
MOTC Operational Maturity
Moving of project end date, related with the issue is above
MS Architect is on holiday, leaving the AGB IT CRM Lead to continue to work on the platform unsupervised
MS estimates are predicated upon being able to staff the team in alignment with the project plan.
MS must address skilled technical and functional German speaking resources with European citizen ship and not replacing them during the PoC. BWI asked to replace Juan.
MS provided Tier one sandboxes to HPE for two months at no cost ending May 31st. This time has expired and HPE has not procured these boxes.
MS Resource Part time availability
MSBI/NSR application compatibility
MSFT requires Access to Tier 0 and Tier 1 for Digital Consultant to be able to have the access to AAD Connect servers to complete the Enablement Phase of the project
MSFT staffing
MSP Maturity and Complexity and has a gap with benfica requirements
MTN Project Manager enpower and experience
Multiple administrators having access to single Intune tenant
Multiple enable phase will have to be conducted to ensure that all combinations of source and target are tested and configured on our factory
Multiple Microsoft Services groups are working to deliver assistance to the DODD
Multiple references to IDD and IRD milestones in the plan may lead to multiple people interpreting the plan in different ways
Multi-Vehicle Parameters – did not have all the parameters
MVP's functionality will not be ready on time
Native integration between AX and CRM, CDS solution not yet available
NCC report & timelines to make needed changes
Need - a full time CRM tech lead to execute DM workshops, Integration Workshops, writing TDDs, and support any CRM technical issues onsite raised by Farmlands. Vivek is taking dual roles (focus on Technical as this is what he is onboarded as. Or we have to back fill him.
Need a full time CRM tech lead to execute DM workshops, Integration Workshops, writing TDDs, and support any CRM technical issues onsite raised by Farmlands. Vivek is taking dual roles (focus on Technical as this is what he is onboarded as. Or we have to back fill him.
Need additional hrs. to complete project delivery
Need app dev technical leadership on-shore
Need for more time to finish the work
Need lab machines for each variety to test the 1703 Task Sequences against for BIOS testing
Need signed DPA agreement between Coke and MSFT to enable hands on keyboard to allow consultants to build and test
need support from outside of customer organization.
Need to identify the 5 models that will be used for phase 1
Need to wait for Identity readiness items to be completed to start AAD Sync
Need to wait for PC Refresh to complete to start velocity migrations
Negative feedbacks after GO Live
Negative press report/video regarding WA ESD Tax system and end user concerns - A Washington based News agency has published a video/report with regards to WA ESD Tax system issues and end user concerns Though the video/report doesn't point anything negative about Microsoft, the article mentions Microsoft by name and the contract details including the rate card and Statement of Work
Negative user experience if applications break that we did not anticipate.
Nestle waters Egypt: AX Build process
Netas, being a new partner for Sonatrach and a new team being brought into the project, does not have the full context of the customer environment, goals etc.
Network
Network Assessment
Network bandwidth requirements and the uncontrolled usage of services
Network capacity to support the new services that will be available through O365. Wifi in Portugal central buildings and stores WAN for stores in Poland
Network change (ECC) not ready by 17-Dec
Network change (ECC) not ready by 17-Dec (PC Track)
Network changes could take a while to be implemented
Network conflict IP network ranges between countries. AD consolidation requires exclusive network IP addresses to allow communication between the sites.
Network Connectivity
Network connectivity requires approvals / implementation to standup the Dev/Test/Prod.
Network Infrastructure across GDC and Skyband datacenters is 100 MBPS, this may affect Recovery Time Objective (RTO), AD Replication & Mailbox Migration timelines.
Network may cause poor performance experience
Network topology not final versión till June 2016
Networking: Current Remediation and Enablement activities need review to keep alignment with O365 recommended practices
New briefs deployment in Claro during the month of July about making changes that require development in the modern version, which affects date of deployment
New CR required by the client and needed to be worked asap but not yet funded or contracted 24/2 srb completed
New exciting features requested by the customer and not very clear if a CR will accepted by the customer.
New IDM requirements (Authorization and Centralized Management of Terms and Conditions/CASL for ALL of the City's services and applications), may impact overall target schedule for December 2016.
New issues in production in the integration with ASCARD and post-production pilot
New Management Team and Stakeholders require ramp-up time
New operating system will require end user training as there are some significant differences from currenlty deployed OSs
New people involved on project
New plan established with new technical leader that could imply more sprints of the estimates
New Product Owner expected as Karen Hudgins transitions off. Additional project manager coming in to support Requirements BA, who will be staying actively engaged
New requests outside of scope
New requirements appear to be forthcoming from CIBC. These need to be managed, otherwise could affect costs and would put timeline at risk
New requirements being identified through design sessions may impact release schedule.
New SCC CIO wishes to be confident that the facility storing data is secure and that the country in which it resides does not pose unacceptable risks to Somerset (i.e. jurisdiction etc.)
New SOC requirements
New ULID Design Change Requests
New Version of the migration tool has to be rolled out until 31.10.2017 (see comments)
New work sold (NWS) leakage
Nexus has problems with the script of migration of data that Nexus developed.
Nintex installation not done
NM effort more than anticipated for data migration, data warehousing and accounting for TX design/development completion extension.
No Account Delivery Executive Assigned for this Engagement
No agreement on how the co-development will be delivered. K3 wish to retain sole responsibility for the final product functionally and so BS requirements may not all be included. K3 standard product development uses an Agile methodology to deliver product enhancements. Using this development approach creates a risk that the final functionality is unknown until development is complete.
No alignment with larger ZF architecture projects (Hybrid/AD)
No antivirus available for significant number of XP computers in TC Jugoistok.
No Change Management plan in place and the current project resources are lacking knowledge around how to do good change management
No clarity of scope after deploying the Government Gateway
No clarity on post production support can lead to post production issues getting pushed to the current implementation project team
No clear response procedure for migration failure
No common ground for collaborative working between the teams as DWP have JIRA/Confluence and Sitekit use VSTS and Sharepoint.
No cost information for storage
No decision on when the Wave 2 training will commence.
NO definition for DWH
No Developer assign to Fiducia/development task
No documented Strategy to aid in making major architectural recommendations.
No exec stakeholder communication We are not included in the communication to the KentCC execs. The KentCC program manager does neither share his status reports etc. with the MS team nor does he align them with our reports. Issue tracking does not seem to be important to KentCC program management.
No existing NTU Click Dimension resource.
No hay seguridad de tener la ultima version del desarrollo ejecutado por bSide en Explotacion 2
No L1 analysis
No lead time for fixing defect during SIT & UAT as all activities will run continuously.
No MIM Consultant in the Region is willing to travel to Pakistan for extended periods.
no overall Governance in place at TK; all Business Areas/AG on the same level
No PjM hours remaining for the project
No plan to consume the entire budget.
No program mananger assigned to the prepare to run
No remediation effort for offshore developers in plan. Adding that capacity will result in the actual effort required for the offshore development
No representation from HAs in workshops, may impact decisions and adoption
No Resources in the stores, SO, CSC or Pick-up points are assigned to work with the project, hence it takes a long time to orchestrate and gather information
No response from Robert on multiple e-mails that have been sent to him over the last two weeks
No Rich Co-Existence (free busy) will lead to bad user experience
No se tiene clara la estrategia a seguir con el producto y por tanto no se están consumiendo las horas on-demand
No stand-in for the solution architect from the customer side during the three weeks in October
No Tier 0 Environment avaibale for real life testing & deployment.
No time to change before roll-out takes place. Due to the significantly Shorter Timelines in Need 4 Speed, there is much less time for the local entities to change the contracts they have in place with their customers such that these will comply to the possibilities of the Microsoft Dynamics AX application (GlobAx Template).
No training plan is developed for users, and they are unprepared to use the new solutions being delivered
No user adoptation due to poor user experience, eg. excel documents with macro's (none supported) may not work.
No user adoptation/ frustration for Office Online, Sharepoint and OneDrive due to low/missing added value compared to today's solution (I can still do my job, but have to learn new processes, but no new value added)
No way to get paid for most completed MAP scans, as customer does not consider those assessments as complete, nor will many of these be used in actual disposition activity
NOC connection to DC: internet and IPVPN connection between Ejada offices and STC DC contractual agreement has been delayed.
Non availability of GD/FTE BizTalk resource
Non availability of resources for Onsite Consultant Role
Non Availability of Resources. The resources that are currently aligned for the project might have get pulled out of the engagement to be aligned in other engagements
Non-alignment of the input file formats to the agreed format as in V&S document (Column names and headers match) can be a significant impact on effort and schedule. This is a top risk item for UAT, since format misaligned can break the flow and raise issues. For example, 1. Material Master 2. E&O 3. MyPRS 4. IGSO 5. Eiffel 6. LCM 7. BOM
Non-availability of DI resource (i.e. Sumit) may lead to delay the end date of the engagement.
Non-availability of the resources caused by a non-existing plan for each one of them.
Non-standard Contract Terms Regarding: - IP Ownership - Open source - Residuals - Redistribution rights - Data Protection Agreement - Indemnification - Liability - Warranty - Non-compete Use of any Work Order (WO) Type besides Type 1. The Customer or Partner Master Agreement is non-standard
Norbord will need to identify an operational support process, along with associated roles/responsibilities, to support AX post go live - otherwise, the transition from project to operation will not be effective.
Not a Dynamics AX 2009 Upgrade
Not all positions on the project are full filled yet
Not enough time to run framework migration and server migration testing activities
Not formal COS known. Neither the customer nor internally.
Not getting feedback from Customer Project Manager who is the point of contact from Mapfre side which might result into delay in Schedule.
NOT getting the relevant stakeholders on the meetings
Not having enough network bandwidth for DR site both with instution data center and internet.
Not having the resources required for the implementation of the active directory on-premises according to design.
Not mature customer organization
Not planned / executed in advance schema extension and domain preparation
NPA has shown, that there are some MOL sites, where network characteristics (like latency) are not optimal for realtime traffix
N-tier app selection
Number of developers (45 FTE over all suppliers) lead to coordination problems
NWS push
O2016 Readiness to deploy to limited HHS reps
O365 Customer Readiness
O365 Customer resourcing
O365 E5 License
Obtain the Green Signal from AIA Management
Ocidental Licenses
ODB Enablement not allowed due to DPPO Approval is not signed till Jan 9th
ODB Enablement not allowed due to Security Approval is not signed till Jan 9th
Office 2007 runs out of support after October
Office 2016 deployment (CLP Task)
Office 365 apps limited experience in web browser for unmanaged devices
Office apps (TAMS) delay
Office Client (2013 / 2016) must be enabled with modern auth. Legacy versions must be upgrade to meet the minimum requirement with AIP
Office Client (2013 / 2016) must be enabled with modern auth. Legacy versions must be upgrade to meet the minimum requirement with Seamless SSO
Office Pro Plus - Deployment a. We still need a view into this effort and what has been done. In looking at the notes, it seems this effort has been worked on for a number of weeks. We just need to know what has been done and what is remaining so if we need additional assistance from the MSFT teams, we can get the teams involved as soon as possible.
Office ProPlus 2016 may not be compatible with existing macros/add-ins. As UNIQA will deploy Office 2010 and Office 2016 side by side and keeps the default file association to Office 2010 this is a unlikely scenario
Office ProPlus BIF funding expires 31 March and is not to be complete at that date.
Offices in Bombay House are being shifted for renovation.
Offshore resource levelling is not done and there are significant peaks and troughs in the plan for offshore dev resourcing. Levelling this resourcing will result in increase in the actual effort required
Offshore team availability during the Christmas period
On Novell server we have PATHS with length 256 chars, which is not supported on Windows systems. We are investigating how to find a workaround on this probable issue.
On prem environment to be assembled and installed by the Customer
On the existing contract, all the days planned for vNext will be delivered end of March == The amendment must be signed before March 31.
Onboarding IE11 Resource
Once the initiatives are approved, we need to have the team ready to start the Rapid Prototype implementation. Have already given early heads up to IGD MA and DI RMs about this engagement and requirement. Have raised the GRM requests per process. Possibility of resource not being available for these implementations from remote, will lead to delays, over runs and CSAT impact
One Drive for business not included in current Scope, but customer is requesting
One Drive for Business scope identified in planning period at 2 TB, however the new customer estimate is 14 TB based on growth patterns
One of our Technical Leads is about to shift role within Microsoft soon ADE has recently left MS and there will be a transition period with an acting role One of our Consultants will terminate our collaboration due to tax implications
One of the conecting system (Remedy) have been implemented yet. MS could not prepare connector with this system. Risk is escalated to project sponsor
One of the team members (Javier Campo - Consultant) is assgined to another Project, so he only can work in this Project 1 day per week, so this chhange have impact in the plan of delivery documentation.
ONE requires Microsoft to manage the unformatted data generated by Success factor in 4 data files with unique primary key, 2 data files without unique key column present and 5 reference files (confirmation awaited on the reference files by next Friday by SuccessFactors team)
One-time replication of SharePoint 2010 servers for all environments using Azure Site replication although it is not supported for implementation of Disaster recovery of SharePoint Server 2010 server.
On-going tuning and increment requests regardless the requirements freeze deadline was imposed a couple times. Directive freeze line from SC: • Requirement freeze=Jul 2015 • Requirement conclusion=Sep 2015
Only 2 Ford Resources remain from the original team (3 years ago); therefore, history of great partnership; good will may be at risk as we leave.
Only surevy available at start of project is Journey Planner
OnPrem rescope required to address the customer need for a new tenant to address a Merge and Spin
Onshore Technical consultant position is not yet staffed. This role is critical as in the absence of onshore PjM/Architect, this person would be driving all discussion & client coordination later in the project
Onsite delivery requirement delivery getting delayed.
Onsite Functional Consultant effort being planned for PMA
Onsite Presence
Onsite Tenure of the Lead Functional Consultant coming to an end on Dec 02nd 2017
Open clarifications against the NetApp team prevent the design phase from being baselined and could impact the Build phase
OpenClinica workshop/session didn't happened as per original plan. Need to have this session & respective SME in the 1st week of Design/Planning phase.
OpenText (DTAG Archive Solution) cannot currently use MAPI/http. Their documentation indicated that they could
Operational Readiness (ability to staff/train operational support)
OP-OP Wave 02 which resulted in accidental content loss across 58 Sites during migrations. The sites will have to be re-provisioned and migrated in the next wave 3. Concern that the project schedule and costs may slip.
Oracle license potentially more expensive to ENMAX on Azure VMs and delay migration, reduce the number of apps/servers migrated or lead to churn to try and find replacement apps/server to migrate.
ORCPS is reviewing the unique ID number to include new non-licensed professionals which might represent a scope or design change. This analysis is being performed by ORCPS and a provider (Innovative) which is helping them with the database normalization. On Monday 29th they will discuss the new professional identification method. Based on the results of this meeting, some changes might be necessary to adapt our development.
Original timeline has changed but OCJ expects due date for March not to change. Additional issue is the fact that some staff will be going on leave during Dec and a Company Office closing time from Microsoft is from 25 Dec - 1 Jan
Original Project Management hours likely to be burned out by week ending August 18th
Original SOW estimates and resource provision are inadequate to deliver the solution in terms of workload.
Original Team members assigned to the project have already been informed about the delays and most of them have been dispatched to work on other projects. Me will definitely face struggles to get the original team members back on the project.
ORP/Service provisioning capacity bottleneck
OTE NatCos consistently missing own deadlines which results in required increased flexibility from MS specifically in terms of resourcing.
Our developer lead is rolling out of the project this week and moving to US for another position in MS, thus resulting a resource shortage, possible loss in technical domain knowledge, and possible customer dissastisfaction.
Our partner – GFI – is saying that they need more money to complete the project
Our partner Istone, which has 5 resources on the project has recently scored a large deal and are therefore expected to remove key resources from our project (has partly already started)
Our scope and schedule may not have accounted for the architectural guidelines, dependencies and rigor of process / documentation. Several of the assumptions in our SOW may not be accurate based on the business vision and architectural requirements a) Solution to be plug’N’play model – No strong coupling between any component of the solution including the Hub. b) Geared toward emerging markets in Asia (India, Taiwan, China to begin with) – High volume of businss and Low Cost of Operations & Support c) Should support both Commercial and Clinical (Adhoc, Structured) aspects of the business. Ability to onboard new platforms without significant change in the architecture.
Our SOW is non-deep in the scope and many technical aspects so we have to work in the project with no 100% clear boundaries.
Our SoW shows a 1-year post UAT support in timeline section. This has to be removed by raising a CR
Out of scope items list has been shared with the client but they are not in agreement with the same.
Out of the box implementation doesn't fit Priva Canada business requirements. Enforcing AX Customization, for which this project approach was not designed.
Outstanding Current version of Siebel being 8.1.1.11.0. Microsoft Exchange 2013 is certified to work on 8.1.1.14.0.
Over run risk
Overcomsumption of RR vs project progress
Overly aggressive LV PMs burning out MCS resources
Owner to workstation affinity is not optimum
P1 Release to Customer are impacted due to some major releases to customer. P1 issues cannot be sent as an emergency patch when Major release is in UAT. This is impacting the response time SLA
P2P implementation timeline not yet fixed, only tentative for Sept-Oct. Now it is rescheduled for mid November.
P2W - Demo 1 : Major design changes
Packaging of Skype basic is included in the project. But now Teams can replace Skype
Parallel Run - Load is too high for Farmlands to perform 3 parallel runs for D4 for statement run.
Parliamentary elections
Partner and Customer Transactional Data Validation will delay UAT, which will put Microsoft budget and contract agreement under pressure
Partner contract with the original partner has to be closed per transition discussion. The funds from the partner component needs to be channelized to the MCS work.
Partner developers allocation and performance is not the one expected.
Partner IN2 is using open source components during development process and some of them are planned to be deployed in Production.
Partner payment schedule is monthly/time based rather than milestone based and we don't have penalty clause for timeline non-compliance.
Partner resources
Partner Schedule adherence Risk to the overall Timelines It has been observed even during the bug fixes to production that the timelines is not completely adhered to.
Partner Skillset issue during Build phase
Partner Tieto being too busy with the project to be able to do the SAA activities with us
Partners cannot be provisioned on time against the schedule
Partners' non-commitment to the agreed design
Password replication issues for the extended Active Directory environment in IaaS due to existing problems in the on-premise environment of Kroton Educacional (pitagoras.polo.com.br)-As AD RAP report submitted by Kroton
PD_Decom 6: Milestone Delay
Pelco users in Office 2007: not compatible with SE Security requirement. High likely to delay start of Velocity Migration to update these users
Pending CR will change the project timelines
Pending decisions to be made by the City on what services to offer via the ADX Self-Serve portal, the information that should be available via this portal and the UX.
People are new to Agile
People risk
Per Fiserv, Loan Services, RDC and AllData will be replaced by other business channels (Retail Online, Access Manager, ACH, Business Mobiliti/Online, Card Services, Wire Manager, Prologue, P-Cycle) of Precision; Architect & Commercial Center of Premier. If the above change does not get approved before 10/26/2017, Release 4 and 5 effort hours will get affected.
Per S'Pore govt directive, CPF needs to reconsider offshore connectivity
Performance and especially search related data refresh delays might deteriorate satisfaction
Performance improvements - Microsoft team is focusing on the improvements of performance based on the code optimization. However that may not produce the greatest or desired output/substantial improvements as the performance bottleneck could be in other areas such as poor implementation of business logic, infrastructure etc. Microsoft team requires substantial support from WA ESD resources including understanding of business functionality, re-writing of business logic, infrastructure improvements and end-to-end tesing to implement substantial improvements
Performance testing approach is unclear (TQA Finding)
Performance Testing Resource
Performance TOPS in Analysis & Design has cast serious doubt on their ability to develop the solution to an acceptable level of quality.
Performances : No contractual commitment
PFW Forecasting according to the GD model requires the Number of Applications and the SKU per application. Both factors are currently not available for AHS and may not likely be for the entire project (model is WO is flexible and financials in CompassOne is designed as first $500k and after $500k up to deal value.
PFW5 have negative budget impact
Phase 1 corrections
Phase 1.5 of the project is occurring over the summer when many people will be on vacation.
Phase 2 / 3 may impact our timelines in terms of queries / any code branching / features to be developed
Phase 2 approach - customer plans to follow same procedures in phase 2 that caused issues in phase 1.
Phase 2 Timeline Finalization not Complete currently not finalized and is being worked out with the vendors and internally. Production code has to be stabilized for Code development for Phase 2 to start
Phase 2 timeline is under pressure.
Phase 3: There is a risk of delay due to: - Customer maturity - Customer business process readiness - Customer availability (for example Commercial department) - Limited number sessions and 3-hours session duration may not be enough to capture all the details for some subjects.
Pilot and Velocity Lists a. Need to ask who is working on this and how the lists are being captured and validated. These are needed in about 2 weeks and we need to know if any assistance is needed to complete these lists. We believe these lists are being pulled from your Active Directory. Just need to confirm and to make sure we have the information needed for the migrations. We also need to review accounts that may have been inactivated recently to see how these accounts will be handled and migrated.
Pilot migration – remaining hours may not be sufficient
Pilot Support may not commence on 4th April as currently planned
Pilotmigration: "Anwenderportal" is not available for Pilot
Pilotmigration: Rolloutdatabase is not in place
Pipeline for sprint 7 is not defined. At the moment the available sites are not enough to complete sprint 7 pipeline. Sprint 7 output might be impacted if pipeline is not provided on-time.
PIV Enforcement requires Modern Authentication which in turn requires upgrade to Office 2013 or 2016
PjM (Kitahara) will be absent one week by training from 2017/10/29 to 2017/11/03. - He can't do project closing work between 10/30 and 10/31. - If he is assigned to new project from November, he can't do PjM work between 11/1 and 11/2.(11/3 is national holiday)
PjM and Sol Arch may not be the same resource after the project break.
PjM availability
PjM has only 4 hours allocate to manage this project.
PKI - not determined whether this should be w/in project scope
PKI Infrastructure
PKM  CSB Interface The current testing approach is more of a “trial and error” where the validation rules in CSB MPP are not clearly spelled out. There is no guarantee the packages tested in UAT are exhaustive ones. The daily interface will potentially hit new validation errors subject to the actual content of the package definition.
Plan for RRPS Go Live not detailed
Planning of test phase (customer constraints, availabilty, plan are not yet shared with Microsoft)
Planning slippage due to no bandwith in Thalys team
Playready backend is becoming obsolete
Playready contract is not signed off, and Inside Secure SDK is not available to continue development in Android.
PMA pending contract may impact the Go-Live date for Deployment 1
Political Situation in Cataluña
Poor co-oporation and conflict between resouce suppliers.
poor local connection in remote branches will impact CRM solution adoption
Poor participation of the IT area in the necessary activities to complete server migration
Pootlook CRM Plugin has several reported issues and PG are workign on a fix
Portal not ready by 24/11.
POS rollout in Sep/Oct - business decision
Posible delay to initiate the release, for dependency with a communication flow
Posible delay to initiate the UAT, for dependency with a communication flow
Posible impacto a nivel de usuarios por desconocimiento de los aplicativos que utilizan
Posible impacto en las aplicaciones que puedan tener en duro el nombre o la IP del DC.
Posible insatisfacción del cliente por los tiempos de despliegue de la imagen de W10.
Posible insatisfacción del cliente por los tiempos de remediación de incidentes.
Posible retraso en la ejecución por la no aprobación de las ventanas de cambio
Posibles incidentes con las aplicaciones compatibilizadas por desconocimiento del aplicativo y su responsable.
Posibles retrasos en la ejecución por cambios de prioridades de los proyectos que componen el programa
Possibility of a delay in schedule
Possibility to change schedule due to customer condition
Possible bug fixes and new features may be added to the software.
Possible delay in the SAP Source database from TetraPak
Possible delays in the project completion due to delays in LiDL execution.
Possible delays in the resources assignation due to a lack of information on the current situation of LiDL and SITIOS actions.
Possible freezes during the program execution due that the program is a "Low priority project" for the customer at this period of the year.
Possible operation issues because some forms were deeply personalized and that requires knowedge of the project
Possible revision of CRM data model based on the data dictionary mapping activity currently in progress.
Possibly more units collaborating with stores than the SO
Post Dallas workshop concluded on 9/22 by Domain on D365, new changes are likely to emerge that will push the UAT start and GO live date of D365
Post Go Live activities and change requests need to be prioritized by Norbord in order to effectively plan the limited remaining time and availability of the project team until Aug. 31st.
Post Production support risk
Potential changes on Payments 3.1 regarding the ATG integration
Potential delay on Photo shooting
Potential delay on the Test the build for Azure set up and lack of ability to test hybrid connection including Firewall and WAF due to purchasing
Potential delays in regards to activities and communications around UPN change
Potential delays in regards to required telecom changes
Potential Impacts: Functional Specifications Signoff Prolong decision making process
Potential limitations for high migration velocity
Potential Loss of Resources - If the CR0003 and Phase 2 SoW are not implemented by the end of Phase 1, there is a potential that the current resources may be reassigned.
Potential re-coding efforts associated with Mobile Responsive and Adaptive behavior
Potential Risks
Potential schedule delay due to customer delays in getting pre-requisites (remote access & configuration artifacts)
Potential Scope Increase due to inclusion of new Architectural Element for Marketing purposes: Features of future releases and possible Localytics Solution integration
Power BI integration with SSO and local portal will impact customer experience and delivery work load, schedule.
Power BI Issues in Dashboard UI (Custom Visuals)
Power BI Licenses
Power BI Pro account has not ready so far
Power BI reporting using more than 1 PWA site
Pre requisites required for deployments of CRM and IDM may not be provided in time
Premium Storage Needed
Prioritization of daily activities of the customer services operation over the activities of the project
Problems at BI PROD environment prevent reports data being loaded properly
Problems with production migration in December. The customer has the internal rules not to carry out production migration of critical systems in December
Proceeding with Process Testing on priority interfaces while still completing Functional Testing for remaining components may require multiple regression testing scenarios.
Proceeding with Process Testing without completion of all scripts may lead to a delay in completion of this phase.
Process Toolbox test scripts are larger than anticipated
Processes not aligned and communicated
Procurement lead times for A360 servers will not allow enough lead time to stand-up and test the archive migration process.
Product backlog & MVP
Product team had previously committed to provide an API to retrieve the IP addresses or DSN names of the ASE Management Service and other required backed services by August 2017. We have been notified that this has been pushed back to end of August 2017. As of last week, we've been informed that this has moved to end of October due to issues they encountered that are being fixed. If this is further delayed, it may impact go-live. JH leadership team previously indicated their preference to have this implemented and fully tested prior to go-live.
Production Access: Microsoft team does not have access on production systems to complete server migrations
Production Enviroment missing
Production environment not ready
Production environment not ready for install procedure on the 6th of October
Production HW availability for SfB2015
Production implementation has impact on Exchange and SharePoint in production.
Production re-director and penetration testing will need to be implemented in production by Fiserv team.
Productivity loss due to lack of work
Program Manager transition cannot be done properly and affects the project on the critical path to the first release planned for July 21st.
Programme might be put on hold for several months if solution is not live by April 2018
Project "NEXT" will migrate a lots of W2K3 systems by themselves.
Project Architect working ont the project (Luc VO VAN) is moving to another function within MICROSOFT. There is an urgent need to find a new Project Architect, onboard her/him and transfer the project knowledge from Luc to a new Architect.
Project at risk to complete past new end date of June 16, 2017 because of outstanding issue with users getting repeated requests for credentials.
Project budget was consumed on 17-May, and the additional NBUE funding (3360 hrs) will be consumed by 21-June.
Project contract/budget of V2 ends Mid january 2018
Project could be extended further than Novembre and this would cause further impacts on project budget.
Project could not continue after analysis phase if customer budget is exceeded after fit gap analysis
Project currently under-run against forecast due to holidays so could result in a back out.
Project delays (refer CR01) may jeopardise later stages of this project
Project Deliverables
Project director has called for a halt to start of the App Factory until subsequent LPRs. Start date for subsequent LPRs in currently unknown.
Project duration (35 weeks) could end and the total migrations not be concluded. Due customer delay to provide the target domain infrastructure configured as required. AD MS migration tool is able to migrate successfully but migrated users could face issues on target domain to use the applications and functionalities.
Project duration may be exceeded in February 2017
Project fee arrangement is fixed fee, mixed fixed fee and T&M, or T&M with a cap (not recommended)
Project is currently being rescoped during envisioning
Project is highly dependent on partner resources which are limited
Project Management hours allocated for engagement almost exhausted (6 hours remaining)
Project may be requested by AT to stand down for a period
Project may be stopped due to poor quality of deliverables
Project may close under budget by greater than 10 percent
Project now is suspend by client. All our resource has been released by the end of May. However, if client want to resume the project in future, it will be hard to get back original resource here to perform left work.
Project payment milestones are attached with the numebr of cameras configured which, by the end of the proejct, might not reach the final 600 number.
Project plans not correct and not being managed
Project PoEC is 80%, but the project billed is only 24% till now, the customer payment is high risk.
Project resources are not fully allocated to this project and have highlighted that they will have limited availability to engage on this project.
Project resources will need to be rolled off during the project pause. Resources will need to take on other projects and will likely be unavailable once the project resumes.
Project Schedule
Project schedule (end date) is not fixed. Customer dependencies and approvals need to be managed closely.
Project Schedule dates variance that affects scope milestones
Project schedules are moving into the rampdown of many resource on the project between now and 6/23/17.
Project scope has change from with was in the orginial engagment
Project Stakeholders (contributers) may be unavailable during the Easter Period.
Project Status is conveyed by Subcontractor to the Project Manager on weekly basis via emails and fornightly meetings
project team (including SA and PjM) is allocated to the project up to mid-July (end of actual engagement). It is very likely that further CRs will arrive extending the project but team is now fully allocated on other MS engagements. In this case we won't be able to deliver further activities with heavy impact on customer satisfaction and CR estimates (done without considering a KT)
Project team roles not staffed - Java developers, Performance testers and Onsite Project Manager.
Project termination by Sinara Stakeholders, due to the low quality of the Project documentation and Project team’s coordination.
Projects have high margin resulting in underrun for resources and additional financial scrutiny.
Prolonged network changes and network incident follow up
Proper resources with specific skills for tasks and appropriate clearance level are difficult to obtain quickly.
Proper test environment for IoT stream is missing
Propsod to start SIT 3 weeks earlier than orginaly planned
Protest of opposition upfront the Prime Minister building becoming permanent. Increased security and limited entrance in Government buildings.
Prototype Approval not been given due to "lack of confidence" in Microsoft. Based on staffing changes, limited interface development, gaps in retail functionality and limited or no commitment from MS to address the gaps. lack of a differentiator now that K3 is not in scope.
Provide ATM model Mini to tests and validation of bitlocker
Provide Azure Subscription access to Microsoft team
Pruebas de desempeno incompletas debido a las limitaciones del volumen de datos.
PSKM Reports - Azure Infrastructure is not available
PST File Migration scope is pre-prod only.
Public cloud movement – feature changes
Public cloud movement – known unknowns
Purchase of Binary Tree Migration Service
QA is taking longer than expected
QA testing effectiveness is limited because Real Madrid IT hasn’t provided an environment where we can test all the possible scenarios
QAI source
QH Project has identified that a Technical Readiness assesssment of the Design is required before certain design elements can be implemented
Quality of Production Solution – Given the delay in PTE finalization, end-to-end testing has not happened. Potential risk to functionality if not properly tested. This will require team to quickly triage and resolve during pilot
Quality Problems like - Coding guidelines not taken into account - Wrong connection strings on wrong environments/hardcoded in the code - Excel PW List Keyvault for every environmant in SP
Quality. The deliverables quality not aligned with internal and external standard (UAT).
Que C4C no entregue los servicios solicitados a tiempo
Que el tiempo requerido para dar soporte al ingeniero de Premier no alcance dentro del Budget del proyecto.
Que finalmente no se pueda involucrar al usuario final (Asesor) en las pruebas de aceptación final.
Que las pruebas de políticas de gobierno a nivel de Exchange Online y OneDrive (tecnologías en uso actual en Rimac) se realicen en Producción
Que no se identifiquen de forma oportuna los 50 usuarios que se desplegarán.
Que no se superen las dependencias mapeadas en cronograma a tiempo, permitiendo que se vuelvan críticas
Que Rimac incorpore tablets distintas durante la Estabilización que no se proporcionaron ni consideraron en el Diseño de la solución
Que se continue con la decisión pendiente de cual será el identificador único de empleados para enlazar con Directorio Activo
Que se generen demoras en el esquema de atención de tickets para los pases de los cambios que requieran permisos superiores a los brindados al equipo MS
Query performance issue found on 24-Mar from load test execution, it's blocker issue for subsequent test execution
Questionnaires may not be returned by the required deadlines.
R005 - Farmlands workshop attendees readiness
R006 - Delivery output of the framework of the future solution state
R006 - Impact of new revenue recognition standards
R01: Cannot Integrate SIEM with ATA due to customer's SIEM
R04 - If delay in reviewing and approving the Solution Architecture results in any changes to the code developed (build is expected to be going on in parallel), it’ll impact project schedule.
R32: NTT DATA Target Site has a content DB growing beyond 167GB
RAC data validation may raise issues in code development for RAC components or with MS Data Migration Tools.
RAC development team may have to be diverted to support the Live AWS platform at short notice.
Ragn Sells has asked to not start ANY design activities before the Analysis phase has been completed (with the exception of the Transportation stream).
Ragn Sells is in the middle of a reorganization, key personel/stake holders might not be with the company in the short/midd term.
Ramadan Stakeholder schedule
Ramadan, holidays and summer vacation season will be overlapped with SIT, Training and UAT sessions
Readiness of Local LOB systems for the new CRM infrastructure (successful request / response)
Readiness of the MDM (data warehouse to host citizen data/interface to all the backend systems).
Real Madrid is still pending to decide if the new functionality that provides members with a QR code for accessing the stadium can be available on apps or not
Real Madrid wants to include unique email for users in current solution, which is not B2C native behaviour. B2C allows to have 3 different users with the same email. Real Madrid thinks an email can’t be repeated in different users. This chande is out of August 30th managed scope
Receive with short notice the information to train the "Asistente Virtual" and MSFT don't have enough resources to execute the training
Recepcion´s Services are dependant of other MS project
Recommended Archive Shuttle infra not capable of migrating ~900TB
Recovery plan to deliver Release 1A on time on July 21st caused an over-consumption of budget (resources working more hours than initially planned).
Recursos asignados al proyecto con actividades pendientes en Explotacion Fase 2 Es prioritario para el cliente la resolucion de la informacion de Fase 2 y de Nominas, por lo cual estos recursos aun no estaran 100% disponibles para el proyecto. Se esta trabajando en reorganizar las actividades de los proyectos de Fase 2, Anexo 20 y Fase 3 para evitar atrasos
Reduced workshop durations (1hr per topics, based on availability of CSC resources) may impact educational / knowledge transfer objective of this engagement
Reduction of application migration scope There is risk that the scope for application migration may be less than expected as detailed in the statement of work.
Reed sponsor may react to time spent on MessagingOps tool. May need to adjust CR to reflect 3 days expending effort on the abandoned approach.
related to the export (not in project scope) Due to the size of the archive and capacity and velocity latency of the network the risk is related to the timeframe for the export from PST to Office365
related to the export (not in project scope) Due to the size of the archive and capacity and velocity latency of the network the risk is related to the timeframe for the export from Symantec EV to PST
Relations with all the interfaces involved in the Development and Go Live for Annual Statement.
Release management weakness
Release Manager, a Microsoft FTE client facing with Azure and DSP expertise is recommended in future releases. He also needs to have proven experience in SSF, Agile ScrumMaster certified recommended.
Release Plan / Schedule
Reliance on SAP Corporate resources.
Relieve one team member (Spencer) to another project - AAD team requesting for Spencer to start on Ascendas Project.
Remaining hours can not been delivered because of missing defined tasks
Remediation activities started late which impacts schedule if not completed before the UAT of each wave 5, 6, 7. 5/6 for Wave 5.
Remediation of Network will take a long time (more than 6 months)
Remote Access is not yet fully working - we can get to the Citrix CAG box but not beyond it (HPE requires funding from BOQ to provision access beyond the CAG box)
Removal of iWACS interface from the Prototype Scope means it will be very difficult to prove the quality of the IGD work and therefore be the "go to" development house. Microsoft responsibility for the project will be very difficult if we do not have control of development.
Remove Silverlight from Adenda Services.
Remove Silverlight from Cancelaciones Services.
Remove Silverlight from Megapac Services.
Replication problems between Domain Controllers on-premise and IaaS in Azure by bloquieo of firewall ports.
Report Expectations - Power BI reporting expectations are still not clear on reports. Tech Data has expressed the desire for a great visual design, however, specific requirements have not been provided.
Reporting database server data migration could exced the 3 to 4 hour limit for cutover data migrations.
Reports not being developed impacts deployment timeline
Repsol request re-designs
Reputational risk from Software Selection (two-way autentication missing in the CRMOL but not clearly stated during the SW selection RFI)
Request by Norbord for Microsoft to complete system setups (eg. security, workflow, data loading) within AX may put Norbord at risk of not being able to maintain them in an operational scenario.
Request domain to provide PjM for transition for the ongoing FY18
Required resources not available when Whitestar decides to start phase 1
Requirement changes and associated cost
Requirements for Milestone 4&5 have not yet been signed-off
Requirements: BAT are unclear about what they wanted us to report on.
Re-scoping Content Migration for “Non-Production environments.”
Resource and budget availability to extend project by 2-3 weeks.
Resource assignation delay might impact engagement success
Resource Availability
Resource availability and knoweledge of Feenstra team
Resource Availability due to vacation plans in this holiday season.
Resource availability limitations due to multiple ongoing projects requiring similar resources
Resource burn rate running out of hours before the end of the contract
Resource Constraint: Accounting SME Stretched thin County Accounting SME - Blair is stretched thin with project responsibilities and meetings. He is the primary decision maker for finalizing the main accounts, account structures, review of functional design and review and approval of process test scripts. He is also a major player in all upcoming Testing activities (process testing, functional testing). Due to these tasks and his other duties, he has become a bottleneck for project deadlines.
Resource constraints with Bank resources may push the project schedule to beyond the BIF availability
Resource constraints with leveraging MSGD Developers and ramp up time would directly impact schedule.
Resource Constraints with multiple workstreams
Resource for System Integration on Interface level unavailable, temporary replacement Architect missing, and need for Frontend Lead has risen in priority
Resource Levelling not available at task level
Resource Modification - The Tech Data, data analytics resource was changed. The new resource does not have the skillset at the same level as the previous resource. The lack of knowledge of the current resource is a risk for the completion required tasks.
Resource request has been filed, negative impact on timeline likely​ 18.08.
Resource shortfall due to subcontractor end date not extending
Resources could be released if the time between the end of analysis and sign off of the CR exceeds 15th March
Resources have leaves planned, Ready event also impacting availability. This will affect planned work.
Resources may not be available for revised Go-Live
Resources Tata Steel
Resourcing
Resourcing - Change of Resources
Resourcing - HP Delivery Management Team not properly managing end customer or project. This is being demonstrated through variety of issues and missteps through project
Resourcing constraints at ENMAX could pose challenge due to competing priorities, resulting in schedule slippage.
Resourcing team has not been able to find a suitably experienced Sr. Finance Consultant for filling up this role. Microsoft has reached out to the partners to look for an alternative consultant.
Resourcing will be required to be ramped down owing to continual project delays and dependencies that are outside of MCS's control i.e. BT line set up, FLS development readiness
Restrasos e impactos largo plazo / Long-term delays and impacts
Results of the performance testing is not conclusive.
Retail Holiday Freeze
Retraso en el inicio de las sesiones de grooming debido que los PBIs no están siendo documentados de acuerdo a la metodología por parte de los PO de DNP
Retraso en la continuidad de actividades de desarrollo (inicios de sprint) debido a diferencias de estimaciones durante las sesiones de groomming
Retraso en la revisión y entrega de feedback sobre la documentación entregada al Banco para su revisión y aceptación que impacta la continuidad de la ejecución del proyecto.
Retraso en las actividades de desarrollo debido a la curva de aprendizaje del equipo de desarrollo en el proyecto
Retrasos en el plan de trabajo causado por el no aprovisionamiento de la infraestructura para los ambientes
Retrasos en la entrega de configuraciones que son requeridas de parte de ICE a nivel de administracion de Exchange y que se necesitan para pruebas unitarias
Retrasos en la entrega de los servidores de Cloud Connector
Review development estimate can result in a higher or lower estimation than initial estimation in Proposal due to new insights during design phase.
Revised Go-live date needs to be confirmed
Revised scope of work will involve MS Project team doing changes in CHI's production environment which is managed by Wipro
Revisit the UI/Functions in the upstream flows of Online through a series of meetings in Sep, 2016
Rework for UX integrations once changes and style revisions have been made
Riesgo de no llegar a desplegar los 1,000 usuarios para Diciembre en la que debe aprobarse la Fase 2.
Rischio che al passaggio in operativo siano presenti anomalie residue non rilevata nel prodotto a causa del limitato e improrogabile tempo dedicato agli UAT
Rischio che la procedura di Change Management non garantisca i requisiti minimi del processo (es baseline certa e corrispondenza sorgenti/eseguibili)
RISK - Compressed timeline associated with Japan Launch; impact on testing and training activities
RISK - Delayed Negotiations on WO Amendment and CR for Japan Opt-in
risk #1
Risk for timeplan slipping, as both project initiation, resource onboarding, design, plan and build needs to take place within a very short timeframe for reaching DP3
Risk Model Accuracy may not get to 87% by 18-Aug-2017
Risk of claim by the customer
Risk of delay to project Schedule due to delay getting estimates for integration with Services Alberta MOVES system
Risk of Dell missing Remediation Completion Dates
Risk of insufficient or unstructured SIT Testing
Risk of missing the Data Center closure on 07/31/17
Risk of New Work Sold decrement as a result of WestRock decision to de-scope CDLM and HH&B sites from the O365 project.
Risk of not meeting the customer dead line 1 Sep 2017 due to CPA Architect (Ian) requesting a new change to the current scope which is the ability to search across the Annuity Renewal Dates (From / To as dates).
Risk of not receiving the inflow for the remaining 49 applications from the customer.
Risk of Project continuity in time since remaining hours ara expected to be consumed by 9/Sept/16. The proposal for the remaining work and its negotiation with the customer will not be ready by then,
Risk of reversal
Risk of rework relating to high frequency of change of Shirley data
Risk of schedule delay and increased cost due to customer demand to deliver more detailed requirements, architecture, and design than we anticipated when estimating the scope of the project.
Risk on capability of integrating systems to sync with multiple project environments as during stabilize the testing will be conducted in multiple project environments
Risk on customer dependencies not met on comitted time leading to further slippage
Risk on the customer's readiness for Go-Live (UAT preparation, training, etc...)
Risk Reserve calculation is incorrect, and Risk Reserve is inadequate
Risk that MSFT may not be paid for the initial 1 or 2 Milestones until Q1 of 2017.
Risk that there will be a number of XP desktop/laptops that will remain beyond the Q1 CSA agreement.
Risk that we will not consume the re-invest hours due to delays and/or lack of resources being committed by customer.
Risk to delay the roll-out phase of the project after the end of July since pre-requisite from the client might not be provided
Risk we may not complete Bot Framework / Virtual Agent Build by W15
Risk we may not meet Customer Request to Go Live early in W18
Risk with performance tuning work is not being able to achieve performance that is acceptable to the customer leading to potentially more investment and customer satisfaction issues.
Risk: Adequate time to train the trainers, business, and all users
Risk: Clas Ohlson may move AX intended functionality and features back to existing legacy systems (RainDance, PCMS, Neolane & Cores) to make the AX scope fit the budget constraint, which is against the initial Clas Ohlson strategic intention of moving functionality into AX in order to enable Clas Ohlson business to scale and move into new markets in a faster manner without long-duration and costly IT investments.
Risk: Critical resources have both Microsoft supporting and Entergy supporting remediation tasks
Risk: Environment Setups, Instance Planning, License Planning, ISV Installation
Risk: People Constraints through out the business, inadequate resources to support timeline
Risk: The duration of the Design Phase period (currently planned for 5 weeks with assumed 30 in-scope AX gaps), ranging from Design Phase start until all the FDDs are approved by Clas Ohlson, may not be feasible anymore, as the comparable period and previously observed durations for AX UK Pilot (14 calendar weeks for 17 AX gaps), AX Country Rollout (11 calendar weeks for 11 AX gaps) and AX HQ (14 calendar weeks for 18 AX gaps)
Risk: The E-Com analysis phase may be extended, if the AX/Avensia scope (that Clas Ohlson is willing to financially aim for) is not confirmed and locked before July 31 (for AX) and Aug.14 (for the Avensia), then the AX Design Phase/Avensia Sprint 0 Phases will be delayed in a 1:1 relationship. Complicating this achievement is, that the Clas Ohlson key stakeholders, the Solution Board, is on summer vacation in from July 3 to July 28.
Risk：The source code will need a security scan called SCAS, any finding is required to be fixed mandatory before system go-live. Solution：After we get SCAS report, we need work closely with SCAS team and confirm every finding's solution.
Risk01
Risk-R01: Due to on-going CCR divestiture, CCR sites FTC will not be retracted
Risk-R02: Changes to production sites / environment
Risk-R02: Cross project dependency
Risk-R02: SMUD’s compliance and regulatory requirements
Risk-R04: Baseline FTC retraction schedule goes into end of October 2017 (updated date - Nov 2017))
Risk-R05: Nonavailability of O365 dedicated Service Deliverable Manager (SDM)
Risks of delay of UAT release 1 of SID due to tight time plan and planned for “non-productive” activities
RK02
RK03
RK05
RK06
RMB support process
Rollback plan not available and needs to be agreed and tested
Rotation of key GD resource- GD has requested to rotate back the project's tech lead by the end of the year
ROW EAMER Business Continuity
RS wide integration platform does not exist
RSK#1
Rule engine implementation is not ordered yet, amendment is needed quickly to keep deadlines
Rule engine logic depends on the readiness of the DOS Service (Days of Supply). Currently, there is no clear update on when this service will be ready to integrate with
RUN workstream leadership is not aligned with the project's requirements.
Sabre API SOAP wrapper is not serving valid data for the bot to read
Sagicor staffing capacity to meet project task delivery timelines
Sales department demand changes
Saryp - Customer has not the suscription for use Azure and this introduce delays in the project.
SAT must to deliver the format change request requirement (Oficio) to Microsoft can advance in the change control process
Saudi Post project owner is overwhelmed with project delivery, and customer onboarding activities and doesn't have capacity the right focus for priority items in all areas.
SAW Attendance
Scalability is one of the key success parameters for the engagement as per the contract, strict requirements related to scalability has been listed down in the contract. Performance baseline is not conducted / assessed even though application is going through the Phase 2 development cycles
Scania will only send one order through the system during the operational support period.
SCCM not presently utlized to deploy OPP. Utilizing portal for self install.
SCCM Upgrade to 1706
SCCM was deployed into Production instead of Test to allow us to continue testing with 1E
SCCM1610 supports of Win10-1703
Schedule
Schedule – Current CIBC Project plan indicates that SIT testing will be conducted Jun 29 – August 7th. Current Build Complete date is scheduled for July 12th and current Test Strategy from CIBC calls for June 15th start of SIT testing
Schedule – Indicated timelines for testing by CIBC (18 weeks) presents significant challenge in meeting CIBC’s communicated end date of October 4th
Schedule compression: initially, the project was planned to last 3 months, but now the project length has been reduced to 2 months.
Schedule delay due to Addressing the AAD Connect Configuration to get a clean configuration - AAD Connect has preferred servers configured, however the entries there are for the EMC root forest DNS name, the 2 DCs in the Dell forest configured behind that DNS alias are responding to requests from the AAD Connect server and are returning a referral to a GC, which happens to be behind a firewall and unreachable.
Schedule Delay due to Dell Remediation Task of Network/Firewall/Proxy Remediation
Schedule deviation
Schedule Extension
Schedule is at risk due to FDD Lifecycle Process
Schedule of post Go Live activities has little margin for delays and will need complete alignment of project team resources to complete by the start of Month End Closing (Apr. 24th).
Schedule ramp up and speed of migrations are very slow which is delaying project end date
Schedule risk due to delay in onboarding partner
Schedule slippage due to Feenstra resource availability issues
Scheduling of migrations needs to be managed closely as this could have an impact on the schedule
Scope - There is still a risk that the scope continue to grow because not all the users stories where fully rewied during the new scoping phase in Nov/Dec 2016
Scope and vision document sent to customer got negative feedback about this deliverable.
Scope Change
Scope change from ZTI to LTI
Scope Changes
Scope changes and ambiguity regarding the approach to implement
Scope Changes requested by DCP could have schedule and/or cost impact
Scope discussion & contract revision to be conducted with the reduced scope
Scope for Obsolescence workstream is not defined
Scope has changed, very few expectations from MS team
Scope is unclear due to sourcing strategy change
Scope is vague in the contract, so there will be obstacles in closing the project.
Scope Management - Re-casted timeline has to be formalized in a Change Request.
Scope Management. ANSA's project is scoped with no Gaps. The five insdustries need to adhere to a series of common processes. There are potential differences between industries that can force a customization.
Scope not necessary at this time for client
Scope of L2/L3 support contract unclear, unclear ownership of training on the core MSDP IP solution for cronos
Scrum Master training and certification for all PJMs planned but will slip as procurement process and budget request
SDL Approach - Prototyping
SDM has transitioned out of role and miss the 360 view of customer
Se identifican dependencias para probar nuestros componentes así como coordinación con el team de Explotación para la liberación y KT con Operaciones
Se identificó que las pruebas con PAC/UAT probablemente no se podrán realizar por cambio en prioridades y falta de respuesta del usuario
Second Engagement with the customer, no previous big projects but small diagnostics phase
Secure licencing for all users to be able to roll out all users, some lciences allready available
Security and Testing Lead roles can be a FT requirement at overlapping points in the project. These are currently assigned to a single resource. An multiplying factor for this Risk is the fact that security requirements are not being actively collected by the teams.
Security Baselines
Security blocking issue for Call Centre (CC) migrations would extend project end date.
Security Check of Consultants
Security Concept not adequate
Security policies preventing the extension of AD onto Azure will have an impact on the application migration onto Azure
Security related findings, in particular, absence of database column encryption for PII data, if not addressed, can result in reputation and financial cost to MS
Security Review Fed Ramp review – Unable secure time with CISO to review Security
Security Scope in flux
Security sign-off of Proposed Solution
Security SME has a personal emergency which has delayed the review. Last minute review comments could potentially destabilize the build.
Security vulnerability
Senior Consultant Availability
Senior resources will be reuired
Server Builds take 3-4 weeks
Server list development and validation delayed
Server performance analysis revealed that we cannot use the planned A8V2 servers because of very slow Video Analysis application performance compared to F8/F16 servers - which increases the Azure consumption costs
Server Scope lower than 500
Servers are not available next week for start the deployment of VMs
Service Activation Date
Service scheduling algorithm is very complex.
Setting appropriate expectations for PoC outcome: This project is unlike typical delivery project in which the deliverables are fixed, scoped and defined – success on this project is not a foregone conclusion. Microsoft, FFS and ENB are setting out on an active discovery project where some balance of expectations, discoveries, and compromises will define the output.
Sever 2003: Customer Project Team
SfB desktop client & companion app and user experience
SfB online product roadmap
SGS is spread across 60+ countries and 140+ datacenters, complexity invovled in discovery and co-ordination across locations will impact schedule
Shared Mailboxes, send as feature cross premise is unsupported.
Shared PCs - Conditional Access blocking access to MS tools to subsequent users
Sharepoint – CRM Permissions insufficient.
SharePoint 2016: Timer Job Issue can't be solved by a Product fix.
SharePoint Farm has a dependency on Networking for DR in Plano
SharePoint workstreams continue to fluctuate due to customer requirements and DuPont uncertainty of the sites, resources that will be either sold off or moved to separate tenants.
SharePoint/Collaboration re-planned. A CR has been crafted to update the strategy and approach.
Shifting schedule & requirements is stalling for OD4B migration work. The PG for OD4B has made a decision to disengage w/ DXC till they're provided concrete on schedule + requirements lock.
SI Architect Tiberius Radu is leaving the team in January.
SI2M team have not enough bandwidth to handle / follow correctly the remediation plan and which could create end user impact (degraded user exp)..
Sign off from customer on UAT
Since Honeywell Migration have multiple sources there is chance that termstore GUID are duplicated and Fasttrack team have indicated that they might not do the Managed Metadata Migrations
Since the design phase for this project has not been completed, and the information required for the SW depends on this phase, there is a risk on continuing the activities.
Since this is a internet application hosted on Azure, we need to review the security setting of the project, loophole of security may have very negative impact on customer satisfaction and leak of customer critical business information
Single Microsoft Project resource as a Single-Point-of-Failure
SIP trunk could not be provided by August 11th
SITA demands a deployment to the local data center which might not be ready before the project completion date
Site readiness - Engen managing site readiness dependencies such as hardware onsite, domain certificates and safety precautions
Size of the database too large
Skills are not transferred from MS team to RAC team
Skype for Business Remediation Timeline
Skype Platform (and features) definition
Skype PSTN Calling development may/will be stopped, limiting the opportunity for ABB to request required changes/ improvements
Skype SOW mismatch with client requirements - client is asking for IM and Presence as well as a cutover only. They have a similar scope issue as the Skype for Business D to MT offering. They have paid for bandwidth calculator planning session but do not want to engage in the assessment at this time. .
Skype workstreams accelerated to complete by March 2018
SkypeB mobile chat is dropped, the email options are – IOS goes directly to Apple personal mail, Android defaults to GOOD. Reviewed with Brian Mannion. This is a low usage case and he requested that we document it as such.
Skype-for-Business 2015: - Full automation of services high availability cannot provided for SfB by design, as customer expects - MSFT will stopp product development for on-Prem version of SfB, only cloud based product version will be further developed (Ignite Announcement)
Slippage in FDD sign-off dates can result into delay in start of offshore development complete resulting into an impact on budget or schedule
Slippage is forecasted in some of the remediation tasks including those related to Backend team
Slow change management
Slow decision-making process at customer's
Slow deployment of the CRM solution due to the uncompatibility of the CRM soltuion towars IE releases deployed on workstations (only 8% of workstations are equipped with IE11).
Slow pre-assessment pace (stage gate)
Slow progress of ZIC remediation checklist tasks
Slow turn around for decision making, specifically PIA approval.
Slower progress than expected for Sprint 0
Small Form Factor (SFF) Support
SMBC tents add new CR s to the current project. (Such as RMS, User picture and Myanalytics). Delivery team has no space handlue those CRs even additional resouces are avairable for CR,
SME Availability; The agency is very small and people hold multiple roles making it impossible to get consistent face time with key users. Further Union and State compliance situations make it hard to schedule meetings and project activities, resulting in potential delays.
SMTP port 25 is not allowed from cloud to on premise network
So far, the customer has not decided to resume or cancel the remaining delivery scope of 2nd phase. If they decide to cancel, NWS of the reaming scope may be reversed.
So far, we can not exectly confirm when will customer's re-org finish.
SO, SIRC team are still not available to participate in the lab testing and validation
Solution Adoption Concerns have been raised around: - Adoption & Change Management - Channel DB Integration - POS Device Support Strategy - Warehouse Adoption of AX as WMS
Solution architecture not approved by the customer on time – by Aug 31st.
Solution constraints us to use PaaS only and virtual machines cannot be used. We have to resort to custom deployment from visual studio and this is not supported from azure portal so need
Solution dependent on pre-G/A product
Solution design requires RSM to develop a number of integration components, there is alikely hood that RSM don have to capacity to develop the required components within the project timeframe
Solution performance
Solution requires SQL license but was not reflected in BOM to JCS. License cost was sent separately outside of RFP submission.
SOMA exisiting in Azure tenant
Some cameras are not supported by Genetec Solution
Some functionalities are postponed.
Some materials/resources must be provided by the client.
Some of customer's resources works on a 28-day basis, being backed-up by a peer
Some of key deliverables have been delayed which is likely to impact the support availability of Microsoft due to the expected schedule of available hours. 1. SOE is delayed and 2. o365 will be delayed due to requirement of a TRA and legislation update
Some of the VM's will not be migrated within the available estimates.
Some resources may be unavailable during certain days between February to May - this may lead to support issues as we transition to Go Live.
Some sites will have very high latency. Outlook is okay unless it exceeds 320ms.
Sonata ISV Solution ASCS not ready for D365
Source control and release management
SOW assumes network speed of 1 Gbps from onpremise to Azure to perform Server Migrations
SOW conflicts with project financials
SPC leadership is evaluating engagement of a 3rd party to manage their security requirements along with IPS team.
Spectris may be unable to review the Requirements Matrix to confirm its veracity
SPO may run out of sites that can be migrated if a solution is not in place for RMS and MFA.
SPO additional sites may need to be migrated
SPO storage capacity has reached the full amount that the customer has paid for
SPO Work Stream Risk: Assignment of Global Delivery lead for content migrations is pending - team member is pending Visa interview, other process completion prior to coming to US to work on this project. Further delays will impact team's ability to be ready for content pilot migrations 5/23.
Sprint 2 readiness – User stories elaboration to continue into sprint 2, which will cause rework, which in turn will have financial and schedule impact.
Sprint 9 Scope
Sprint sign-off from FIT: There is no formal sign-off from FIT on any of the deliverables made by MS. Example: UX Wireframes and mock-ups;
SQL application DB cannot be upgraded: - If the SQL application DB is unable to be upgraded due to the application vendor compatibility, then application can either be decommissioned or a new application should be indentified to take on the business compatibility.
SQL DB backup for all data sources excepts Iconics
SQL server 2000 version and older are discovered in Phase-1: If there are definitely more SQL 2000 versions (or older) from the discovered SQL Server instance (confirmed by the MAP tool), then this will outside what the contract/SOW
SQL server clusters discovery count - If SQL Clusters and other sources or reasons of incorrect estimation may have contributed to the approximated total number of SQL server instances, then the project activities, planning and labour estimation will be incorrect as well.
Sql server connectivity issue
SQL Server: There is a large number of supplier applications connecting to SQL backends
SQL Storage Performance and Configuration - The performance of the Production database is currently being affected by the underlying Storage performance, with read latency peaking at 393ms and Write Latency peaking at 267ms
SQL-R1: SQL server clusters discovery count
SQL-R2: SQL server 2000 version and older are discovered in Phase-1
SQL-R4: Infrastructure readiness
SQL-R6: SQL application DB cannot be upgraded
SQL-R7: Workstation discovered with SQL 2005 Express
Stablisment of a FQDN communication method is not an actual option for security team at SAT.
Staffing (not all positions filled, and different understanding of Daimler on what additional roles are needed). Daimler is concerned about the System/Network Integration Lead role and the second head unit developer role not yet filled. MCS however believes that the first role is not relevant and should be replaced by a business analyst, and the second one by a CRM developer. Eleven additional roles have been identified to be added which will require a change request.
Staffing Constraints with Customer Resources
Staffing SfB with Portuguese Speaking Team
Stage- and Prod. Environments: currently there is issue that the users from pwc browser cannot login to the application.
Staging schema still pending
Staging servers hasn't enough space to work with big databases
Stakeholder Decision Matrix. The key stakeholders represent both infrastructure and application groups, which have conflicting agendas. As design decisions are raised, an arbiter must be able to resolve debates quickly to avoid schedule impact.
Stakeholder Unavailability
Stakeholders participating in envisioning sessions believed additional environment was part of the deployment
Starbucks project/program team is not aligned with the schedule/directive the MCS team is marching to. Starbucks teams doesn't believe they have a schedule to march to and not real direction until they see the security criteria and re-evaluate the approved design to determine what needs to be modified and how it impacts consumption
Starbucks Readiness / ongoing support / establishment of a Cloud Capability Organization Governance of and processes and procedures to support the activities in the cloud environment need to be in place to provide the Starbucks desired level of deployment, monitoring, reporting, tracking and auditing.
Start date of support period agreed as 1st May - 30th June (60 days instead of 90 days). Deployment period was extended by 30 days instead. CR was raised, it is yet to be approved by customer. This was discussed and agreed on steering committee meeting on 25th April.
Starting development without the FDD signoff can result into significant rework effort
State Street Bank Corp (SSC) is a fin svc institution that has adopted Office Excel and Access as tools to enable financial calculations and reporting to their customer and internal groups across the global enterprise of approximately 60k users. SSC has contracted with MCS to obtain guidance with implementing a governance process. One of the key technologies recommended by MCS to certify authenticity and prevent malware injection is to use digital signatures with their Excel Workbooks. As part of recent test scenarios the technology is not working as expected within the customers workflow across 5000 developers and it is this problem that is now putting the MCS project at risk and has generated executive escalation within the bank.
Status of Network Readiness at different TATA Locations - though customer has tested configuring outlook profiles of test accounts at all TATA locations but this is not as per MS recommended practice.
STC internal processes are impacting the Handover of our project to the Ops team
Steep Resource Rampup
Steerco meeting to be rescheduled - new date not set.
Step 3 Conversion Strategy Echoed R005, the overall conversion strategy is crucial to meeting the Step 3 timeline in mid-Nov 2016. Full support from TVB IT (especially on CSB) on the data scheme, definition, transformation logic, and mapping in CSB and others is key. Prerequisites: • Business users to confirm the data mapping (down to the function point) • TVB IT to provide advisory support on transformation logic
StoneDonut not meeting development timelines. StoneDonut has been contracted by PIVOT for EDI development. PIVOT following up.
Stores with Shared Desktops are not covered by VBA scan
Storm in Chennai and holidays due to Chief Ministers death has had the partner team off work for almost 5 days now. This has schedule impact and budget impact due to MCS resource aligned full time on the engagement.
Strong Dependency to CORE Phase 1 go live date
Sub Project manager has not enough experience to manage project delivery, so need MS Pjm spend more time to project management and system go-live.
Subcon contract being cancelled by microsoft
Subcon UI designer, UX developer may not be available by next week
Subcontractor hours are over-spent.
Subs (Spain for now) is claming for resources to be disengaged from internaltional projects
Subscription Design not approved by SBUX
Subscription status and source of ownership must be determined to make a decision on network and firewall appliance. Current "pay-as-you-go" paradigm does not allow level of detail necessary for Active Directory implementation.
SuccessFactor Team to provision the SFTP by 11th August 2017.
SuccessFactors Resources. Resources may not always be available when MSFT needs them. Meetings are being shifted as resources have other priorities or conflicts. Example: Anika has scheduled 1 meeting 5 times
Sum of small delays are pushing SIT/UAT for final release to be executed with less than 4 weeks of duration or Benfica will have to postpone final milestone
Support from CV during SIT and UAT to reduce Turnaround time for issue resolution.
Support on code bugs and functionality of the Modern Version may not be covered by the Azure Fast Response service purchased
Support plan needs to be finalized. There may be no support contract in place at the time of go-live (Turning into issue soon)
Support vs Project activities for MS_Tavia team
Suspend or stop the Deployment to production by solving the problem of dependent system capacity
Swisscom Service Organization not ready
Sync versioning problems of code from other simultaneous evolutive developments.
System capacity for number of users to migrate on each wave to be above typical scenarios
System Centre - Partner contract delays (Work Order and PO)
T&M hours unused
Tactical (temporary) PAWs
Tanya is involved in other issues or dependencies uncovered during the Remediation phase.
Target VM's are critical to the migration of any of the servers, applications and databases.
TATA does not have a PSS contract to support this engagement.
TDW needs to acquire D365 licenses
Team access to environments
Team capacity and project run-rate. It has been recognised that the demands of the project are increasing and people time is become maxed from a Hyperion perspective. To be considered in planning activities
Team does not have experience with Map APIs or building web applications. Technology limitations may require additional effort to resolve issues or develop work-arounds.
Team has been destaffed due to scope cancellation, but now renault is adding new features in scope.
Team has consumed the week long buffer for incorporatng customer feedback. The final presentation date has not yet been fixed by customer
Team is building competing architectures • Limited resources to complete in sprint timeframes • Non-collaborative effort • Comparing architectures that not all in line with business objectives
Team is not set up for 24x7 support
Team operates at risk of being pulled into unplanned support and triaging for VIMT needs.
Team size capability to respond to V2 UAT and warranty
Team Support after GoLive
Team work/backlog is re-prioritized frequently by different business owners
Teaming issues with HP IT team.
Tech Data resources assigned to the migration tasks are not familiar with the technology being used (SSIS). There is a skills gap.
Technical - OP read: IT Security: banking is subjected to several security requirements in terms of tracking identity especially by Italian Law.
Technical assumptions for the roll out plan not validated
Technical blueprint of the solution and the ability to connect seemlessly with Hacienda/OGP
Technical Complexities greater than expected, communication. Technical complexities are potentially significant with discussions around requirements being in/out of scope and impact to project if included.
Technical constraints on the two current domains (Claro and Comcel) for the implementation that allows all users access to the tool and integration with 123MIC
Technical debt
Technical Emails are not answered quickly because of the tight deadline of the project. Delays in answering these emails may result in project delays
Technical Environment Set-up and Data Migration timeline: • Meeting planned for Wednesday 15 with BCP Infrastructure team • Installation guideline to be completed by Tuesday 14 • Deployment check-list under construction • Prerequisites and planning for prod and pre-prod environment set-up already sent • Get additional HLI resources to support the technical installation set-up (within budget) • Get Ertu (Veripark) on site to secure end of UAT/Data Migration subjects (within budget)
Technical impact / effort of changes increased because of individual requirements/different processes of the BAs
Technical Issues O365 and WP1 completion
Technical lead (Eduardo Guerra) overload on directing and completing project activities
Technical Lead CRM may not be able to focus on technical activities due to his involvement in a dual role of technical as well as S&M lead
Technical Leadirship: No available resources to start the project.
Technical Office not being well dimensioned to populate backlog at required pace for upcoming releases
Technical problems during a migration, that was not detected during the QA and the customer don't inform about the network configuration, the solution designed is not possible and new solution is not easy in the customer enviroment
Technical quality and stability for release 1A may be at risk.
Technical Risks in app backend
Technically it is difficult and new for us (Indeed, nobody has integrated Xamarin with CECA Bank, so there is no documentation and previous experiences) We are having many problems with HCE documentation, errors with the SDK At the beginning the communications with CECA was very slow and inefficient
Telelink's maturity to deliver complete solution from a technical standpoint, and its ability to manage government customer is doubtful. This will impact project success.
Telenor’s decision and strategy of AAD Connect – password sync setup
Telenor’s O365 and EMS operating model readiness
Telstra may rollback and stop migrations if eDiscovery tool issues not resolved by end of October.
Telstra Ops has not provided ATO to the Telstra Exchange Hybrid environment as yet. This will limit rollback of users.
Test data creation will take longer than anticipated and can't start due to R-01
Test data that does not exist will have to be created by STM
Test environment is not yet available.
Test Environment not ready
Test scenarios have not been identified for data analytics and visualization
Testing Apps with Multiple Business Units
Testing environments are not stable.
Testing team is not planned in PMA, we had planned to use Phase 2 project testing team. Due to other dependencies Phase 2 start date has been moved to Q4 this will impact the capacity planned for PMA
Testing with linked mailbox on current forest means thatt strategies selected are changing and not a formal communication from repsol has been given. This impacts directly on the rest of projects (exchange /Lync)
Thalys has no real experience in the implementation of BI project and very low level of maturity in defining business needs. This risk is not to have enough elements to be able to design the solution to be implemented to reach project goals
The $25M Azure pre-pay that was included in Walmart's three year Enterprise Agreement has been consumed in two years. The EA consumption contract terms are still in place so they will get quarterly bills. This leaves them without an overall Azure consumption contract.
The 208 apps in the SOW included WWW apps. However, the list of components in the spreadsheet (totalling 208) excludes www apps (there are79 www apps)
The above items and any other security issues we face in the sandbox implementation might delay the schedule as we are working in a constrained PaaS environment for PCI-DSS certification.
The Accenture project manager has informed the Microsoft team that she is no longer involved in the project. However, a replacement has not been identified. We are now working only with the tech lead at Accenture.
The Acceptance criteria is pretty basic (usually just a happy workflow) and does not cover a lot of scenarios driven by business rules, which will certainly be a part of the UAT Testing scenarios
The account team was informed that the client should be presented with an SCCM Engagement plan. One comment from ECG: “I understand there are other security engagements in the deal stages. Our suggestion for this customer is to offer them a SCCM engagement. For account teams in the future, if a customer is unable to deploy a simple software package, then a SCCM (or other vendor) engagement is warranted and should be prioritized over any security initiative since the inability to deploy and patch remains their biggest vulnerability.”
The activities might be stopped
The actual size (data) of the sites to be migrated is much higher than originally thought of and more cirtical in the throughput speed than the number of sites. Therefor it is unlikely that with the current approach we will be able to migrate the volume of data (2.7TB) before September 15th.
The addition of frequently asked call center scenarios to the current backlog may have effects on budget and schedule.
The administrative process in the client are slow and difficult for projects with tide schedules
The agency seems to be very small and people playing multiple roles making it impossible to get face time with key users. Further Union and State compliance situations make it hard to schedule meetings and project activities Result delays and potential overruns.
The agreement on ACM phase 2 scope and execution is still missing and the ACM consultants gets pulled into tactical activities.
The AHS AD team have stated that they have limited resource/capacity to take on the additional work (GPOs) for the Windows 10 project.
The amount of time it will take to identify all the work that needs to be in scope as well as get it approved could cause further delays to the project. Currently HPE wants to identify all the items for all work streams that need to be brought in scope prior to presenting any to the exec. sponsors. The reason for this is so they have one big change order and not piece meal it to the sponsors. However, the target to get all these items identified is the end of July.
The AMS team has been convened during the diagnostics and maintenance activities on site, and we don't have response.
The Analytic platform needs to be licensing to get the SO & SQL Server Enterprise products to working the new approach with the client.
The app will be tested on a single iPhone and Android phone device (iPhone 6s/Samsung S6) and there could be differences in experience on other resolutions/form factors
The approval Process from azure consumption is very burocratic from the customer side. There have been some delays from our side to deliver the inputs to start the Process.
The architecture level key resource from City of Oulu (Lauri Lappalainen) is currently on sick leave and will be retiring immediately after.
The assessment of business systems and applications will require AT to identify and map the configuration items that form a service/application. Failure to do so, might result in increased effort and time required to complete the Enterprise Modernisation assessment activities.
The availability of customer's Resources is limited. Some key activites are at the end of december and January.
The Azure subscription is needed to catch up with the deadlines
The bank have asked for this to be a 3rd party managed programme. This means that MS will be the bank's programme manager. Negative risk is that MS could be left to 'fend for themselves' or have little influence on getting activity completed to plan. Mitigation is that this is supported by Governance and by individuals on the ground at the programme level in the bank. Governance are keenly aware of the situation and the move to ask MS to 3rd party manage the programme is being supported by the key IT and business stakeholders and the MS PgM is being supported on the ground by a bank business manager and project manager. Being a 3rd party managed programme is a key COS for the key business and IT stakeholder as the bank is somewhat resource constrained due to Omega. Positive risk is that MS can quickly build into a trusted advisor and this will aide securing further budget to implement DWP and/or assist with Win7. Check-In 19th September: We successfully delivered DWP design complete
The Barclays environment will require strong technical leadership in order to control technical scope & processes for the project.
The BIF will finish at the end of FY17
The BT EA team lacks the skill and capacity in some areas to support the new ERP solution.
The business stakeholders/decisions makers needed to participate in the adoption change management activities are not accessible to the Microsoft ACM team as needed to complete tasks like health check, work style analysis, etc.
The CAL's for SharePoint 2016 is not available after getting access to MVLS. Now we need to check if we can have mixed environment (ie., if we can use SharePoint 2013 Foundation for self service group management)
The change in current hardware status and impending redesign will impact the project timeline and scope.
The change of government resulting from elections can delay or close the project
The change was discussed in the CheckPoint meeting on 27-Apr. Patrick will summarize the changes needed for CKHH confirmation
The Changes to Production could not be performed due to Change Embargo period in Teltra
The City's vision for the MDM is yet to be understood/articulated internally; a meeting within the City has been scheduled for July 5, 2016 to discuss this.
The Claro VD project is dependent upon the Modernization project.
The client is continually deferring closure with additional issues that should be changes, which may be to extend the MS support to the project. This needs to be arrested and the project closed
The client is not given the approval to go live with Asistente Virtual
The Contract will shift to On Hold
the contracted hours won’t be used by the targeted final date.
The costomer has requested an extension of 2 weeks for one of the consultants. The premier hours are yet to be leveraged for the same. We are trying to figure out the process that is needed to be followed.
The CR that repurposes $1.3M to other work has not been signed by SSB as of 24JAN. It also includes no detailed specifications (like an SOW would have) about what work is being agreed to, There is a long lead time to assign resources and get the SSB on-boarding completed. Thus, there is danger that by the time the CR is signed, we will have difficulty burning through the funding in FY17.
The criticality of the system to business operations is a concern.
The CRM requests out of scope.
The current approach of assessment may not result in the traction and velocity required to migrate in the required timeframe
The current custom renderer for PDF viewer works only for UWP. Due to the time constraint, this solution satisfies the pilot requirement but we should look for a Xamarin Forms solution otherwise we would need to develop a custom solution for each platform.
The current customer platform (Exchange 2007) has stability issues. The client requested to analyze the possibility of accelerate the mailbox migration to Exchange 2013, disconnected from Desktop migration
The current effort to create the required policies is going slower than planned. As such, there is a risk of a date slip for the delivery of the policy document as well as Cloud Infrastructure Design Guidance and Deployment Methodology Document.
The current Ips that team has may not work with 2007 source farms
The current Microsoft consulting services contract (TLT) ends May 19th.
The current monitoring tool (SCOM) is 2007 R2 – it will NOT work on Windows Server 2016
The current schedule delay on the project is 11 days, as of the last reporting period. Deployment of Motor therefore needs to be extended by 11 days however, this revised date for Motor deployment may not be accepted by ANSA.
the custome is very likely inclined to ask for change request o modify the scope
The customer clearly stated that they consider Microsoft as an extremely expensive vendor and they will be reluctant to proceed to next phases. Important note: The customer appreciated the quality of the services provided.
The customer currently has not started any development of the solution to be deployed in Portugal whilst they are planning to have UAT on the 8th of August.
The customer did not accept the replacement of the PjM so that there is actually no date for the release of the actual one (Daniele Petranca) who was scheduled on a different project / customer. Moreover, the customer is willing to keep Daniele for at least 3 more months.
The customer does not confirm the availability of the apps code and data for testing, so we cannot have a last version of the schedule for the second part of the project.
The customer does not have clear the scope in terms of the data bases list. Posible Change Request.
The customer doesn't want to integrate the end-to-end PCI DSS governance.
The customer environment is not yet ready which will affect the schedule of the project
The customer has asked MCS to take on high level Program Management responsibilities for consolidating overall project plans and Program Status Reporting. As these tasks are normally assigned to the customer, we have called this out as an Engagement Risk.
The customer has identified that there are operational readiness issues internal to their environment and business units that have custom circumstances for migration
The customer has raised that they have underestimated the workload plan of the key user to cover the project tasks and their internal business task
The customer hasn't a single point of contact, and the PMO is delegated to Accenture, who provides the customer with a not reliable PMO support. For this reason we have to interact directly with more than 20 focal points inside at the customer site.
The customer is responsible of the execution of actions that will allow the project continuity with the team and is scheduling the working sessions according to their progress. Last minute cancellations migh impact the team utilization considering that they won't be available to be assigned to other possible tasks.
The customer is responsible of the execution of actions that will allow the project continuity with the team but is not providing the status over the actions completed, on going or deayed.
The customer maturity regarding business processes is low. The customer requested to change the scope of the assignment so the team has few weeks visibility and planning capabilities. The Data Insight part of the project remains unknown as the customer is concentrated to the new OSS scope. This makes the planning for the non CRM streams extremely difficult. The customer timelines are extremely tight and there are multiple (deep) integrations with Portal and Aconex.
The customer may not have a budget for funding iteration-1 as per our initial capacity planning.
The Customer Project Manager, Giusy Damiano, is leaving the Company. As a consecuence there are high chances that the next Project phase (a different contract) will be delayed until the replacement arrives
The customer requested an effort for the whole team to accompany him in the Certification tests that will be run in weekends, it will be necessary to incorporate partner hours into the project to inforce the successful of this phase.
The customer requested to put the project on hold until they complete their internal requirements. This will impact the NWS at some point.
The customer SAT, is requested a Change Request, we are in the Phase 1 and the Phase 2 is in progress.
The customer wants a OneDrive Autoconfiguration option.
the customer wants to take advantage of some ambiguos point at the SOW and they was trying to add more functionality.
The data mapping has been delayed for CRM system
The Delays during execution due to Customer Dependencies
The Design Phase is not approve for Customer
The different architectural responsibilities will be unclear during and after the new architect comes in
The duration of ASR replications is currently forecasted in the plan and could vary drastically dependent on internet speeds
The effort required for end to end System Testing of Sprint 2b cannot be accommodated in the expected schedule
The end customer CMS is not following or is not aware of the Leidos Project Plan. The Prime has created a master project plan that is not being shared to Microsoft
The end of the project is in the last week of December, the Master contract due date is Dec 31, 2017. This situation put in risk the project invoicing The ADE is dealing with customer the procedure to follow
The engagement will be publicly known and information will be able to be obtained through the Freedom on Information Act in the State of Ohio,
The estimation of 5 applications & 8 databases per server is below the reality we're facing. With half of the servers reviewed we have almost 4 times this amount so far.
The ESWO specifies that $1M of the $3.5M in BIF must be consumed in FY17. Currently, the staffing plan does not have enough planned work to consume this budget.
The existence of a transition indicates that we're planning to turn things over. We have "side by side" as the knowledge transfer approach. Dev resources are in India, so sxs not likely to happen. Need to know how we get knowledge from India to the US to the customer.
The expected 'need' for Program Oversite is to be high.
The fact that we are working only with the technical members of Akbank's Integro team during analysis, there may be gaps in requirements gathering.
The Fast Track Team has been advised by LCA to not sign for accounts nor take training required by Entergy. The accounts are required by Entergy
The FedEx OPP manager is out
The following changes have eventuated: ADE has moved into a new role, GD OC has travelled back home, Original PjM has transitioned onto a new project. The following changes are expected to eventuate: Architect going on leave from 15 Sept - 30 Oct, AT/MS Programme Manager expected to disengage early October, potential new PjM assigned.
The following Intune requirements need to be met to allow the migration to continue: Block Wearables from accessing the container: TD requires the ability to control if data leaves the container and consider this an essential control of a mature EMS platform. Please note, this cant and should not be limited to iOS and Android. Data also includes notifications. ACTION: MAM controls for office on mobile to disable corporate data sync and notifications from appearing on a mobile device DLP issues must be closed or dates provided for resolution. The Sharepoint App and OneDrive access after outlook has been removed issue are the two top issues that will stop us from proceeding. ACTION: Provide dates on when these issues will be closed Confirmation that Android MDM will enforce a PIN on wearables: We are still waiting for answer, without this in place 45% of our users would be blocked from taking advantage of Office on mobile.
The FRS document has not bee approved yet and there is an approaching holiday period (due to Eid), the approval and sign off FRS might be delayed by over a week.
The GPR might not have enough equipment (PCs, Projectors, rooms) required to deliver the analysis workshops (several sessions in parallel)
The hand over to the Helsana Operations Team need additional documentation and script development. There is a risk that the knowledge to run the solution is not sufficiant within Helsana.
The hours consumed so far are more than the originally estimated.
The Identity (Personalization) work have following dependency for OneAccess Web Application configuration before deployment • Google Recaptcha Key • Exchange Accounts for Dev & Test to send email • SSO Account approver list for each location.
The initial estimates for expected CRM database size is approx. 6Tb. Deal team is in discussion with E2 team of CRM PG and have initial go ahead to proceed, however the assumptions made regarding customer business requirements need to be validated at the earliest in Analysis phase. Minor deviation from assumptions made at this initial stage could lead to severe performance issues as there is no comparable reference for DB size of this scale.
The Install, Load Test (ILT) environment setup may be delayed due to BOQ/HPE process.
The IT staff continues to comment on documents submitted in February 2017. Four months after they have been delivered, they continue to make comments.
The lack of commitment to procure enterprise licenses carries the risk of Design and Implementation remediation
The lack of reserves for the implementation of the budgets BDR, BDDS will require an additional project budget.
The lead time needed to get a report from EXO-D and EXO vNext team will cause a longer wait time to confirm the resolution to unsynced objects
The Link to Safaricom is unstable and unreliable
The main deliverable on Project is the architecture design. This document is complex and envolve many customer teams acceptance/feedback.
the main sponsor and responsible of the projects last week is in maternity period. Her backup may be not have enugh context and konoledge about the solution in order to take desitions or validate functionality.
The major risk to this project is the newly found Engineering agreement between Baxter and MSFT to complete the migrations by Nov 30th....this is shortening the project timeline to a short Critical Path effort. https://microsoft.sharepoint.com/teams/CampusProjectSites032_Ext/7o7hkd3hzd/_layouts/15/DocIdRedir.aspx?ID=CPS032EXT-349821738-13 The schedule for this effort is being prepared as we are working with a number of groups within MSFT...PG/BG.
The Microsoft Identity Manager Certificate Management module for managing the life cycle of smart cards does not support the card models currently in use by Angola LNG
The Microsoft planned testing start date for the xPression upgrade clashes with the Development testing start date for another BOQ project (managed by Keith Dawson). A priority decision may be required
THE MSFT Infra consultant, has several other projects and will not be able to continue executing on this projects.
The new Acting Management are reviewning their need for the this Customs Projet as they are of the opinion this is a duplication of their Asycuda Project.
The New Board Member may consider irrelevant the previous IS strategy sustained by the contracts
The new datacenter in Soyo (Annex) is still waiting for the new hardware (G9 generation HP servers) to support the future virtualization environment.
The new MA Architect may be escalated off of the project before joining
The number of available MCS PM days will not be enough to cover the requirements to close out the project
The OBS project manager has not been identified or left will cause a delay to remediation activities owned by OBS.
The official customer Product Owner (Serhat Yilmaz) is not suitable according to his capabilities for his role. 1. He lead meetings and workshops with business department without detailed agenda. This results in chaos. 2. He makes decision without sufficient information and consultation with the development team. 3. He forgets often what he said and at next conversation says that he doesn't meant it. 4. He wants to drive his own ideas even these are not accepted by the business departments.
The ongoing issues and project environment is very challenging and puts significant drain on project consultants and management. Team members are demotivated by some of the actions of Sinara.
The partner is not skilled enough to deploy and test the build process
The partner is still currently doing design during development (Populating and Consuming routines)
The partners of the customer takes more time than expected in doing the modules that we need to integrate our application with the existing systems and data.
The Phase 2 deliverable has been submited for review to the customer long time but there are internal conflicts between the stakeholders and there is no progress on the sign-off.
The Phase 2 Sprint 1 User Stories have been submitted to Customer. Team will start to plan for the implementation. There could be a possibility of change in User requirements, if implementation (technical and functionality) strategy is decided before the Customer reverts
The PjM is moving to other domain and new replacement may create some challenges.
The planning for migration of SP internal users has not been completed yet. Customer wants the migration to take place between Nov 1 and Dec 31. Migration is out of scope for current engagement, however, customer expects Microsoft to assist through additional engagements
The platform may not be able to store telemetry at the rate required at cutover or for future predicted volumes.
The power in the control room, which was supposed to be stable now, will be stable not before June. The customer is trying to mitigate by buying small UPS
The process for setting up a VPN connectivity by CBA is a lengthy process and will delay start date. Addditional ways of connecting to CBA environment are being exploted ( VDI vs RAS vs Azure)
The project budget does not account for the ongoing delays and unplanned re-design work.
The project funding is very tight.
The project has experienced significant scope changes which resulted in CR. The CR might experience attempts to change scope
The project has high dependency on Partner. Further delay on Partner implementation will cause delay for MS to start the Performance test. Risk on Revenue and Resources availability. We estimate that we can start performance test in FEB. 2017
The project initiation will be severely delayed
the project is necessary freezing because there are not available QA environment.
The project may not be complete by the planned date of 13 Sep 2016
The project must engage with multiple resources at Vodafone (e.g. Business System Owners/Operations Teams) and make use of existing business as usual process (e.g. hardware procurement, maintenance windows and change control). The project schedule currently assumed may not be achievable due to resource availability at Vodafone and lead times to use existing business process.
The project solution architect (Ville Päivinen) is changing position in end of H1.
The project team is run from at Priva HQ in the Netherlands, where as Pilot Customer is Priva Canada risking the solution to be not aligned with Priva Canada Needs
The project will essentially pause in terms of onsite work and be pushed out for one month, to give time for the management meeting, the architectural meeting and their decisions to be finalized. This also takes into account the Thanksgiving US Holiday (week of November 21st). update Dec04:Cybersecurity team next on-site plan will be Jan for production deployment, but until now the project plan still not confirm with 88
The project will face challenge to join all necessary resources since it conflicts with the yearly vacation period and other major events and hollidays.
The project xBG is currently being staffed (big driver of Azure consumption) with the need of 1-2 resources from the R3 team who have the experience from R1 and R2. The impacted resources are SI consultant Gangadhar Gaur - IGD (40 hours p/w) and architect - EMEA Attila Farkas (8-16 hours).
The proposed Design does not match BUs requirements
The quality of the information from the universe defined of tax payers , could not have the necessary quality in terms of repeated or missing invoices.
The Ragn Sells strategy and therewith potentially their business model and related business processes are currently being reassessed/developed.
The real data will be delivered by Euler Hermes first in the beginning of CW 26 (27th June, which doesn’t allow sufficient time the testing of migration tool and data migration until the end of June is in danger.
The recent pre-pilot migration of 23 users met with some unexpected outcomes for calendars migrated -subscribed calendars were also migrated along with user's calendars. The service description from the FTC is to migrate "ALL" calendars or "NONE".
The reference architecture contains proposals for common services but no details on making them production ready
The remaining time for R.17.2 is not enough to develop the requested scope. The main reasons for that are missing requirement Details and we were not able to find a suitable Architect for the DiBAP project in time. Thus the current estimations shows that it is no longer possible to reach the target date R. 17.2. Helsana will decide on Thursday 20.04. if they will continue with the Microsoft portal or stay with their current Portal solution.
The remediation checklist is not completed within the forecasted schedule
The Resource is overbooking the hours due to customer's request. The resource is initially planned for 200 hours. An additional 74 hours have been consumed by the resource.
The resource may not be able to deliver the following in scope items due to schedule constraints. • Creating a defined development style guide that is optimized for Xamarin Forms development and incorporated into the local/tfs build process (to fail the build if the style is incorrect/incomplete). • Process/development foundation that utilizes a TDD approach to code creation and how it applies to Xamarin development
The resources assigned to this project are the same resources assigned to the Datos Abiertos project.
The results from processing 1 month for BI and Sum, could throw differences on expected data.
The RFCs for On prem are not approved as some of the pre-requisites are not yet completed by STC stakeholders as Backup and App assessment.
The Rules Engine has been developed using un-supported code.
The scope for the CCLM project is very large. The strategy to deploy a single large system will come with many challenges.
The screen interface, level of detail and interactions on the web application need to match customer expectation and usability.
The second level sponsor changed, a new hired for the IT department
The Second payment process still not finished
The selected finance consultant was able to cope up with the project needs. Hence is released from the project
The Service Bus issue will need more effort to be resolved, risk reserve should be used to cover that.
The service fee budget will be depleted in Feb 2018 before all migrations are completed
The SharePoint Architect Christoph Lesser has a new role from 1st Oct. 2017. This could lead to a huge escalation at the customer side.
The SITA hardware procurement process can be very lengthy and might delay the project.
the solution architect staffed on the project has not enough time to fulfill the fulltime assignment
The solution of CECA BANK (web services and SDK for payments) isn't very mature, we found many problems and they are still in an stabilization phase
The solution to provide NON-Telstra managed device access to O365 is not completed as yet.
The SOW has no expectation setting for any type of remote work scenarios.
The state barely has the ability to sustain the delivered system. There is no capability to do future development.
The State has refused to face reality regarding the feasibility of the April 2017 timeline. There are critical path impacts that cannot be resolved that make a current plan for April 2017 impossible to meet. The State has yet to meet a single
The state is anticiptated to not respond fully within the 5 day period for all submitted deliverables.
The State is requesting additional support resources as the concerns increase about the MCS team roll-off timeframe.
The State is slow to grasp the challenges and magnitude of the decisions required to implement the POS Retail model that is in play.
The subcon and/or MS idenitifies a CR that is not accepted by the customer.
The Surface Hub requires Internet access in order to access all device featues. Due to DHS network security constraints, it is likely that the a design/technical spec will need to be produced and approved by DHS security teams in order to enable this access.
The Sweden Country Manager has been trying to block this project from starting. In the end she gave in and accepted the project. We are not entirely sure what "power" she currently has to torpedo the project if she would want to/what her current relation to/emotion with the project is.
The target platform must be identified, provisioned and available for the migration phase of the project. The target platform must be suitable for the application requirements.
The team leader left the company midway through the UAT process
The time taken to obtain the vanity domains required by the project will not arrive in time
The timeline of BIF is not sufficient for the consultants to deliver the work, the main possible reason that customer is not ready for the migration.
The total number of discovery calls conducted are 10 so far by 2/23
The two modules, Plan Inquiry and Partipant Inquiry, that TRS had planned to deliver by Oct 2017 have significant number of screens.
The UAT requires the correct test case definition from Customer
The UAT will not be completed as expected, as some of the Scania integrations and/or end point systems are not ready for test yet.
The whole project lifecycle is to be delivered under one fixed fee contract.
The Wyeth CRM data cannot connected by Wyeth EDW DB server
The Wyeth Sales Power BI UI has not confirmed
Thee are too many user stories to complete within the 3 remaining sprints, with the team size we have.
their a risk of Schedule slippage and also bad CPE as the project manager is not able to schedule skype calls with the customer and the project manager needs to align with the customer on project delivery/track
There are a set of items that are being rejected in testing due to a lack of automation in the implementation. 1. Inventory adjustments on Enterprise Portal 2. Inventory adjustments for Over and Short shipments 3. Sales file processing on Enterprise Portal Automation of these would require a Change Request.
There are around 75 SME's for varying Applications and Databases.
There are concerns on the ability of our partner Unipartner to lead the AS-IS functionality identification and defining the UX strategy.
There are differences in how the Lube portion of Shell and the Marine portion of Shell handle many items, such as labels, sample numbering, etc. In order to manage this with the new application, and agreement must be made between Marine and Lube on how to handle many fields within the application. This cause some decisions to be made slowly.
There are disconections with DB2 schema, this interrupts for days developer activities until is resolved by a third party provider with no agreeded SLAs.
There are multiple, concurrent initiatives at JH that may impact our timeline including Optimization, Migration to ARM and Premier activities to address production issues.
There are no customizations considered in scope. However, ANSA McAL holds today about 1000+ customization of all types in their current AX 2009 instances. The nature and complexity of those customizations is unknown and there is not documentation available.
There are scope discrepancies between the SOW for the Analysis-only phase and the SOW for the complete project life cycle delivery (i.e. TAODS-only vs TAODS + Central beneficiaries services processing units)
There are several CRs that have been requested for sizing estimates and a BE. This is a new risk profile that needs to be assessed for taking on any new work within the umbrella of this engagement.
There are several known issues which could occur during the coexistence phase as well as during the migration. There is still no approval from business side that these are acceptable, as well as there is no communication for end-users yet.
There are several vendors ( CEMS, HV, HealthPrize, OpenClinica, CareMAtix, etc)who are part of the solution and will need to complete their work before the solution can be integration tested as a complete platform
There are three TCCC owned deliverables required to move forward on the AD security work stream: 1) Approval for Microsoft hands on keyboards 2) Installation/execution of Spider Scanners 3) Domain Controllers Memory/CPU upgrades
There can be multiple ends where the delays can occur. If there is no strong monitoring mechanism it would be difficult to track the delivery units
There have been internal conversations that workloads have been earmarked for AWS without providing the Azure team to provide feedback. Discussions internally at Starbucks and the cloud governance team continue without resolution.
There is a change in scope and additional requirements got added
There is a dependency on when the Marketing product for D365 will be released
There is a gap between RA & SOW, the gap maybe significant.
There is a issue that project not able proceed within high level schedule and target dates due to LBG delays.
There is a misalignment of how MCS is to be used (based on the SOW) and how the client is currently using MCS resource.
There is a overall program for the transition away from KPN. As Enexis recently introduced a agile way of working (SCRUM) there are different squads working on different topics. However an overall scope definition and high level planning seems to be missing.
There is a request not to run post configuration play backs. One of the key outputs from these sessions is to review with the key Stakeholders the workstream dynamics configuration, validate decisions and assumptions made during the scoping workshops. Failure to do so may compromise system tetsing and result in request for late chnages impacting quality and scehdule. Playbacks are aslo a key component for the progressive Knowledge Transfger process
There is a risk in not having UAT test cases and comprehensively testing the application and server migrations
There is a risk of building and testing Foundation framework based on reference architecture v0.2 which is not yet approved
There is a risk of delay due to: - The Marketing department may get back in scope - New unknown departments may get back in scope - The readiness of the additional departments is expected to be very low
There is a risk of delay if the Plan and Budget is not approved. The Expo2020 has to approve the Implementation Budget and Plan by 2017.08.21 to avoid any delays to requested deadlines.
There is a risk of getting new IP Range for Uniper after network split.
There is a risk of larger variances to forecast/actual revenue recognition due to the programme being in planning phase and having no initial plan.
There is a risk of not getting the managed service in place in time for Azure Go-Live
There is a risk of not having Hub VNET connectivity with Shared Express Route connection by 31st May to complete Build and Test due to dependency on Uniper/EON T-Systems
There is a risk of project delays if we are delayed getting access to CA Identity Manager and SiteMinder environment in the development domain
There is a risk of significant customer dissatisfaction if it is not possible to consume the reinvestment funding within the 18 month term or there is a perception that they did not receive value from the reinvestment.
There is a risk that Customer plan and resoure capacity alignment is not understood and remains unavailable. There is also Microsoft resource constraints impacting customer requested project start dates
There is a risk that CSAT would be lowered if three product issues are not resolved or less progress at the end of this project.
There is a risk that customer confidence in Microsoft is damaged to an extent that the project timeline and budget does not adequately support quality and face to face engagement to fully mitigate.
There is a risk that interviews with SL1 applications may not be in place by end of October, hence the Gap analysis may be delayed
There is a risk that network configuration (switch config) issues may implede or block the Production solution build activity.
There is a risk that project not able proceed within high level schedule and target dates due to LBG delays.
There is a risk that RBS will not provide approval to progress the Domain Upgrades according to the revised schedule for business reasons. For example, there could be other changes of a higher priority, there could be low support from the business.
There is a risk that scans and approvals may not be in place by mid October , hence the Gap analysis may be delayed
There is a risk that Server 2016 cannot be used for the PROD environment until early 2018
THere is a risk that Site to Site ASR and ARM Migration activities will need to extend beyond Jun 30 due to interdependencies between these initiatives. Testing of both ASR upgrade and ARM migration require a new DR Test environment to be setup which may take longer.
There is a risk that some servers running Win2K3 will not get remediated by June 30, 2017--and that AA will have to buy a CSA for FY 2018.
There is a risk that the business will be unhappy with the UI and user experience of the solution
There is a risk that the Change approval for production installation and connection of the solution will delay the project so that the target contact end date cannot be achieved.
There is a risk that the design may be delivered later than planned
There is a risk that the ETD service will not be rolled out and a sufficent pace to demosntrate value from the service and secure a renewal
There is a risk that the extended lapsed time of delivery will drive cost for PJM and architecture
There is a risk that the MOVES delay will result in work stoppage and resources being disengaged.
There is a risk that the team can not be onsite because of Denmark tax laws
There is a risk that the use of Service Bus as a technology will cause additional separate processing to be required in the event messages are not written to Service bus.
There is a risk that updating the stored procedures migrated from MySQL to Azure SQL to reflect the differences in the DB technologies has been missed.
There is a risk to re-secure the deployment consultant resource after the pause period to restart the remediation phase to support onsite - as per BHPB requested.
There is a significant lack of scope definition, which is moving the project back to design/definition phase.
There is currently no clear strategy for end user compute including delivery of a Windows 10 platform.
There is gap between what has been announced during the Presales activities and the current status (ie Identity and Exchange hybrid readiness ). Moreover, due to external factors, resources were not dedicated to the project. SPIE needs more time to perform activities under its responsibilities but have limited availabilities.
There is no application setup document present currently, this might be asked for given the capabilities of the support team.
There is no direct interaction with the Customer and the Project Manager due to language constraints. Project is based in Macao and the Project Manager is based out of India
There is no DP/Apps/VP/CRM/BI Support to PRODUCTION.
There is no identified coverage for the warranty period.
There is no SCOM PM assigned from TD who orchestrates the input from various dispersed groups.
There is not a reliable source of the active pages. The only way to estimate the pages that are being used is getting them from the system logs
There is not enough pipeline to finish the CoE
There is unused budget of 91 hours.
There may be lack of Cooperation with agencies/ministries, which shall be connected to GG.
There may be lack of e-service documentation in agency/ministry.
There maybe an income tax liability for consultants working on the project which would have to met by the project.
There where identified some extra dependencies for APS.
There's a risk of MCTO canceling contract with TR thus invalidating MCS contract with TR
There's no plan for cutovers of old servers to new ones we don't have sight on when the UAT is expected to finish and the cutover to be done.
This is a 100% IT driven project. Project ROI is based on their ability to go live before end of this year. This will save Oracle licensing cost for 2018 and beyond. Key business user does not have any business benefit other than a separate legal entity from accounting perspective. 37 week project schedule does not have any slack and this is challenge for the business since they have to make architectural decisions quickly.
This is a Type 2 , Thin Prime , Public Sector Project . There is very minimal involvement from Microsoft . The implementation and customer facing project management is being done by the Subcontractor. The MCS architect is very minimally involved. AAD team is involved now. Architect has moved to another role. Currently looking for a replacement resource for architect.
This is one of the first AI EAP projects done on the Microsoft BOT framework. The quality of the available IP is rather low.
This is the first time we have carried this out as a customer engagement
This project depend of other Project PSM
This project is designed to pilot a 'lift and shift' project for TFL. If additional work is added such as updating versions of Server OS and Database to align with new strategic direction in TfL then the project will not be a lift and shift, will potentially attract more risk and extend the timelines.
Though the support is planned with minimal team 1 or 2 resources, there may be additional support that will be needed during School beginning, as the entire District will be using OneView for the first time
Threat model has not been produced early enough vs NCC results vs financialy liability
Throttling exceptions will expire unless renewed.
Tiempos largos para cierre de proyecto
Tier 0 Environment (VMWare) will not be available for test / deployment of ESAE
Tight Deadline for December 15th Cutover
Tight timeline and many features/functions desired.
Time available for internal integration testing is not sufficient
Time available to support implementation
Time off - Dev Lead - personal situation
Time Zone Challenges
Timeboxed activities must be met to meet obligations for both MCS and SSA-OIG
Timeline expectation versus the contracted timeline
Timeline for implementing the silo is unknown
Timeline will need to be reviewed for consideration of the OP and MT migrations running in parallel as well as the release of information of resources who will be part of the AGCO team are announced
Timely availability & onboarding of offshore / onsite resources
Timing of decision on which environments will be moved to WatServ for E2E phase.
Titanium informed us that Rym B. had sent a letter to quit the company. They are working to retain her and they are confident they will be able to.
TM Hours for migratation of all projects
To accommodate the design change we will require to add additional effort and hence schedule and finances will be impacted.
To complete the assessment interviews the project need to engage with Vodafone's operating companies (opcos). To be successful the opcos will need to buy-in to the project approach, adhere to a standard delivery approach and provide their own funding.
To continue this project after November, there is a risk that project can't be able to assign right members. - professional of cyber security may not exist in Japan. - Customer may need full assigned consultant and parmanently staying in customer's site(Toyota). - MSIT ACE team may have the skill, but the costs of them are double fro Japan.
To date, TRS has not been able to identify any Win2003 that can be upgraded due to incompatibility of some of their applications with newer versions of Windows.
To do our job, we have to integrate our development with other platforms active in the customer. Two partners of MS (hired by the customer) are involved. Their availability and speed-to-act is a risk for us
To have communication flows and federations
to replace Express Route, customer requested MS to provide a High availability solution to Exchange
Tokin/Kemet Communications
Too many members from customer teams on sumer holidays for 4 weeks, no people of their teams to complete their tasks.
Tool Scoping for the Run is currently not defined. We are waiting for a resource to identify Tools and no resource is found currently.
TOPS can not completely complete the writing of the TDDs. Risk of the need for additional resources from the MS to complete and finalize the documents.
TOPS did not correctly estimate the complexity of the project and have already consumed significantly higher budget than anticipated.
Total actual hours are currently behind plan, however the current burn rate is higher than planned and will need to be managed carefully.
TP Security rules don't allow openings for Internet Traffic on Subnet. Solution and decisions must be provided by TP in order to get connections between PaaS and VM's to work
Tracking the project using multiple tracking sheets by ZIC
Training concerns with AP group may result in delays to completion of Simulation phase and remaining E2E test cases.
Training Requirements - Jabil has expressed concern that the Vitalyst training they purchased under the original contract may not be what they truly require. They have not been able though to quantify what they do require.
Transactions take longer to write to MCDC (60 seconds +), thus the response time to track & catch potential fraudulent transactions within a reasonable timeframe is compromised.
Transition between current and the newcoming Project Architects
Transition from vCurrent (dedicated on-premise) to vNext (dedicated instance in multi-tenant) Exchange server has not taken place yet in TD Production environment, which limits scope and impacts feasibility for Production Intune Pilot.
Transport are not certain on the testing skills of some of their resources and the confidence that they will test accurately enough to go live.
Travel to Soyo location is uncertain, depending on weather conditions and airport availability
Trizetto working-level staff desired more rigorous disaster recovery and high availability failover than standard provided in scoped delivery.
Trust needs to be in place by May 1st in order to meet the date of PILOT Migrations starting on May 8th
Two to four dedicated training venues in order to run end user training for PVC, Document Management, Balance of Apps and Inactive waves of applications simultaneously.
UAT end date on Feb 24 to keep current go-live • It is the main risk right now on the project. Still challenging to do so but strong mobilization of all actors (VP, HLI, MS) and VPN access will make the difference the coming 2 weeks. • Get Okan (Veripark) on-site the coming week too and get Ertu (Veripark) on-site the following week too. • 2 challenging weeks to secure the UAT process.
UAT Environment and Apps configuration
UAT Environment Concerns and Readiness for UAT with-in Azure 2 days to 2 weeks required for this and to be factored into plan.
UAT plan not in place, missing end user guidelines
UAT Testers Some (if not most) invited UAT testers are new to NGCSB project. With only UAT coaching session(s), it is not sufficient to get UAT testers familiar with NGCSB and be able to validate the functionalities in Step 1.
UC ACM Schedule possible extension
U-Drives are heavily used (180 Terabyte, 1.3 GB per user on average)
UI color changes done in Stab phase decreased our testing capacity and diluted the focus of Dev team. Quality issues, especially on the UI and text, might appear when entering UAT
UI will not be ready on time delaying front end build.
UK Timber go live has been delayed and may require additional support from project team.
UK.GOV UI templates cannot be used in certain UI scenarios
Unable to achieve the gross revenue under the current FF contract based on low migration velocity.
Unable to complete offshore build testing in the time allocated in the plan
Unable to find needed skillset with-in Microsoft
Unable to provide resource to complete the Brand SoG CR
Unable to resolve all isses during the Bridge Support period
Unable to support a September start of migration as originally planned.
Unable to sync work with Level 5
Unable to upload large files to the DEV/PROD Azure SCCM Server
Unavailability of ~total 24 APIs to support completion of SPRINT 1
Unavailability of an On-site consultant may hinder project progress.
Unavailability of binaries & install instructions. This is expected to be ong0ing throughout the project
Unavailability of binaries and installation instructions may eliminate server from scope
Unavailability of CRM Outlook functionality during UAT
Unavailability of Daimler key contact persons, e.g. for test data, lead to unavailability of test data for testing of services
Unavailability of Deputy Program Manager for a consistent 50% (20 hrs per week)
Unavailability of replacement project manager
Unavailability of the GOVTT technical team due to staff shortage may delay progress on project activities. The timelines for completion of activities for these projects are tight and overlap each other. The members of these teams are also on other projects and activities which are competing for their time and effort.
Unavailibility of resourcing for Microsoft may impact schedule and ability to meet deliverables
Unavalability of the technical staff led to the abandonment of some planned sessions. This will lead to delays in the coming and dependent activities
Uncertainty of scope and direction until PG and Daimler come to agreement
Unclear definition of scope, approach and project methodology.
Unconsumed BIF for FY17. Due to reduced burn rate of consultants, it is not possible to consume all the BIF allocated to the project.
Under evaluation a deployment strategy that includes a set of basic functionalities to be activated in Jan and a subsequent deployment strategy that will bring the full operativity by March. A multi release approach can cope with the customer expectations
Underestimation of the number of applications to be migrated in the scope of 23 applications
Understanding a more in depth knowledge of what VF needs for ITSM and what MCS is able to deliver.
Uniper will use E.ON Express route, this may impact performance
UNIQA must provide a binding offer to each country. This is a UNIQA Internal Process, but is a requirement for us to beging the migration.
Unique email feature may not be delivered during the project lifetime, and will need to be continued in new evolutive contract
Unplanned hours left for consumption
Unrealistic Dependency from Vendors
Unrealistic timeframe for testing impacts timeline and induces risk of re-planning
Unrecoverable CSAT situation
Unreliable connectivity to customer database (C360) is causing functionality and test issues
Unstable network connection
Untimely response from clients for remediation activities may cause project delays.
Upcoming holidays & vacations may impact availability of key customer contacts
Upgrade CRM 2016 failure
UPN change (remediation item B7) requires current and future Identity Management solution to be updated to align UPN=SMTP=SIP. MCS is engaged into the MIM project and we were informed that this project as not receive the requirement brought by B7. Issue: Failure to perform this task will not permit to close remediation item B7 and will prevent Enablement phase to start. ActionItem: Customer must request a change to the current plans for MIM and the current ID management processes to provide ongoing support to align UPN with SMTP and SIP.
UPN Remediation- External Risk
UPN - email address
Usability of MatterCenter with 3rd party tool called Epona.
Usage of Non Billable time: There is a contractual obligation for our Partners to provide a specific number of Non Billable time to the end customer. Upon Customer agreement we have decided to extend the end of the 1st calendar year until the end of March of 2017. Our proposal was sent and eventually agreed with the Customer Procurement Department. We have managed to come up with a substantial decrease of the non billable hours for calendar 2016.
Use of a varchar(50) will impact performance related to page splits and index re-sorts due to non-sequential inserts.
Use of IPv6 for PAW
Use of NAT between DCs (Domain Controllers) networks. NAT is not supported by Active Directory.
User bandwidth contention will reach the peak during July to Sep 2016 timeframe when all of the following critical tasks are running in parallel: Step 3.0 UAT: April to Sep 2016 Step 3.0 Data Conversion: July to Sep 2016 Step 2.0 UAT: July to Sep 2016 It was acknowledged in last PSC meeting that a Traffic champion is missing fundamentally in the project team. With the promotion of Sam Ho (Head of Research) effective in May, the project team is missing a Sales champion as well.
User observations for Copia Certificada consumption by DD
User Stories are varying quite much in size
User Stories continue to be added/enhanced as the result of continuing discussions regarding the STAR application functionality
User will use all function of SharePoint, Skype, and Exchange (outlook) to check its function. As happened for Windows 10 Mobile, Customer may find product bug/issue during their test.
User won´t give priority for testing all scenarios
Users will be Local administrators on client devices
USMT adds a level of complexity because of variations in models.
UTC presented two network designs during the networking workshop. Which network design does UTC prefer moving forward?
Utilising the hours from the offshore development bucket for offshore dev lead may result into difficulty in convincing client about the actual hours planned vs spend on the development
Utilization
UX Design will not be completed in accordance to what is outlined in the SOW due to the stopping work on 6/20/17, pending decisions from Tech Data management.
UX process on the project is not yielding results. The UX resource is having bandwidth issues to complete IA & Navigation etc. Also, the customer feedback on the UX is not positive.
VA Archiving solution(s) not compatible with Office 2016 / O365
VAA plan to use their AD in the new DEV and TEST environmetns they are created rather than using a TEST AD, therefore those using the DEV and TEST environments will be able to test Live (possibly confidential data) from both of these environments.
Vale cancel the contract if some partner offer a good proposal through RFP
Validation and user adoption
Variance in testing results being received from Mecklenburg Testing team
Variations around definition of minimal viable product for day 1 migrations.
VDF provisioning may be too slow for technical information and prerequisites and validation.
Velocity of Automated Tests may not meet deadline. GTIL expects the automated test suite to be completed and handed over to the Support team by 10/31. The GD Automated Test Factory team’s test creation velocity is lower than originally planned and may not be adequate to finish in time.
Veripark resources are only English speaking and the project will be completely delivered in French. HLi resources will facilitate and translate the documents. This risk is to be monitored closely for the first weeks of the project.
Very compressed timeline. Migration start/end dates maybe at risk
Very limited travel budget
Very stretched utilization ~30% fixed fee subcon resource generally, these resources has no ability to understand to MA Playbook
Very tight project schedule
Very tight schedule in Stage1 for DTU deploy
Very tight timeline for implementation of the MSDP in the expected follow-up project (phase 3)
Very very less people are familiar with MA Playbook content
victor might not have the expertise and knowledge to design pieces that are missing.
Viral Tenant Blocking Production Tenant for Yammer
Virus attack
Vitaliy(Consultant) is troubleshooting SCSM Console performance issues. This will slightly delay the project.
VM design to include additional agents/software not yet defined
vNext upgrade for SharePoint must be completed before migrations begin, which is currently scheduled to begin mid- to end of April.
Vodafone may have specific security reqirements that must be met to allow the project deliverables to be completed. Microsoft are not currently aware of specific requirements and therefore these cannot be planned. Specifically access to systems (identity, VPN) needed, rules of access to migration systems unclear.
VPN connectivity to On-Prem is required
VSTS 145: Delay in project kickoff may impact overall timeline.
VSTS 146: IATF requirements may impact availability of resources at Litens
VSTS 184: Legal Entities structure needs to be identified
Waiting the staff of 2 Resources on RUN for the Monitoring Team
Walmart Technical Expert/Leader for Azure, Jason Norris, is leaving Walmart on 8/5/2016.
Wave 1 user identification – Not yet determined who the wave 1 users will be. If these user groups not notified, issues may arise that prevent
We are following the Sure Step Evolved process to mitigate the risk.
We are implementing a CRM project for Dr. Lal Path Labs. In addition to CRM they are getting a dot net portal called LCM to be developed which will be used by internal as well as external users. There is a single database schema / entity set which is being used by CRM & LCM both. LCM portal will have some basic functionalities of CRM. The primary reason for investing into LCM portal is to cut down on the CRM licenses required. The same was apparently suggested by Microsoft presales team to the client. The ask from the customer is now to give them a formal confirmation that the use of LCM portal will not attract any CRM Licenses. Bit licensing team says that LCM will attract licenses
We are in the official AX7 TAP Program; customer signed off on the program, and is aware of the risks and potential product bugs etc. There is a full time PJM and a full time Solution Architect for potential issues during times that the consultants are working. Corp, is available within the boundaries of the TAP program.
We are not going to allow file transfer for regulated users - Users will still be able to send a link to other users instead of a FTP.
We are seeing delays in staffing scarce resources (e.g. RMS) and also fieldimg questions about approval status and FTC role when submitting some GRM requests
We do not have a travel budget planned for the resources travelling to site to meet with the customer.
We don’t have experience in converting Nintex to AgilePoint. This will be executed for the first time and we will have to skill the resources during the project
We have heard about SITA's efforts on completing this project by themselves by overhrowing MS.
We have major discrepancies between what the customer really wants vs. what we promised to deliver (what is the SoW).
We have one hours regular meeting among TMNA, TMC, MS once a week but it is not enough for project goal achievement. (frequency, length)
We have two bugs that are related to the browsers that we are using, both are the ones that SAT is using in the production environment
We have used a wet cost rate and a part of the wet rate (20$/hr) is allocated for expense. But based on the forecasted calculation we are around $8000 short due to this arrangement
We may not be able to identify resources with the appropriate skillset in time for phase 2 (i.e. similar engagement model to begin after 9/30). Assignment of the Dev resources has been delayed
We may not be able to transfer the operating and SQL licences running out of ASI
We need to get a memorandum of understanding agreed between the Azure B2C PG and the customer. This is because the product is still in preview.
We need to get the signed CR, the AA team will escalate it with the customer.
We need to review with different team in SAT, in order, to have the SISE Service en UAT, and the business user can test that functionality.
We need to understand the C1 approach to Hold API for us to wind up our design and development
We still don't have an ETA for sign in/up new policy delivery.
Weak governance, not addressing geographic, cultural and organizational complexity.
WF sent 9 laptops, however, only 3 of those are for technical team members and the remaining are all for governance team. Customer may think we are fully onboarded and expect higher velocities.
What MDM authority will be used within BP (Intune or Intune with SSCM)?
When Operation Team define the new squedule for implementation activities of Sumarizado Nómina 1.1, the squedule of build activities of Sumarizado Nómina 1.2 will be affected.
White Glove locations have not been confirmed for pilot and velocity migrations which may cause a delay in staffing needed resources
WHOLESALE: Business Accountable bottleneck
WHOLESALE: High number of interdependant blockers that impact timely delivery
WHOLESALE: Lack of availability of BS Lead Analyst
WHOLESALE: Low fit ratio may jeopardize the progress of this project
WHOLESALE: System knowledge missing in the test team
WIG API documentation. Documentation for this dependency (D382) is not expected until 10/28.
Win7 Packaging: There is a risk that we are working in a vacuum. We do not have visibility of the upstream pipeline (volume of apps to be packaged, their complexity, etc.) and therefore cannot forecast accurately. We also do not have visibility of downstream process (i.e. we deliver to BOI's UAT team but do not know how much of our deliverable has actually been reviewed). Lack of downstream visibility could again result in impact to schedule as reconfiguring packages at "end game" may become a significant demand. We are purely "on demand" and to date meeting all customer expectations.
With 4 weeks remaining to the sprint, all the 6 FDD will not be covered as part of this Pilot
With large amounts of CRs due to missed dependencies, the rigorous change management process may result in CSAT Issues
With no new date for Go live declared, a financial impact will be reported.
With the additional "needs" of the client, PM and SA hours may not be enough at total of 44/wk
With the current hours burn rate, PMA may not be able to support the project till the end date as per contract
With the involvment of the Governor's office in project level escalation of issues and risks, the team will likely only "Fail Forward" into production.
With the new government administration coming into power in January 2017, we are told that it's likely that ALL government projects will be stopped and re-evaluated in early January. We don't know how long this evaluation process will take place (if indeed it occurs).
Within the contract there are included some roles related to .net and sharepoint technologies, and according to the TO BE proposal, DNP will require more specializaed resources to develop the PIIP.
Without access to the current environment, it will be difficult to accurately assess the current state of the environment and plan accordingly.
Without any clear timeline for approval of remaining RDDs and/or CRs, the offshore development team is at risk of hitting idle time during the week of Aug. 15th.
Without Edge Sync, migrated users are recognized as external and will have issues booking boardrooms.
Without local EPS resources available, planned work cannot be done in the planned project time frame.
WM resources will be stretched and may not be able to manage migration tasks, UAT tasks, Post migration tasks, and Site remediation support tasks.
WMS Configuration not updated at E2E
WMT V2 tool is not working for the ADM Migrations
Wo signed not aligned with last request to the client
Work done twice, and additional activities due to base line delivery, include neither regional activations nor Brief 01031. Last could generate further changes which are not contemplated.
Work Permit not renewed.
Workday - SSO and MFA integration
Workers Council & Personal Rat will not agree to MS Europe Cloud
Workflow modifications may not be completed and tested in time for Go Live.
Workflow processes may need review before implementation.
Workload Migration has lots of dependency on customer, we need documentations like install instruction, configurationa nd architecture documents along with binaries from customer. If customer is not able to provide this documentation, it will lead to erosion of scope
Workplace Join must be completed
Workshop delays
Workstation discovered with SQL 2005 Express - If there are so many SQL 2005 Express instances in 7000 workstations, then we need to identify if this is in scope and we need to know if there is a plan to move them or if it will continue to have them.
Workstreams are still not fully defined, the OP-OP workstream can not start since the IGD team will need to be engaged due to the size of the new target site collections
Wrong usage of Severity and Priority
WS3 has an external dependence, that is, work being done by a 3rd party vendor (iWay) engaged by the City. Timelines are unknown and the City's vision for the MDM are not very clear to their internal.
WYP Staff Holidays
Xerox Separation - Xerox separation into two different companies has complicated the delivery process
YEC Business continuity is endangered due to Network Bandwidth in few locations is not capable to handle initial workload in YEC
Zoovel SDK is not mature and has bugs
Zscalar and OneLogin Impact
ZT is not providing prerequisites on time, and MS cannot progress as planned.